## GRAFICO
| sem1 | sem2 | sem3 | sem4 | sem5 | sem6 | sem7 | sem8 | sem9 | sem10 | sem11 | sem12 | sem13 | sem14 | sem15 | sem16 | sem17 | sem18 | sem19 | sem20 | sem21 | sem22 | sem23 | sem24 | sem25 | sem26 | sem27
Trazado | [5 empty] | 62.08% | 67.18% | 74.44% | 79.01% | 84.39% | 89.25% | 94.09% | 95.7% | 95.7% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
Yeso Cielo | [5 empty] | 81.96% | 81.96% | 91.4% | 91.4% | 91.4% | 91.4% | 91.4% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
Yeso Muro | [5 empty] | 67.51% | 73.1% | 77.5% | 85.26% | 91.98% | 97.96% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
Tabique 1° Cara | [5 empty] | 58.58% | 64.39% | 72.56% | 73.1% | 81% | 81.7% | 92.21% | 94.2% | 97.31% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
I. Sanitaria | [5 empty] | 69.87% | 75.52% | 75.52% | 82.24% | 81.97% | 86.82% | 86.82% | 86.82% | 89.78% | 96.29% | 97.36% | 97.47% | 98.71% | 99.14% | 99.14% | 99.14% | 99.52% | 100% | 100% | 100% | 100% | 100%
I. Eléctrica | [5 empty] | 50.63% | 52.99% | 56.92% | 59.34% | 63.26% | 66.75% | 70.68% | 72.18% | 81.43% | 89.41% | 93.22% | 96.83% | 98.33% | 99.09% | 99.14% | 99.14% | 99.14% | 99.84% | 100% | 100% | 100% | 100%
Extracción | [5 empty] | 54.45% | 58.64% | 62.56% | 66.75% | 68.53% | 68.74% | 73.8% | 74.31% | 74.31% | 83.94% | 86.33% | 91.23% | 94.95% | 97.85% | 99.57% | 99.57% | 100% | 100% | 100% | 100% | 100% | 100%
Tabique 2° Cara | [5 empty] | 45.69% | 52.19% | 54.71% | 54.82% | 63.37% | 63.37% | 63.96% | 69.93% | 80.84% | 90.05% | 91.35% | 91.4% | 99.89% | 99.95% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
Puertas | [5 empty] | 26.44% | 29.51% | 35.3% | 43.06% | 47.06% | 54.37% | 58.88% | 64.32% | 67.86% | 75.25% | 80.88% | 83.59% | 87.02% | 87.7% | 92.43% | 92.43% | 95.26% | 95.44% | 95.44% | 95.44% | 95.44% | 95.44%
Cerámicos | [5 empty] | 25.03% | 29.99% | 33.51% | 36.16% | 37% | 42.66% | 48.2% | 53.68% | 56.07% | 64.94% | 66.84% | 70.6% | 72.32% | 78.39% | 79% | 81.98% | 86.69% | 88.15% | 89.37% | 91.16% | 93.98% | 93.93%
Piso Vinilico | [5 empty] | 13.07% | 16.21% | 23.01% | 29.39% | 31.01% | 31.82% | 36.73% | 45.92% | 43.49% | 48.78% | 54.13% | 55.1% | 58.88% | 64.95% | 69.33% | 69.33% | 69.33% | 83.15% | 88.19% | 88.19% | 91.96% | 97.5%
Ventanas | [5 empty] | 31.52% | 43.86% | 43.86% | 43.86% | 53.45% | 61.22% | 60.3% | 58.93% | 63.05% | 70.32% | 75.58% | 80.16% | 81.53% | 87.01% | 90.5% | 93.06% | 93.92% | 95.24% | 95.24% | 95.24% | 95.24% | 95.24%
Baranda Cristal | [5 empty] | 2.687% | 2.687% | 2.687% | 2.687% | 2.687% | 2.687% | 2.687% | 2.687% | 2.687% | 2.687% | 2.687% | 2.687% | 2.687% | 4.999% | 4.999% | 8.062% | 16.07% | 22.76% | 37.17% | 59.23% | 68.56% | 92.09%
Pasta | [5 empty] | 44.37% | 46.36% | 60.76% | 72.65% | 81.34% | 81.34% | 82.26% | 83.17% | 83.17% | 82.55% | 82.71% | 83.01% | 83.01% | 83.17% | 83.17% | 84.54% | 86.83% | 86.83% | 86.83% | 86.83% | 86.83% | 92.85%
Pintura | [5 empty] | 13.89% | 15.2% | 19.41% | 26.4% | 26.54% | 29.39% | 30.56% | 31.83% | 32.66% | 35.82% | 35.82% | 39.58% | 42.14% | 51.27% | 54.37% | 56.33% | 59.84% | 60.35% | 60.57% | 60.57% | 60.87% | 62.89%
Muebles C/B | [5 empty] | 7.973% | 13.27% | 15.84% | 21.93% | 24.11% | 27.41% | 30.3% | 32.74% | 33.74% | 41.73% | 43.66% | 46.93% | 49.08% | 56.19% | 58.18% | 61.29% | 62.4% | 65.66% | 75.68% | 78.54% | 82.06% | 86.17%
Muebles Closet | [5 empty] | 2.042% | 2.042% | 6.235% | 10.16% | 12.09% | 16.82% | 18.65% | 25.96% | 28.22% | 34.72% | 34.72% | 34.72% | 37.09% | 43.32% | 45.23% | 50.76% | 54.31% | 55.17% | 65.14% | 67.61% | 72.18% | 74.92%
Cubiertas | [5 empty] | 2.15% | 2.15% | 9.137% | 21.02% | 27.41% | 27.41% | 27.41% | 36.09% | 36.09% | 43.86% | 45.58% | 45.69% | 45.69% | 54.82% | 57.56% | 63.96% | 64.87% | 73.1% | 73.1% | 82.23% | 82.23% | 100%
Retropintado | [5 empty] | 1.29% | 1.29% | 1.29% | 1.29% | 1.29% | 4.945% | 5.643% | 23.92% | 26.77% | 24.03% | 27.3% | 24.94% | 32.36% | 32.36% | 35.55% | 42.86% | 43.32% | 43.32% | 47.89% | 61.14% | 61.14% | 62.97%
0
|  | 27 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0.95443 | 0.93934 | 0.97499 | 0.95242 | 0.92093 | 0.92846 | 0.62886 | 0.86174 | 0.74924 | 1 | 0.62965
|  | 26 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0.95443 | 0.93979 | 0.91963 | 0.95242 | 0.68559 | 0.86826 | 0.6087 | 0.82062 | 0.72183 | 0.82234 | 0.61138
|  | 25 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0.95443 | 0.91157 | 0.88192 | 0.95242 | 0.5923 | 0.86826 | 0.60574 | 0.78542 | 0.67614 | 0.82234 | 0.61138
|  | 24 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0.95443 | 0.89365 | 0.88192 | 0.95242 | 0.37167 | 0.86826 | 0.60574 | 0.75684 | 0.65142 | 0.73096 | 0.47889
|  | 23 | 1 | 1 | 1 | 1 | 1 | 0.99839 | 1 | 1 | 0.95443 | 0.88147 | 0.8315 | 0.95242 | 0.22763 | 0.86826 | 0.60352 | 0.65661 | 0.55172 | 0.73096 | 0.4332
|  | 22 | 1 | 1 | 1 | 1 | 0.99516 | 0.9914 | 1 | 1 | 0.95255 | 0.86692 | 0.69334 | 0.93924 | 0.16071 | 0.86826 | 0.59835 | 0.62401 | 0.54312 | 0.64873 | 0.4332
Valores |  | 21 | 1 | 1 | 1 | 1 | 0.9914 | 0.9914 | 0.9957 | 1 | 0.92434 | 0.81976 | 0.69334 | 0.93064 | 0.080621 | 0.84542 | 0.56334 | 0.6129 | 0.50764 | 0.63959 | 0.42864
Promedio de Trazado | #REF! | 20 | 1 | 1 | 1 | 1 | 0.9914 | 0.9914 | 0.9957 | 1 | 0.92434 | 0.79002 | 0.69334 | 0.90505 | 0.049985 | 0.83171 | 0.54372 | 0.58182 | 0.45228 | 0.57563 | 0.35554
Suma de Yeso Cielo | #REF! | 19 | 1 | 1 | 1 | 1 | 0.9914 | 0.99086 | 0.9785 | 0.99946 | 0.87704 | 0.78392 | 0.64949 | 0.87011 | 0.049985 | 0.83171 | 0.51268 | 0.56193 | 0.4332 | 0.54822 | 0.32356
Suma de Yeso Muro | #REF! | 18 | 1 | 1 | 1 | 1 | 0.98709 | 0.98334 | 0.94948 | 0.99893 | 0.87016 | 0.72317 | 0.58884 | 0.81529 | 0.026874 | 0.8301 | 0.42138 | 0.4908 | 0.37086 | 0.45685 | 0.32356
Suma de Tabique 1° Cara | #REF! | 17 | 1 | 1 | 1 | 1 | 0.97471 | 0.96829 | 0.91231 | 0.914 | 0.83586 | 0.70597 | 0.55102 | 0.80158 | 0.026874 | 0.8301 | 0.39585 | 0.4693 | 0.34721 | 0.45685 | 0.24939
Suma de I. Sanitaria | #REF! | 16 | 1 | 1 | 1 | 1 | 0.97363 | 0.93224 | 0.86333 | 0.91346 | 0.80878 | 0.66844 | 0.5413 | 0.75584 | 0.026874 | 0.82714 | 0.35823 | 0.43661 | 0.34721 | 0.45578 | 0.27304
Suma de I. Eléctrica | #REF! | 15 | 1 | 1 | 1 | 1 | 0.96288 | 0.89408 | 0.83939 | 0.90052 | 0.75246 | 0.64936 | 0.48782 | 0.70317 | 0.026874 | 0.82553 | 0.35823 | 0.41726 | 0.34721 | 0.43858 | 0.24025
Suma de Extracción | #REF! | 14 | 0.957 | 1 | 1 | 0.97313 | 0.89778 | 0.81431 | 0.74306 | 0.80836 | 0.67856 | 0.56067 | 0.43487 | 0.63052 | 0.026874 | 0.83171 | 0.32665 | 0.33744 | 0.28217 | 0.36091 | 0.26766
Suma de Tabique 2° Cara | #REF! | 13 | 0.957 | 1 | 1 | 0.94195 | 0.86817 | 0.72183 | 0.74306 | 0.69925 | 0.64322 | 0.53685 | 0.45918 | 0.58934 | 0.026874 | 0.83171 | 0.31832 | 0.32741 | 0.2596 | 0.36091 | 0.23918 | 0.60653
Suma de Puertas | #REF! | 12 | 0.94088 | 0.914 | 1 | 0.92207 | 0.86817 | 0.70678 | 0.73795 | 0.63959 | 0.5888 | 0.48202 | 0.36735 | 0.60305 | 0.026874 | 0.82257 | 0.30555 | 0.30305 | 0.1865 | 0.27411 | 0.056435
Suma de Cerámicos | #REF! | 11 | 0.89245 | 0.914 | 0.97958 | 0.81696 | 0.86817 | 0.66754 | 0.68743 | 0.63368 | 0.54365 | 0.42658 | 0.31819 | 0.61218 | 0.026874 | 0.81344 | 0.29386 | 0.27411 | 0.16823 | 0.27411 | 0.049448
Suma de Piso Vinilico | #REF! | 10 | 0.84394 | 0.914 | 0.91984 | 0.80997 | 0.81971 | 0.63261 | 0.68528 | 0.63368 | 0.47056 | 0.36996 | 0.31008 | 0.53452 | 0.026874 | 0.81344 | 0.26538 | 0.24106 | 0.12093 | 0.27411 | 0.012899
Suma de Ventanas | #REF! | 9 | 0.79009 | 0.914 | 0.85256 | 0.73096 | 0.82241 | 0.59337 | 0.66754 | 0.54822 | 0.43057 | 0.36161 | 0.29388 | 0.43858 | 0.026874 | 0.72655 | 0.26403 | 0.21929 | 0.10158 | 0.21015 | 0.012899
Suma de Baranda Cristal | #REF! | 8 | 0.7444 | 0.914 | 0.77504 | 0.72559 | 0.75515 | 0.56918 | 0.62562 | 0.54715 | 0.35304 | 0.3351 | 0.23013 | 0.43858 | 0.026874 | 0.60761 | 0.1941 | 0.15838 | 0.062347 | 0.091371 | 0.012899
Suma de Pasta | #REF! | 7 | 0.67184 | 0.81965 | 0.73096 | 0.64389 | 0.75515 | 0.52995 | 0.58638 | 0.52189 | 0.29513 | 0.29989 | 0.16206 | 0.43858 | 0.026874 | 0.46357 | 0.15204 | 0.13267 | 0.020424 | 0.021499 | 0.012899
Suma de Muebles C/B | #REF! | 6 | 0.62078 | 0.81965 | 0.67507 | 0.58585 | 0.69872 | 0.5063 | 0.54446 | 0.45685 | 0.26444 | 0.25027 | 0.13073 | 0.31523 | 0.026874 | 0.44368 | 0.13894 | 0.079725 | 0.020424 | 0.021499 | 0.012899
Suma de Muebles Closet | sem1: #REF!; sem2: 5
Suma de Cubiertas | sem1: #REF!; sem2: 4
Suma de Retropintado | sem1: #REF!; sem2: 3
2
1

## DINAMICA
Etiquetas de fila | Máx. de PISO 1 | Máx. de PISO 2 | Máx. de PISO 3 | Máx. de PISO 4 | Máx. de PISO 5 | Máx. de PISO 6 | Máx. de PISO 7 | Máx. de PISO 8 | Máx. de PISO 9
FASE 1 | 24.06% | 11.7% | 0.9091% | 0% | 0% | 0% | 0% | 0% | 0%
Total general | 24.06% | 11.7% | 0.9091% | 0% | 0% | 0% | 0% | 0% | 0%
Etiquetas de fila | Máx. de PISO 1 | Máx. de PISO 2 | Máx. de PISO 3 | Máx. de PISO 4 | Máx. de PISO 5 | Máx. de PISO 6 | Máx. de PISO 7 | Máx. de PISO 8 | Máx. de PISO 9
FASE 2 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
Total general | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
Etiquetas de fila | Máx. de PISO 1 | Máx. de PISO 2 | Máx. de PISO 3 | Máx. de PISO 4 | Máx. de PISO 5 | Máx. de PISO 6 | Máx. de PISO 7 | Máx. de PISO 8 | Máx. de PISO 9
FASE 3 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
Total general | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
Etiquetas de fila | Máx. de PISO 1 | Máx. de PISO 2 | Máx. de PISO 3 | Máx. de PISO 4 | Máx. de PISO 5 | Máx. de PISO 6 | Máx. de PISO 7 | Máx. de PISO 8 | Máx. de PISO 9
FASE 4 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
Total general | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
Etiquetas de fila | Máx. de PISO 1 | Máx. de PISO 2 | Máx. de PISO 3 | Máx. de PISO 4 | Máx. de PISO 5 | Máx. de PISO 6 | Máx. de PISO 7 | Máx. de PISO 8 | Máx. de PISO 9
FASE 4 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
Total general | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
Máx. de PISO 1 | Máx. de PISO 2 | Máx. de PISO 3 | Máx. de PISO 4 | Máx. de PISO 5 | Máx. de PISO 6 | Máx. de PISO 7 | Máx. de PISO 8 | Máx. de PISO 9
6.016% | 2.924% | 0.2273% | 0% | 0% | 0% | 0% | 0% | 0%

## FASE 4
Avance General
CONTROL AVANCE FASE 4 SAN FRANCISCO 211
[12 empty] | Cantidad de Deptos. | 359 | 0%
|  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
| Deptos. | Instalacion de Artefactos Sanitarios. | Extractor de baño. | Instalación de Shower Door | Instalacion de Espejos y Retropintados | Kit de cocina (Horno-Encimera -Campana - Lavaplato) | Griferia. | Pruebas de Instalaciones. | Piso Flotante + cubrejunta + junquillo | Protección Piso Flotante | 2da Mano de Pintura | Instalación de Papel Mural | Topes en piso y Accesorios | Avance Real x Piso
PISO N° 1 | DEPTO 102 | [12 empty] | 0% | bar: 1 to 12
| DEPTO 103 | [12 empty] | 0% | bar: 1 to 12
| DEPTO 104 | [12 empty] | 0% | bar: 1 to 12
| DEPTO 105 | [12 empty] | 0% | bar: 1 to 12
| DEPTO 106 | [12 empty] | 0% | bar: 1 to 12
| DEPTO 107 | [12 empty] | 0% | bar: 1 to 12
| DEPTO 108 | [12 empty] | 0% | bar: 1 to 12
| DEPTO 118 | [12 empty] | 0% | bar: 1 to 12
| DEPTO 119 | [12 empty] | 0% | bar: 1 to 12
| DEPTO 120 | [12 empty] | 0% | bar: 1 to 12
| DEPTO 121 | [12 empty] | 0% | bar: 1 to 12
| LOCAL 1 | [12 empty] | 0% | bar: 1 to 12
| LOCAL 2 | [12 empty] | 0% | bar: 1 to 12
| LOCAL 3 | [12 empty] | 0% | bar: 1 to 12
| LOCAL 4 | [12 empty] | 0% | bar: 1 to 12
| LOCAL 5 | [12 empty] | 0% | bar: 1 to 12
| LOCAL 6 | [12 empty] | 0% | bar: 1 to 12
| LOCAL 7 | [12 empty] | 0% | bar: 1 to 12
| LOCAL 8 | [12 empty] | 0% | bar: 1 to 12
| LOCAL 9 | [12 empty] | 0% | bar: 1 to 12
| COWORK | [12 empty] | 0% | bar: 1 to 12
| GIMNASIO | [12 empty] | 0% | bar: 1 to 12
| SALON GOURMET 1 | [12 empty] | 0% | bar: 1 to 12
| SALON GOURMET 2 | [12 empty] | 0% | bar: 1 to 12
GRAFICO DE AVANCE POR PARTIDA
PORCENTAJE POR PARTIDA | bar: 1 to 12
AVANCE GENERAL PISO N° 1 | bar: 1
PISO N° 2 A | Depto 202 | [12 empty] | 0% | bar: 1 to 12
| Depto.203 | [12 empty] | 0% | bar: 1 to 12
| Depto.204 | [12 empty] | 0% | bar: 1 to 12
| Depto.205 | [12 empty] | 0% | bar: 1 to 12
| Depto.206 | [12 empty] | 0% | bar: 1 to 12
| Depto.207 | [12 empty] | 0% | bar: 1 to 12
| Depto.208 | [12 empty] | 0% | bar: 1 to 12
| Depto.209 | [12 empty] | 0% | bar: 1 to 12
| Depto.210 | [12 empty] | 0% | bar: 1 to 12
| Depto.211 | [12 empty] | 0% | bar: 1 to 12
| Depto.212 | [12 empty] | 0% | bar: 1 to 12
| Depto.213 | [12 empty] | 0% | bar: 1 to 12
| Depto.214 | [12 empty] | 0% | bar: 1 to 12
| Depto.215 | [12 empty] | 0% | bar: 1 to 12
| Depto.216 | [12 empty] | 0% | bar: 1 to 12
| Depto.217 | [12 empty] | 0% | bar: 1 to 12
| Depto.218 | [12 empty] | 0% | bar: 1 to 12
| Depto.219 | [12 empty] | 0% | bar: 1 to 12
| Depto.220 | [12 empty] | 0% | bar: 1 to 12
| Depto.221 | [12 empty] | 0% | bar: 1 to 12
| Depto.222 | [12 empty] | 0% | bar: 1 to 12
| Depto.223 | [12 empty] | 0% | bar: 1 to 12
PISO N° 2 B | Depto.201 | [12 empty] | 0% | bar: 1 to 12
| Depto.202 | [12 empty] | 0% | bar: 1 to 12
| Depto.203 | [12 empty] | 0% | bar: 1 to 12
| Depto.204 | [12 empty] | 0% | bar: 1 to 12
| Depto.205 | [12 empty] | 0% | bar: 1 to 12
| Depto.206 | [12 empty] | 0% | bar: 1 to 12
| Depto.207 | [12 empty] | 0% | bar: 1 to 12
| Depto.208 | [12 empty] | 0% | bar: 1 to 12
| Depto.209 | [12 empty] | 0% | bar: 1 to 12
| Depto.210 | [12 empty] | 0% | bar: 1 to 12
| Depto.211 | [12 empty] | 0% | bar: 1 to 12
| Depto.212 | [12 empty] | 0% | bar: 1 to 12
| Depto.213 | [12 empty] | 0% | bar: 1 to 12
| Depto.214 | [12 empty] | 0% | bar: 1 to 12
| Depto.215 | [12 empty] | 0% | bar: 1 to 12
| Depto.216 | [12 empty] | 0% | bar: 1 to 12
| Depto.217 | [12 empty] | 0% | bar: 1 to 12
| Depto.218 | [12 empty] | 0% | bar: 1 to 12
| Depto.219 | [12 empty] | 0% | bar: 1 to 12
| Depto.220 | [12 empty] | 0% | bar: 1 to 12
| Depto.221 | [12 empty] | 0% | bar: 1 to 12
GRAFICO DE AVANCE POR PARTIDA
PORCENTAJE POR PARTIDA | bar: 1 to 12
AVANCE GENERAL PISO N° 2 | bar: 1
PISO N°3 A | Depto.301 | [12 empty] | 0% | bar: 1 to 12
Depto.302 | bar: 1 to 12
Depto.303 | bar: 1 to 12
Depto.304 | bar: 1 to 12
Depto.305 | bar: 1 to 12
Depto.306 | bar: 1 to 12
Depto.307 | bar: 1 to 12
Depto.308 | bar: 1 to 12
Depto.309 | bar: 1 to 12
| Depto.310 | [12 empty] | 0% | bar: 1 to 12
| Depto.311 | [12 empty] | 0% | bar: 1 to 12
| Depto.312 | [12 empty] | 0% | bar: 1 to 12
| Depto.313 | [12 empty] | 0% | bar: 1 to 12
| Depto.314 | [12 empty] | 0% | bar: 1 to 12
| Depto.315 | [12 empty] | 0% | bar: 1 to 12
| Depto.316 | [12 empty] | 0% | bar: 1 to 12
| Depto.317 | [12 empty] | 0% | bar: 1 to 12
| Depto.318 | [12 empty] | 0% | bar: 1 to 12
| Depto.319 | [12 empty] | 0% | bar: 1 to 12
| Depto.320 | [12 empty] | 0% | bar: 1 to 12
| Depto.321 | [12 empty] | 0% | bar: 1 to 12
| Depto.322 | [12 empty] | 0% | bar: 1 to 12
| Depto.323 | [12 empty] | 0% | bar: 1 to 12
PISO N°3 B | Depto.301 | [12 empty] | 0% | bar: 1 to 12
| Depto.302 | [12 empty] | 0% | bar: 1 to 12
| Depto.303 | [12 empty] | 0% | bar: 1 to 12
| Depto.304 | [12 empty] | 0% | bar: 1 to 12
| Depto.305 | [12 empty] | 0% | bar: 1 to 12
| Depto.306 | [12 empty] | 0% | bar: 1 to 12
| Depto.307 | [12 empty] | 0% | bar: 1 to 12
| Depto.308 | [12 empty] | 0% | bar: 1 to 12
| Depto.309 | [12 empty] | 0% | bar: 1 to 12
| Depto.310 | [12 empty] | 0% | bar: 1 to 12
| Depto.311 | [12 empty] | 0% | bar: 1 to 12
| Depto.312 | [12 empty] | 0% | bar: 1 to 12
| Depto.313 | [12 empty] | 0% | bar: 1 to 12
| Depto.314 | [12 empty] | 0% | bar: 1 to 12
| Depto.315 | [12 empty] | 0% | bar: 1 to 12
| Depto.316 | [12 empty] | 0% | bar: 1 to 12
| Depto.317 | [12 empty] | 0% | bar: 1 to 12
| Depto.318 | [12 empty] | 0% | bar: 1 to 12
| Depto.319 | [12 empty] | 0% | bar: 1 to 12
| Depto.320 | [12 empty] | 0% | bar: 1 to 12
| Depto.321 | [12 empty] | 0% | bar: 1 to 12
GRAFICO DE AVANCE POR PARTIDA
PORCENTAJE POR PARTIDA | bar: 1 to 12
AVANCE GENERAL PISO N° 3 | bar: 1
PISO N°4 A | Depto.401 | [12 empty] | 0% | bar: 1 to 12
| Depto.402 | [12 empty] | 0% | bar: 1 to 12
| Depto.403 | [12 empty] | 0% | bar: 1 to 12
| Depto.404 | [12 empty] | 0% | bar: 1 to 12
| Depto.405 | [12 empty] | 0% | bar: 1 to 12
| Depto.406 | [12 empty] | 0% | bar: 1 to 12
| Depto.407 | [12 empty] | 0% | bar: 1 to 12
| Depto.408 | [12 empty] | 0% | bar: 1 to 12
| Depto.409 | [12 empty] | 0% | bar: 1 to 12
| Depto.410 | [12 empty] | 0% | bar: 1 to 12
| Depto.411 | [12 empty] | 0% | bar: 1 to 12
| Depto.412 | [12 empty] | 0% | bar: 1 to 12
| Depto.413 | [12 empty] | 0% | bar: 1 to 12
| Depto.414 | [12 empty] | 0% | bar: 1 to 12
| Depto.415 | [12 empty] | 0% | bar: 1 to 12
| Depto.416 | [12 empty] | 0% | bar: 1 to 12
| Depto.417 | [12 empty] | 0% | bar: 1 to 12
| Depto.418 | [12 empty] | 0% | bar: 1 to 12
| Depto.419 | [12 empty] | 0% | bar: 1 to 12
| Depto.420 | [12 empty] | 0% | bar: 1 to 12
| Depto.421 | [12 empty] | 0% | bar: 1 to 12
| Depto.422 | [12 empty] | 0% | bar: 1 to 12
| Depto.423 | [12 empty] | 0% | bar: 1 to 12
PISO N°4 B | Depto.401 | [12 empty] | 0% | bar: 1 to 12
| Depto.402 | [12 empty] | 0% | bar: 1 to 12
| Depto.403 | [12 empty] | 0% | bar: 1 to 12
| Depto.404 | [12 empty] | 0% | bar: 1 to 12
| Depto.405 | [12 empty] | 0% | bar: 1 to 12
| Depto.406 | [12 empty] | 0% | bar: 1 to 12
| Depto.407 | [12 empty] | 0% | bar: 1 to 12
| Depto.408 | [12 empty] | 0% | bar: 1 to 12
| Depto.409 | [12 empty] | 0% | bar: 1 to 12
| Depto.410 | [12 empty] | 0% | bar: 1 to 12
| Depto.411 | [12 empty] | 0% | bar: 1 to 12
| Depto.412 | [12 empty] | 0% | bar: 1 to 12
| Depto.413 | [12 empty] | 0% | bar: 1 to 12
| Depto.414 | [12 empty] | 0% | bar: 1 to 12
| Depto.415 | [12 empty] | 0% | bar: 1 to 12
| Depto.416 | [12 empty] | 0% | bar: 1 to 12
| Depto.417 | [12 empty] | 0% | bar: 1 to 12
| Depto.418 | [12 empty] | 0% | bar: 1 to 12
| Depto.419 | [12 empty] | 0% | bar: 1 to 12
| Depto.420 | [12 empty] | 0% | bar: 1 to 12
| Depto.421 | [12 empty] | 0% | bar: 1 to 12
GRAFICO DE AVANCE POR PARTIDA
PORCENTAJE POR PARTIDA | bar: 1 to 12
AVANCE GENERAL PISO N° 4 | bar: 1
PISO N°5 A | Depto.501 | [12 empty] | 0% | bar: 1 to 12
Depto.502 | bar: 1 to 12
Depto.503 | bar: 1 to 12
Depto.504 | bar: 1 to 12
Depto.505 | bar: 1 to 12
Depto.506 | bar: 1 to 12
Depto.507 | bar: 1 to 12
Depto.508 | bar: 1 to 12
Depto.509 | bar: 1 to 12
| Depto.510 | [12 empty] | 0% | bar: 1 to 12
| Depto.511 | [12 empty] | 0% | bar: 1 to 12
| Depto.512 | [12 empty] | 0% | bar: 1 to 12
| Depto.513 | [12 empty] | 0% | bar: 1 to 12
| Depto.514 | [12 empty] | 0% | bar: 1 to 12
| Depto.515 | [12 empty] | 0% | bar: 1 to 12
| Depto.516 | [12 empty] | 0% | bar: 1 to 12
| Depto.517 | [12 empty] | 0% | bar: 1 to 12
| Depto.518 | [12 empty] | 0% | bar: 1 to 12
| Depto.519 | [12 empty] | 0% | bar: 1 to 12
| Depto.520 | [12 empty] | 0% | bar: 1 to 12
| Depto.521 | [12 empty] | 0% | bar: 1 to 12
| Depto.522 | [12 empty] | 0% | bar: 1 to 12
| Depto.523 | [12 empty] | 0% | bar: 1 to 12
PISO N°5 B | Depto.501 | [12 empty] | 0% | bar: 1 to 12
| Depto.502 | [12 empty] | 0% | bar: 1 to 12
| Depto.503 | [12 empty] | 0% | bar: 1 to 12
| Depto.504 | [12 empty] | 0% | bar: 1 to 12
| Depto.505 | [12 empty] | 0% | bar: 1 to 12
| Depto.506 | [12 empty] | 0% | bar: 1 to 12
| Depto.507 | [12 empty] | 0% | bar: 1 to 12
| Depto.508 | [12 empty] | 0% | bar: 1 to 12
| Depto.509 | [12 empty] | 0% | bar: 1 to 12
| Depto.510 | [12 empty] | 0% | bar: 1 to 12
| Depto.511 | [12 empty] | 0% | bar: 1 to 12
| Depto.512 | [12 empty] | 0% | bar: 1 to 12
| Depto.513 | [12 empty] | 0% | bar: 1 to 12
| Depto.514 | [12 empty] | 0% | bar: 1 to 12
| Depto.515 | [12 empty] | 0% | bar: 1 to 12
| Depto.516 | [12 empty] | 0% | bar: 1 to 12
| Depto.517 | [12 empty] | 0% | bar: 1 to 12
| Depto.518 | [12 empty] | 0% | bar: 1 to 12
| Depto.519 | [12 empty] | 0% | bar: 1 to 12
| Depto.520 | [12 empty] | 0% | bar: 1 to 12
| Depto.521 | [12 empty] | 0% | bar: 1 to 12
GRAFICO DE AVANCE POR PARTIDA
PORCENTAJE POR PARTIDA | bar: 1 to 12
AVANCE GENERAL PISO N° 5 | bar: 1
PISO N°6 A | Depto.601 | [12 empty] | 0% | bar: 1 to 12
| Depto.602 | [12 empty] | 0% | bar: 1 to 12
| Depto.603 | [12 empty] | 0% | bar: 1 to 12
| Depto.604 | [12 empty] | 0% | bar: 1 to 12
| Depto.605 | [12 empty] | 0% | bar: 1 to 12
| Depto.606 | [12 empty] | 0% | bar: 1 to 12
| Depto.607 | [12 empty] | 0% | bar: 1 to 12
| Depto.608 | [12 empty] | 0% | bar: 1 to 12
| Depto.609 | [12 empty] | 0% | bar: 1 to 12
| Depto.610 | [12 empty] | 0% | bar: 1 to 12
| Depto.611 | [12 empty] | 0% | bar: 1 to 12
| Depto.612 | [12 empty] | 0% | bar: 1 to 12
| Depto.613 | [12 empty] | 0% | bar: 1 to 12
| Depto.614 | [12 empty] | 0% | bar: 1 to 12
| Depto.615 | [12 empty] | 0% | bar: 1 to 12
| Depto.616 | [12 empty] | 0% | bar: 1 to 12
| Depto.617 | [12 empty] | 0% | bar: 1 to 12
| Depto.618 | [12 empty] | 0% | bar: 1 to 12
| Depto.619 | [12 empty] | 0% | bar: 1 to 12
| Depto.620 | [12 empty] | 0% | bar: 1 to 12
| Depto.621 | [12 empty] | 0% | bar: 1 to 12
| Depto.622 | [12 empty] | 0% | bar: 1 to 12
| Depto.623 | [12 empty] | 0% | bar: 1 to 12
PISO N°6 B | Depto.601 | [12 empty] | 0% | bar: 1 to 12
| Depto.602 | [12 empty] | 0% | bar: 1 to 12
| Depto.603 | [12 empty] | 0% | bar: 1 to 12
| Depto.604 | [12 empty] | 0% | bar: 1 to 12
| Depto.605 | [12 empty] | 0% | bar: 1 to 12
| Depto.606 | [12 empty] | 0% | bar: 1 to 12
| Depto.607 | [12 empty] | 0% | bar: 1 to 12
| Depto.608 | [12 empty] | 0% | bar: 1 to 12
| Depto.609 | [12 empty] | 0% | bar: 1 to 12
| Depto.610 | [12 empty] | 0% | bar: 1 to 12
| Depto.611 | [12 empty] | 0% | bar: 1 to 12
| Depto.612 | [12 empty] | 0% | bar: 1 to 12
| Depto.613 | [12 empty] | 0% | bar: 1 to 12
| Depto.614 | [12 empty] | 0% | bar: 1 to 12
| Depto.615 | [12 empty] | 0% | bar: 1 to 12
| Depto.616 | [12 empty] | 0% | bar: 1 to 12
| Depto.617 | [12 empty] | 0% | bar: 1 to 12
| Depto.618 | [12 empty] | 0% | bar: 1 to 12
| Depto.619 | [12 empty] | 0% | bar: 1 to 12
| Depto.620 | [12 empty] | 0% | bar: 1 to 12
| Depto.621 | [12 empty] | 0% | bar: 1 to 12
GRAFICO DE AVANCE POR PARTIDA
PORCENTAJE POR PARTIDA | bar: 1 to 12
AVANCE GENERAL PISO N° 6 | bar: 1
PISO N°7 A | Depto.701 | [12 empty] | 0% | bar: 1 to 12
| Depto.702 | [12 empty] | 0% | bar: 1 to 12
| Depto703 | [12 empty] | 0% | bar: 1 to 12
| Depto.704 | [12 empty] | 0% | bar: 1 to 12
| Depto.705 | [12 empty] | 0% | bar: 1 to 12
| Depto.706 | [12 empty] | 0% | bar: 1 to 12
| Depto.707 | [12 empty] | 0% | bar: 1 to 12
| Depto.708 | [12 empty] | 0% | bar: 1 to 12
| Depto.709 | [12 empty] | 0% | bar: 1 to 12
| Depto.710 | [12 empty] | 0% | bar: 1 to 12
| Depto.711 | [12 empty] | 0% | bar: 1 to 12
| Depto.712 | [12 empty] | 0% | bar: 1 to 12
| Depto.713 | [12 empty] | 0% | bar: 1 to 12
| Depto.714 | [12 empty] | 0% | bar: 1 to 12
| Depto.715 | [12 empty] | 0% | bar: 1 to 12
| Depto.716 | [12 empty] | 0% | bar: 1 to 12
| Depto.717 | [12 empty] | 0% | bar: 1 to 12
| Depto.718 | [12 empty] | 0% | bar: 1 to 12
| Depto.719 | [12 empty] | 0% | bar: 1 to 12
| Depto.720 | [12 empty] | 0% | bar: 1 to 12
| Depto.721 | [12 empty] | 0% | bar: 1 to 12
| Depto.722 | [12 empty] | 0% | bar: 1 to 12
| Depto.723 | [12 empty] | 0% | bar: 1 to 12
PISO N°7 B | Depto.701 | [12 empty] | 0% | bar: 1 to 12
| Depto.702 | [12 empty] | 0% | bar: 1 to 12
| Depto.703 | [12 empty] | 0% | bar: 1 to 12
| Depto.704 | [12 empty] | 0% | bar: 1 to 12
| Depto.705 | [12 empty] | 0% | bar: 1 to 12
| Depto.706 | [12 empty] | 0% | bar: 1 to 12
| Depto.707 | [12 empty] | 0% | bar: 1 to 12
| Depto.708 | [12 empty] | 0% | bar: 1 to 12
| Depto.709 | [12 empty] | 0% | bar: 1 to 12
| Depto.710 | [12 empty] | 0% | bar: 1 to 12
| Depto.711 | [12 empty] | 0% | bar: 1 to 12
| Depto.712 | [12 empty] | 0% | bar: 1 to 12
| Depto.713 | [12 empty] | 0% | bar: 1 to 12
| Depto.714 | [12 empty] | 0% | bar: 1 to 12
| Depto.715 | [12 empty] | 0% | bar: 1 to 12
| Depto.716 | [12 empty] | 0% | bar: 1 to 12
| Depto.717 | [12 empty] | 0% | bar: 1 to 12
| Depto.718 | [12 empty] | 0% | bar: 1 to 12
| Depto.719 | [12 empty] | 0% | bar: 1 to 12
| Depto.720 | [12 empty] | 0% | bar: 1 to 12
| Depto.721 | [12 empty] | 0% | bar: 1 to 12
GRAFICO DE AVANCE POR PARTIDA
PORCENTAJE POR PARTIDA | bar: 1 to 12
AVANCE GENERAL PISO N° 7 | bar: 1
PISO N°8 A | Depto.801 | [12 empty] | 0% | bar: 1 to 12
| Depto.802 | [12 empty] | 0% | bar: 1 to 12
| Depto803 | [12 empty] | 0% | bar: 1 to 12
| Depto.804 | [12 empty] | 0% | bar: 1 to 12
| Depto.805 | [12 empty] | 0% | bar: 1 to 12
| Depto.806 | [12 empty] | 0% | bar: 1 to 12
| Depto.807 | [12 empty] | 0% | bar: 1 to 12
| Depto.808 | [12 empty] | 0% | bar: 1 to 12
| Depto.809 | [12 empty] | 0% | bar: 1 to 12
| Depto.810 | [12 empty] | 0% | bar: 1 to 12
| Depto.811 | [12 empty] | 0% | bar: 1 to 12
| Depto.812 | [12 empty] | 0% | bar: 1 to 12
| Depto.813 | [12 empty] | 0% | bar: 1 to 12
| Depto.814 | [12 empty] | 0% | bar: 1 to 12
| Depto.815 | [12 empty] | 0% | bar: 1 to 12
| Depto.816 | [12 empty] | 0% | bar: 1 to 12
| Depto.817 | [12 empty] | 0% | bar: 1 to 12
| Depto.818 | [12 empty] | 0% | bar: 1 to 12
| Depto.819 | [12 empty] | 0% | bar: 1 to 12
| Depto.820 | [12 empty] | 0% | bar: 1 to 12
| Depto.821 | [12 empty] | 0% | bar: 1 to 12
| Depto.822 | [12 empty] | 0% | bar: 1 to 12
| Depto.823 | [12 empty] | 0% | bar: 1 to 12
PISO N°8 B | Depto.801 | [12 empty] | 0% | bar: 1 to 12
| Depto.802 | [12 empty] | 0% | bar: 1 to 12
| Depto.803 | [12 empty] | 0% | bar: 1 to 12
| Depto.804 | [12 empty] | 0% | bar: 1 to 12
| Depto.805 | [12 empty] | 0% | bar: 1 to 12
| Depto.806 | [12 empty] | 0% | bar: 1 to 12
| Depto.807 | [12 empty] | 0% | bar: 1 to 12
| Depto.808 | [12 empty] | 0% | bar: 1 to 12
| Depto.809 | [12 empty] | 0% | bar: 1 to 12
| Depto.810 | [12 empty] | 0% | bar: 1 to 12
| Depto.811 | [12 empty] | 0% | bar: 1 to 12
| Depto.812 | [12 empty] | 0% | bar: 1 to 12
| Depto.813 | [12 empty] | 0% | bar: 1 to 12
| Depto.814 | [12 empty] | 0% | bar: 1 to 12
| Depto.815 | [12 empty] | 0% | bar: 1 to 12
| Depto.816 | [12 empty] | 0% | bar: 1 to 12
| Depto.817 | [12 empty] | 0% | bar: 1 to 12
| Depto.818 | [12 empty] | 0% | bar: 1 to 12
| Depto.819 | [12 empty] | 0% | bar: 1 to 12
| Depto.820 | [12 empty] | 0% | bar: 1 to 12
| Depto.821 | [12 empty] | 0% | bar: 1 to 12
GRAFICO DE AVANCE POR PARTIDA
PORCENTAJE POR PARTIDA | bar: 1 to 12
AVANCE GENERAL PISO N° 8 | bar: 1
PISO N°9 A | Depto.901 | [12 empty] | 0% | bar: 1 to 12
| Depto.902 | [12 empty] | 0% | bar: 1 to 12
| Depto.903 | [12 empty] | 0% | bar: 1 to 12
| Depto.904 | [12 empty] | 0% | bar: 1 to 12
| Depto.905 | [12 empty] | 0% | bar: 1 to 12
| Depto.906 | [12 empty] | 0% | bar: 1 to 12
| Depto.907 | [12 empty] | 0% | bar: 1 to 12
| Depto.908 | [12 empty] | 0% | bar: 1 to 12
| Depto.909 | [12 empty] | 0% | bar: 1 to 12
| Depto.910 | [12 empty] | 0% | bar: 1 to 12
| Depto.911 | [12 empty] | 0% | bar: 1 to 12
| Depto.912 | [12 empty] | 0% | bar: 1 to 12
| Depto.913 | [12 empty] | 0% | bar: 1 to 12
| Depto.914 | [12 empty] | 0% | bar: 1 to 12
| Depto.915 | [12 empty] | 0% | bar: 1 to 12
| Depto.916 | [12 empty] | 0% | bar: 1 to 12
| Depto.917 | [12 empty] | 0% | bar: 1 to 12
| Depto.918 | [12 empty] | 0% | bar: 1 to 12
| Depto.919 | [12 empty] | 0% | bar: 1 to 12
| Depto.923 | [12 empty] | 0% | bar: 1 to 12
PISO N°9 B | Depto.901 | [12 empty] | 0% | bar: 1 to 12
| Depto.902 | [12 empty] | 0% | bar: 1 to 12
| Depto.903 | [12 empty] | 0% | bar: 1 to 12
| Depto.904 | [12 empty] | 0% | bar: 1 to 12
| Depto.905 | [12 empty] | 0% | bar: 1 to 12
| Depto.906 | [12 empty] | 0% | bar: 1 to 12
| Depto.907 | [12 empty] | 0% | bar: 1 to 12
| Depto.908 | [12 empty] | 0% | bar: 1 to 12
| Depto.909 | [12 empty] | 0% | bar: 1 to 12
| Depto.910 | [12 empty] | 0% | bar: 1 to 12
| Depto.911 | [12 empty] | 0% | bar: 1 to 12
| Depto.912 | [12 empty] | 0% | bar: 1 to 12
| Depto.913 | [12 empty] | 0% | bar: 1 to 12
| Depto.914 | [12 empty] | 0% | bar: 1 to 12
| Depto.915 | [12 empty] | 0% | bar: 1 to 12
| Depto.916 | [12 empty] | 0% | bar: 1 to 12
| Depto.917 | [12 empty] | 0% | bar: 1 to 12
| Depto.918 | [12 empty] | 0% | bar: 1 to 12
| Depto.919 | [12 empty] | 0% | bar: 1 to 12
| Depto.920 | [12 empty] | 0% | bar: 1 to 12
| Depto.921 | [12 empty] | 0% | bar: 1 to 12
GRAFICO DE AVANCE POR PARTIDA
PORCENTAJE POR PARTIDA | bar: 1 to 12
AVANCE GENERAL PISO N° 9 | bar: 1
| PISO | Instalacion de Artefactos Sanitarios. | Extractor de baño. | Instalación de Shower Door | Instalacion de Espejos y Retropintados | Kit de cocina (Horno-Encimera -Campana - Lavaplato) | Griferia. | Pruebas de Instalaciones. | Piso Flotante + cubrejunta + junquillo | Protección Piso Flotante | 2da Mano de Pintura | Instalación de Papel Mural | Topes en piso y Accesorios | Avance Real x Piso
| Piso n°1 | [12 empty] | 0% | bar: 1 to 12
| Piso n°2 | [12 empty] | 0% | bar: 1 to 12
| Piso n°3 | [12 empty] | 0% | bar: 1 to 12
| Piso n°4 | [12 empty] | 0% | bar: 1 to 12
| Piso n°5 | [12 empty] | 0% | bar: 1 to 12
| Piso n°6 | [12 empty] | 0% | bar: 1 to 12
| Piso n°7 | [12 empty] | 0% | bar: 1 to 12
| Piso n°8 | [12 empty] | 0% | bar: 1 to 12
| Piso n°9 | [12 empty] | 0% | bar: 1 to 12
| AVANCE PARTIDA | [12 empty] | 0% | bar: 1 to 12
0%

## FASE 3
Avance General
CONTROL AVANCE FASE 3 SAN FRANCISCO 211
[21 empty] | Cantidad de Deptos. | 359 | 0.8818%
|  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21
| Deptos. | Instalación piernas de closet | Instalación Cornisas | Cuadratura de cajas. | Remate yeso y cornisas | Puertas interiores | Puertas de acceso y pasillo | Cerradura Puertas | Cableado Eléctrico y CCDD | Canterias | Empaste Muro Cielo | Instalacion Guardapolvo | Instalación de Baranda de Crital | Pintura Cielo Terrazas | Grano Muros Terrazas | Losalin Cielo Departamento | Pintura Cielo Baños | Instalacion de Muebles baño | Instalacion Muebles de cocina (Base) | Instalacion Muebles de cocina (Aereo) | Instalación cubiertas cocina | Muebles Interior closet | Avance Real x Piso
PISO N° 1 | DEPTO 102 | [21 empty] | 0% | bar: 1 to 21
| DEPTO 103 | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 4.762%
| DEPTO 104 | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 4.762%
| DEPTO 105 | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 4.762%
| DEPTO 106 | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 4.762%
| DEPTO 107 | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 4.762%
| DEPTO 108 | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 4.762%
| DEPTO 118 | [21 empty] | 0% | bar: 1 to 21
| DEPTO 119 | [21 empty] | 0% | bar: 1 to 21
| DEPTO 120 | 0% | 100% | 100% | 100% | 100% | 0% | 100% | 100% | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 0% | 80.95%
| DEPTO 121 | 0% | 100% | 100% | 100% | 100% | 0% | 100% | 100% | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 0% | 80.95%
| LOCAL 1 | [21 empty] | 0% | bar: 1 to 21
| LOCAL 2 | [21 empty] | 0% | bar: 1 to 21
| LOCAL 3 | [21 empty] | 0% | bar: 1 to 21
| LOCAL 4 | [21 empty] | 0% | bar: 1 to 21
| LOCAL 5 | [21 empty] | 0% | bar: 1 to 21
| LOCAL 6 | [21 empty] | 0% | bar: 1 to 21
| LOCAL 7 | [21 empty] | 0% | bar: 1 to 21
| LOCAL 8 | [21 empty] | 0% | bar: 1 to 21
| LOCAL 9 | [21 empty] | 0% | bar: 1 to 21
| COWORK | [21 empty] | 0% | bar: 1 to 21
| GIMNASIO | [21 empty] | 0% | bar: 1 to 21
| SALON GOURMET 1 | [21 empty] | 0% | bar: 1 to 21
| SALON GOURMET 2 | [21 empty] | 0% | bar: 1 to 21
GRAFICO DE AVANCE POR PARTIDA
PORCENTAJE POR PARTIDA |  | 0% | 8.333% | 33.33% | 8.333% | 8.333% | 0% | 8.333% | 8.333% | 0% | 8.333% | 8.333% | 8.333% | 8.333% | 8.333% | 8.333% | 8.333% | 8.333% | 8.333% | 8.333% | 8.333% | 0%
AVANCE GENERAL PISO N° 1 |  | 1: 7.937%
PISO N° 2 A | Depto 202 | [21 empty] | 0% | bar: 1 to 21
| Depto.203 | [21 empty] | 0% | bar: 1 to 21
| Depto.204 | [21 empty] | 0% | bar: 1 to 21
| Depto.205 | [21 empty] | 0% | bar: 1 to 21
| Depto.206 | [21 empty] | 0% | bar: 1 to 21
| Depto.207 | [21 empty] | 0% | bar: 1 to 21
| Depto.208 | [21 empty] | 0% | bar: 1 to 21
| Depto.209 | [21 empty] | 0% | bar: 1 to 21
| Depto.210 | [21 empty] | 0% | bar: 1 to 21
| Depto.211 | [21 empty] | 0% | bar: 1 to 21
| Depto.212 | [21 empty] | 0% | bar: 1 to 21
| Depto.213 | [21 empty] | 0% | bar: 1 to 21
| Depto.214 | [21 empty] | 0% | bar: 1 to 21
| Depto.215 | [21 empty] | 0% | bar: 1 to 21
| Depto.216 | [21 empty] | 0% | bar: 1 to 21
| Depto.217 | [21 empty] | 0% | bar: 1 to 21
| Depto.218 | [21 empty] | 0% | bar: 1 to 21
| Depto.219 | [21 empty] | 0% | bar: 1 to 21
| Depto.220 | [21 empty] | 0% | bar: 1 to 21
| Depto.221 | [21 empty] | 0% | bar: 1 to 21
| Depto.222 | [21 empty] | 0% | bar: 1 to 21
| Depto.223 | [21 empty] | 0% | bar: 1 to 21
PISO N° 2 B | Depto.201 | [21 empty] | 0% | bar: 1 to 21
| Depto.202 | [21 empty] | 0% | bar: 1 to 21
| Depto.203 | [21 empty] | 0% | bar: 1 to 21
| Depto.204 | [21 empty] | 0% | bar: 1 to 21
| Depto.205 | [21 empty] | 0% | bar: 1 to 21
| Depto.206 | [21 empty] | 0% | bar: 1 to 21
| Depto.207 | [21 empty] | 0% | bar: 1 to 21
| Depto.208 | [21 empty] | 0% | bar: 1 to 21
| Depto.209 | [21 empty] | 0% | bar: 1 to 21
| Depto.210 | [21 empty] | 0% | bar: 1 to 21
| Depto.211 | [21 empty] | 0% | bar: 1 to 21
| Depto.212 | [21 empty] | 0% | bar: 1 to 21
| Depto.213 | [21 empty] | 0% | bar: 1 to 21
| Depto.214 | [21 empty] | 0% | bar: 1 to 21
| Depto.215 | [21 empty] | 0% | bar: 1 to 21
| Depto.216 | [21 empty] | 0% | bar: 1 to 21
| Depto.217 | [21 empty] | 0% | bar: 1 to 21
| Depto.218 | [21 empty] | 0% | bar: 1 to 21
| Depto.219 | [21 empty] | 0% | bar: 1 to 21
| Depto.220 | [21 empty] | 0% | bar: 1 to 21
| Depto.221 | [21 empty] | 0% | bar: 1 to 21
GRAFICO DE AVANCE POR PARTIDA
PORCENTAJE POR PARTIDA | bar: 1 to 21
AVANCE GENERAL PISO N° 2 | bar: 1
PISO N°3 A | Depto.301 | [21 empty] | 0% | bar: 1 to 21
| Depto.302 | [21 empty] | 0% | bar: 1 to 21
| Depto.303 | [21 empty] | 0% | bar: 1 to 21
| Depto.304 | [21 empty] | 0% | bar: 1 to 21
| Depto.305 | [21 empty] | 0% | bar: 1 to 21
| Depto.306 | [21 empty] | 0% | bar: 1 to 21
| Depto.307 | [21 empty] | 0% | bar: 1 to 21
| Depto.308 | [21 empty] | 0% | bar: 1 to 21
| Depto.309 | [21 empty] | 0% | bar: 1 to 21
| Depto.310 | [21 empty] | 0% | bar: 1 to 21
| Depto.311 | [21 empty] | 0% | bar: 1 to 21
| Depto.312 | [21 empty] | 0% | bar: 1 to 21
| Depto.313 | [21 empty] | 0% | bar: 1 to 21
| Depto.314 | [21 empty] | 0% | bar: 1 to 21
| Depto.315 | [21 empty] | 0% | bar: 1 to 21
| Depto.316 | [21 empty] | 0% | bar: 1 to 21
| Depto.317 | [21 empty] | 0% | bar: 1 to 21
| Depto.318 | [21 empty] | 0% | bar: 1 to 21
| Depto.319 | [21 empty] | 0% | bar: 1 to 21
| Depto.320 | [21 empty] | 0% | bar: 1 to 21
| Depto.321 | [21 empty] | 0% | bar: 1 to 21
| Depto.322 | [21 empty] | 0% | bar: 1 to 21
| Depto.323 | [21 empty] | 0% | bar: 1 to 21
PISO N°3 B | Depto.301 | [21 empty] | 0% | bar: 1 to 21
| Depto.302 | [21 empty] | 0% | bar: 1 to 21
| Depto.303 | [21 empty] | 0% | bar: 1 to 21
| Depto.304 | [21 empty] | 0% | bar: 1 to 21
| Depto.305 | [21 empty] | 0% | bar: 1 to 21
| Depto.306 | [21 empty] | 0% | bar: 1 to 21
| Depto.307 | [21 empty] | 0% | bar: 1 to 21
| Depto.308 | [21 empty] | 0% | bar: 1 to 21
| Depto.309 | [21 empty] | 0% | bar: 1 to 21
| Depto.310 | [21 empty] | 0% | bar: 1 to 21
| Depto.311 | [21 empty] | 0% | bar: 1 to 21
| Depto.312 | [21 empty] | 0% | bar: 1 to 21
| Depto.313 | [21 empty] | 0% | bar: 1 to 21
| Depto.314 | [21 empty] | 0% | bar: 1 to 21
| Depto.315 | [21 empty] | 0% | bar: 1 to 21
| Depto.316 | [21 empty] | 0% | bar: 1 to 21
| Depto.317 | [21 empty] | 0% | bar: 1 to 21
| Depto.318 | [21 empty] | 0% | bar: 1 to 21
| Depto.319 | [21 empty] | 0% | bar: 1 to 21
| Depto.320 | [21 empty] | 0% | bar: 1 to 21
| Depto.321 | [21 empty] | 0% | bar: 1 to 21
GRAFICO DE AVANCE POR PARTIDA
PORCENTAJE POR PARTIDA | bar: 1 to 21
AVANCE GENERAL PISO N° 3 | bar: 1
PISO N°4 A | Depto.401 | [21 empty] | 0% | bar: 1 to 21
| Depto.402 | [21 empty] | 0% | bar: 1 to 21
| Depto.403 | [21 empty] | 0% | bar: 1 to 21
| Depto.404 | [21 empty] | 0% | bar: 1 to 21
| Depto.405 | [21 empty] | 0% | bar: 1 to 21
| Depto.406 | [21 empty] | 0% | bar: 1 to 21
| Depto.407 | [21 empty] | 0% | bar: 1 to 21
| Depto.408 | [21 empty] | 0% | bar: 1 to 21
| Depto.409 | [21 empty] | 0% | bar: 1 to 21
| Depto.410 | [21 empty] | 0% | bar: 1 to 21
| Depto.411 | [21 empty] | 0% | bar: 1 to 21
| Depto.412 | [21 empty] | 0% | bar: 1 to 21
| Depto.413 | [21 empty] | 0% | bar: 1 to 21
| Depto.414 | [21 empty] | 0% | bar: 1 to 21
| Depto.415 | [21 empty] | 0% | bar: 1 to 21
| Depto.416 | [21 empty] | 0% | bar: 1 to 21
| Depto.417 | [21 empty] | 0% | bar: 1 to 21
| Depto.418 | [21 empty] | 0% | bar: 1 to 21
| Depto.419 | [21 empty] | 0% | bar: 1 to 21
| Depto.420 | [21 empty] | 0% | bar: 1 to 21
| Depto.421 | [21 empty] | 0% | bar: 1 to 21
| Depto.422 | [21 empty] | 0% | bar: 1 to 21
| Depto.423 | [21 empty] | 0% | bar: 1 to 21
PISO N°4 B | Depto.401 | [21 empty] | 0% | bar: 1 to 21
| Depto.402 | [21 empty] | 0% | bar: 1 to 21
| Depto.403 | [21 empty] | 0% | bar: 1 to 21
| Depto.404 | [21 empty] | 0% | bar: 1 to 21
| Depto.405 | [21 empty] | 0% | bar: 1 to 21
| Depto.406 | [21 empty] | 0% | bar: 1 to 21
| Depto.407 | [21 empty] | 0% | bar: 1 to 21
| Depto.408 | [21 empty] | 0% | bar: 1 to 21
| Depto.409 | [21 empty] | 0% | bar: 1 to 21
| Depto.410 | [21 empty] | 0% | bar: 1 to 21
| Depto.411 | [21 empty] | 0% | bar: 1 to 21
| Depto.412 | [21 empty] | 0% | bar: 1 to 21
| Depto.413 | [21 empty] | 0% | bar: 1 to 21
| Depto.414 | [21 empty] | 0% | bar: 1 to 21
| Depto.415 | [21 empty] | 0% | bar: 1 to 21
| Depto.416 | [21 empty] | 0% | bar: 1 to 21
| Depto.417 | [21 empty] | 0% | bar: 1 to 21
| Depto.418 | [21 empty] | 0% | bar: 1 to 21
| Depto.419 | [21 empty] | 0% | bar: 1 to 21
| Depto.420 | [21 empty] | 0% | bar: 1 to 21
| Depto.421 | [21 empty] | 0% | bar: 1 to 21
GRAFICO DE AVANCE POR PARTIDA
PORCENTAJE POR PARTIDA | bar: 1 to 21
AVANCE GENERAL PISO N° 4 | bar: 1
PISO N°5 A | Depto.501 | [21 empty] | 0% | bar: 1 to 21
| Depto.502 | [21 empty] | 0% | bar: 1 to 21
| Depto.503 | [21 empty] | 0% | bar: 1 to 21
| Depto.504 | [21 empty] | 0% | bar: 1 to 21
| Depto.505 | [21 empty] | 0% | bar: 1 to 21
| Depto.506 | [21 empty] | 0% | bar: 1 to 21
| Depto.507 | [21 empty] | 0% | bar: 1 to 21
| Depto.508 | [21 empty] | 0% | bar: 1 to 21
| Depto.509 | [21 empty] | 0% | bar: 1 to 21
| Depto.510 | [21 empty] | 0% | bar: 1 to 21
| Depto.511 | [21 empty] | 0% | bar: 1 to 21
| Depto.512 | [21 empty] | 0% | bar: 1 to 21
| Depto.513 | [21 empty] | 0% | bar: 1 to 21
| Depto.514 | [21 empty] | 0% | bar: 1 to 21
| Depto.515 | [21 empty] | 0% | bar: 1 to 21
| Depto.516 | [21 empty] | 0% | bar: 1 to 21
| Depto.517 | [21 empty] | 0% | bar: 1 to 21
| Depto.518 | [21 empty] | 0% | bar: 1 to 21
| Depto.519 | [21 empty] | 0% | bar: 1 to 21
| Depto.520 | [21 empty] | 0% | bar: 1 to 21
| Depto.521 | [21 empty] | 0% | bar: 1 to 21
| Depto.522 | [21 empty] | 0% | bar: 1 to 21
| Depto.523 | [21 empty] | 0% | bar: 1 to 21
PISO N°5 B | Depto.501 | [21 empty] | 0% | bar: 1 to 21
| Depto.502 | [21 empty] | 0% | bar: 1 to 21
| Depto.503 | [21 empty] | 0% | bar: 1 to 21
| Depto.504 | [21 empty] | 0% | bar: 1 to 21
| Depto.505 | [21 empty] | 0% | bar: 1 to 21
| Depto.506 | [21 empty] | 0% | bar: 1 to 21
| Depto.507 | [21 empty] | 0% | bar: 1 to 21
| Depto.508 | [21 empty] | 0% | bar: 1 to 21
| Depto.509 | [21 empty] | 0% | bar: 1 to 21
| Depto.510 | [21 empty] | 0% | bar: 1 to 21
| Depto.511 | [21 empty] | 0% | bar: 1 to 21
| Depto.512 | [21 empty] | 0% | bar: 1 to 21
| Depto.513 | [21 empty] | 0% | bar: 1 to 21
| Depto.514 | [21 empty] | 0% | bar: 1 to 21
| Depto.515 | [21 empty] | 0% | bar: 1 to 21
| Depto.516 | [21 empty] | 0% | bar: 1 to 21
| Depto.517 | [21 empty] | 0% | bar: 1 to 21
| Depto.518 | [21 empty] | 0% | bar: 1 to 21
| Depto.519 | [21 empty] | 0% | bar: 1 to 21
| Depto.520 | [21 empty] | 0% | bar: 1 to 21
| Depto.521 | [21 empty] | 0% | bar: 1 to 21
GRAFICO DE AVANCE POR PARTIDA
PORCENTAJE POR PARTIDA | bar: 1 to 21
AVANCE GENERAL PISO N° 5 | bar: 1
PISO N°6 A | Depto.601 | [21 empty] | 0% | bar: 1 to 21
| Depto.602 | [21 empty] | 0% | bar: 1 to 21
| Depto.603 | [21 empty] | 0% | bar: 1 to 21
| Depto.604 | [21 empty] | 0% | bar: 1 to 21
| Depto.605 | [21 empty] | 0% | bar: 1 to 21
| Depto.606 | [21 empty] | 0% | bar: 1 to 21
| Depto.607 | [21 empty] | 0% | bar: 1 to 21
| Depto.608 | [21 empty] | 0% | bar: 1 to 21
| Depto.609 | [21 empty] | 0% | bar: 1 to 21
| Depto.610 | [21 empty] | 0% | bar: 1 to 21
| Depto.611 | [21 empty] | 0% | bar: 1 to 21
| Depto.612 | [21 empty] | 0% | bar: 1 to 21
| Depto.613 | [21 empty] | 0% | bar: 1 to 21
| Depto.614 | [21 empty] | 0% | bar: 1 to 21
| Depto.615 | [21 empty] | 0% | bar: 1 to 21
| Depto.616 | [21 empty] | 0% | bar: 1 to 21
| Depto.617 | [21 empty] | 0% | bar: 1 to 21
| Depto.618 | [21 empty] | 0% | bar: 1 to 21
| Depto.619 | [21 empty] | 0% | bar: 1 to 21
| Depto.620 | [21 empty] | 0% | bar: 1 to 21
| Depto.621 | [21 empty] | 0% | bar: 1 to 21
| Depto.622 | [21 empty] | 0% | bar: 1 to 21
| Depto.623 | [21 empty] | 0% | bar: 1 to 21
PISO N°6 B | Depto.601 | [21 empty] | 0% | bar: 1 to 21
| Depto.602 | [21 empty] | 0% | bar: 1 to 21
| Depto.603 | [21 empty] | 0% | bar: 1 to 21
| Depto.604 | [21 empty] | 0% | bar: 1 to 21
| Depto.605 | [21 empty] | 0% | bar: 1 to 21
| Depto.606 | [21 empty] | 0% | bar: 1 to 21
| Depto.607 | [21 empty] | 0% | bar: 1 to 21
| Depto.608 | [21 empty] | 0% | bar: 1 to 21
| Depto.609 | [21 empty] | 0% | bar: 1 to 21
| Depto.610 | [21 empty] | 0% | bar: 1 to 21
| Depto.611 | [21 empty] | 0% | bar: 1 to 21
| Depto.612 | [21 empty] | 0% | bar: 1 to 21
| Depto.613 | [21 empty] | 0% | bar: 1 to 21
| Depto.614 | [21 empty] | 0% | bar: 1 to 21
| Depto.615 | [21 empty] | 0% | bar: 1 to 21
| Depto.616 | [21 empty] | 0% | bar: 1 to 21
| Depto.617 | [21 empty] | 0% | bar: 1 to 21
| Depto.618 | [21 empty] | 0% | bar: 1 to 21
| Depto.619 | [21 empty] | 0% | bar: 1 to 21
| Depto.620 | [21 empty] | 0% | bar: 1 to 21
| Depto.621 | [21 empty] | 0% | bar: 1 to 21
GRAFICO DE AVANCE POR PARTIDA
PORCENTAJE POR PARTIDA | bar: 1 to 21
AVANCE GENERAL PISO N° 6 | bar: 1
PISO N°7 A | Depto.701 | [21 empty] | 0% | bar: 1 to 21
| Depto.702 | [21 empty] | 0% | bar: 1 to 21
| Depto703 | [21 empty] | 0% | bar: 1 to 21
| Depto.704 | [21 empty] | 0% | bar: 1 to 21
| Depto.705 | [21 empty] | 0% | bar: 1 to 21
| Depto.706 | [21 empty] | 0% | bar: 1 to 21
| Depto.707 | [21 empty] | 0% | bar: 1 to 21
| Depto.708 | [21 empty] | 0% | bar: 1 to 21
| Depto.709 | [21 empty] | 0% | bar: 1 to 21
| Depto.710 | [21 empty] | 0% | bar: 1 to 21
| Depto.711 | [21 empty] | 0% | bar: 1 to 21
| Depto.712 | [21 empty] | 0% | bar: 1 to 21
| Depto.713 | [21 empty] | 0% | bar: 1 to 21
| Depto.714 | [21 empty] | 0% | bar: 1 to 21
| Depto.715 | [21 empty] | 0% | bar: 1 to 21
| Depto.716 | [21 empty] | 0% | bar: 1 to 21
| Depto.717 | [21 empty] | 0% | bar: 1 to 21
| Depto.718 | [21 empty] | 0% | bar: 1 to 21
| Depto.719 | [21 empty] | 0% | bar: 1 to 21
| Depto.720 | [21 empty] | 0% | bar: 1 to 21
| Depto.721 | [21 empty] | 0% | bar: 1 to 21
| Depto.722 | [21 empty] | 0% | bar: 1 to 21
| Depto.723 | [21 empty] | 0% | bar: 1 to 21
PISO N°7 B | Depto.701 | [21 empty] | 0% | bar: 1 to 21
| Depto.702 | [21 empty] | 0% | bar: 1 to 21
| Depto.703 | [21 empty] | 0% | bar: 1 to 21
| Depto.704 | [21 empty] | 0% | bar: 1 to 21
| Depto.705 | [21 empty] | 0% | bar: 1 to 21
| Depto.706 | [21 empty] | 0% | bar: 1 to 21
| Depto.707 | [21 empty] | 0% | bar: 1 to 21
| Depto.708 | [21 empty] | 0% | bar: 1 to 21
| Depto.709 | [21 empty] | 0% | bar: 1 to 21
| Depto.710 | [21 empty] | 0% | bar: 1 to 21
| Depto.711 | [21 empty] | 0% | bar: 1 to 21
| Depto.712 | [21 empty] | 0% | bar: 1 to 21
| Depto.713 | [21 empty] | 0% | bar: 1 to 21
| Depto.714 | [21 empty] | 0% | bar: 1 to 21
| Depto.715 | [21 empty] | 0% | bar: 1 to 21
| Depto.716 | [21 empty] | 0% | bar: 1 to 21
| Depto.717 | [21 empty] | 0% | bar: 1 to 21
| Depto.718 | [21 empty] | 0% | bar: 1 to 21
| Depto.719 | [21 empty] | 0% | bar: 1 to 21
| Depto.720 | [21 empty] | 0% | bar: 1 to 21
| Depto.721 | [21 empty] | 0% | bar: 1 to 21
GRAFICO DE AVANCE POR PARTIDA
PORCENTAJE POR PARTIDA | bar: 1 to 21
AVANCE GENERAL PISO N° 7 | bar: 1
PISO N°8 A | Depto.801 | [21 empty] | 0% | bar: 1 to 21
| Depto.802 | [21 empty] | 0% | bar: 1 to 21
| Depto803 | [21 empty] | 0% | bar: 1 to 21
| Depto.804 | [21 empty] | 0% | bar: 1 to 21
| Depto.805 | [21 empty] | 0% | bar: 1 to 21
| Depto.806 | [21 empty] | 0% | bar: 1 to 21
| Depto.807 | [21 empty] | 0% | bar: 1 to 21
| Depto.808 | [21 empty] | 0% | bar: 1 to 21
| Depto.809 | [21 empty] | 0% | bar: 1 to 21
| Depto.810 | [21 empty] | 0% | bar: 1 to 21
| Depto.811 | [21 empty] | 0% | bar: 1 to 21
| Depto.812 | [21 empty] | 0% | bar: 1 to 21
| Depto.813 | [21 empty] | 0% | bar: 1 to 21
| Depto.814 | [21 empty] | 0% | bar: 1 to 21
| Depto.815 | [21 empty] | 0% | bar: 1 to 21
| Depto.816 | [21 empty] | 0% | bar: 1 to 21
| Depto.817 | [21 empty] | 0% | bar: 1 to 21
| Depto.818 | [21 empty] | 0% | bar: 1 to 21
| Depto.819 | [21 empty] | 0% | bar: 1 to 21
| Depto.820 | [21 empty] | 0% | bar: 1 to 21
| Depto.821 | [21 empty] | 0% | bar: 1 to 21
| Depto.822 | [21 empty] | 0% | bar: 1 to 21
| Depto.823 | [21 empty] | 0% | bar: 1 to 21
PISO N°8 B | Depto.801 | [21 empty] | 0% | bar: 1 to 21
| Depto.802 | [21 empty] | 0% | bar: 1 to 21
| Depto.803 | [21 empty] | 0% | bar: 1 to 21
| Depto.804 | [21 empty] | 0% | bar: 1 to 21
| Depto.805 | [21 empty] | 0% | bar: 1 to 21
| Depto.806 | [21 empty] | 0% | bar: 1 to 21
| Depto.807 | [21 empty] | 0% | bar: 1 to 21
| Depto.808 | [21 empty] | 0% | bar: 1 to 21
| Depto.809 | [21 empty] | 0% | bar: 1 to 21
| Depto.810 | [21 empty] | 0% | bar: 1 to 21
| Depto.811 | [21 empty] | 0% | bar: 1 to 21
| Depto.812 | [21 empty] | 0% | bar: 1 to 21
| Depto.813 | [21 empty] | 0% | bar: 1 to 21
| Depto.814 | [21 empty] | 0% | bar: 1 to 21
| Depto.815 | [21 empty] | 0% | bar: 1 to 21
| Depto.816 | [21 empty] | 0% | bar: 1 to 21
| Depto.817 | [21 empty] | 0% | bar: 1 to 21
| Depto.818 | [21 empty] | 0% | bar: 1 to 21
| Depto.819 | [21 empty] | 0% | bar: 1 to 21
| Depto.820 | [21 empty] | 0% | bar: 1 to 21
| Depto.821 | [21 empty] | 0% | bar: 1 to 21
GRAFICO DE AVANCE POR PARTIDA
PORCENTAJE POR PARTIDA | bar: 1 to 21
AVANCE GENERAL PISO N° 8 | bar: 1
PISO N°9 A | Depto.901 | [21 empty] | 0% | bar: 1 to 21
| Depto.902 | [21 empty] | 0% | bar: 1 to 21
| Depto.903 | [21 empty] | 0% | bar: 1 to 21
| Depto.904 | [21 empty] | 0% | bar: 1 to 21
| Depto.905 | [21 empty] | 0% | bar: 1 to 21
| Depto.906 | [21 empty] | 0% | bar: 1 to 21
| Depto.907 | [21 empty] | 0% | bar: 1 to 21
| Depto.908 | [21 empty] | 0% | bar: 1 to 21
| Depto.909 | [21 empty] | 0% | bar: 1 to 21
| Depto.910 | [21 empty] | 0% | bar: 1 to 21
| Depto.911 | [21 empty] | 0% | bar: 1 to 21
| Depto.912 | [21 empty] | 0% | bar: 1 to 21
| Depto.913 | [21 empty] | 0% | bar: 1 to 21
| Depto.914 | [21 empty] | 0% | bar: 1 to 21
| Depto.915 | [21 empty] | 0% | bar: 1 to 21
| Depto.916 | [21 empty] | 0% | bar: 1 to 21
| Depto.917 | [21 empty] | 0% | bar: 1 to 21
| Depto.918 | [21 empty] | 0% | bar: 1 to 21
| Depto.919 | [21 empty] | 0% | bar: 1 to 21
| Depto.923 | [21 empty] | 0% | bar: 1 to 21
PISO N°9 B | Depto.901 | [21 empty] | 0% | bar: 1 to 21
| Depto.902 | [21 empty] | 0% | bar: 1 to 21
| Depto.903 | [21 empty] | 0% | bar: 1 to 21
| Depto.904 | [21 empty] | 0% | bar: 1 to 21
| Depto.905 | [21 empty] | 0% | bar: 1 to 21
| Depto.906 | [21 empty] | 0% | bar: 1 to 21
| Depto.907 | [21 empty] | 0% | bar: 1 to 21
| Depto.908 | [21 empty] | 0% | bar: 1 to 21
| Depto.909 | [21 empty] | 0% | bar: 1 to 21
| Depto.910 | [21 empty] | 0% | bar: 1 to 21
| Depto.911 | [21 empty] | 0% | bar: 1 to 21
| Depto.912 | [21 empty] | 0% | bar: 1 to 21
| Depto.913 | [21 empty] | 0% | bar: 1 to 21
| Depto.914 | [21 empty] | 0% | bar: 1 to 21
| Depto.915 | [21 empty] | 0% | bar: 1 to 21
| Depto.916 | [21 empty] | 0% | bar: 1 to 21
| Depto.917 | [21 empty] | 0% | bar: 1 to 21
| Depto.918 | [21 empty] | 0% | bar: 1 to 21
| Depto.919 | [21 empty] | 0% | bar: 1 to 21
| Depto.920 | [21 empty] | 0% | bar: 1 to 21
| Depto.921 | [21 empty] | 0% | bar: 1 to 21
GRAFICO DE AVANCE POR PARTIDA
PORCENTAJE POR PARTIDA | bar: 1 to 21
AVANCE GENERAL PISO N° 9 | bar: 1
| PISO | Instalación piernas de closet | Instalación Cornisas | Cuadratura de cajas. | Remate yeso y cornisas | Puertas interiores | Puertas de acceso y pasillo | Cerradura Puertas | Cableado Eléctrico y CCDD | Canterias | Empaste Muro Cielo | Instalacion Guardapolvo | Instalación de Baranda de Crital | Pintura Cielo Terrazas | Grano Muros Terrazas | Losalin Cielo Departamento | Pintura Cielo Baños | Instalacion de Muebles baño | Instalacion Muebles de cocina (Base) | Instalacion Muebles de cocina (Aereo) | Instalación cubiertas cocina | Muebles Interior closet | Avance Real x Piso
| Piso n°1 | 0% | 8.333% | 33.33% | 8.333% | 8.333% | 0% | 8.333% | 8.333% | 0% | 8.333% | 8.333% | 8.333% | 8.333% | 8.333% | 8.333% | 8.333% | 8.333% | 8.333% | 8.333% | 8.333% | 0% | 7.937%
| Piso n°2 | [21 empty] | 0% | bar: 1 to 21
| Piso n°3 | [21 empty] | 0% | bar: 1 to 21
| Piso n°4 | [21 empty] | 0% | bar: 1 to 21
| Piso n°5 | [21 empty] | 0% | bar: 1 to 21
| Piso n°6 | [21 empty] | 0% | bar: 1 to 21
| Piso n°7 | [21 empty] | 0% | bar: 1 to 21
| Piso n°8 | [21 empty] | 0% | bar: 1 to 21
| Piso n°9 | [21 empty] | 0% | bar: 1 to 21
| AVANCE PARTIDA | 0% | 0.9259% | 3.704% | 0.9259% | 0.9259% | 0% | 0.9259% | 0.9259% | 0% | 0.9259% | 0.9259% | 0.9259% | 0.9259% | 0.9259% | 0.9259% | 0.9259% | 0.9259% | 0.9259% | 0.9259% | 0.9259% | 0% | 0.8818%
0.8818%

## FASE 2
Avance General
CONTROL AVANCE FASE 2 SAN FRANCISCO 211
[15 empty] | Cantidad de Deptos. | 359 | 1.318%
|  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
| Deptos. | Huinchas tabiques | Instalación Marco Puerta Acceso | Marcos Puertas Interiores | Impermeabilizacion Baños | Impermeabilizacion Terrazas | Preparación de Pisos | Instalacion de tina/Receptaculo | Protección Tina/receptaculo | Faldon de tina. | Instalación Ventana | Ceramica Pisos | Ceramica Muros | Instalación de Gargolas en Terraza | Frague | Cerámica de Terrazas | Avance Real x Piso
PISO N° 1 | DEPTO 102 | 0% | 0% | 0% | 80% | 0% | 90% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 12.14%
| DEPTO 103 | 0% | 0% | 0% | 80% | 100% | 90% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 26.43%
| DEPTO 104 | 0% | 0% | 0% | 80% | 100% | 90% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 26.43%
| DEPTO 105 | 0% | 0% | 0% | 80% | 0% | 90% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 12.14%
| DEPTO 106 | 0% | 0% | 0% | 80% | 0% | 90% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 12.14%
| DEPTO 107 | 0% | 0% | 0% | 80% | 0% | 90% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 12.14%
| DEPTO 108 | 0% | 0% | 0% | 0% | 0% | 90% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 6.429%
| DEPTO 118 | [15 empty] | 0% | bar: 1 to 15
| DEPTO 119 | [15 empty] | 0% | bar: 1 to 15
| DEPTO 120 | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 0% | 0% | 0% | 0% | 100% | 78.57%
| DEPTO 121 | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 0% | 100% | 0% | 92.86%
| LOCAL 1 | [15 empty] | 0% | bar: 1 to 15
| LOCAL 2 | [15 empty] | 0% | bar: 1 to 15
| LOCAL 3 | [15 empty] | 0% | bar: 1 to 15
| LOCAL 4 | [15 empty] | 0% | bar: 1 to 15
| LOCAL 5 | [15 empty] | 0% | bar: 1 to 15
| LOCAL 6 | [15 empty] | 0% | bar: 1 to 15
| LOCAL 7 | 50% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 10.71%
| LOCAL 8 | 50% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 10.71%
| LOCAL 9 | 60% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 4.286%
| COWORK | [15 empty] | 0% | bar: 1 to 15
| GIMNASIO | [15 empty] | 0% | bar: 1 to 15
| SALON GOURMET 1 | [15 empty] | 0% | bar: 1 to 15
| SALON GOURMET 2 | [15 empty] | 0% | bar: 1 to 15
GRAFICO DE AVANCE POR PARTIDA
PORCENTAJE POR PARTIDA |  | 15% | 8.333% | 8.333% | 36.67% | 16.67% | 34.58% | 8.333% | 8.333% | 8.333% | 8.333% | 4.167% | 4.167% | 0% | 4.167% | 12.5%
AVANCE GENERAL PISO N° 1 |  | 1: 11.86%
PISO N° 2 A | Depto 202 | [15 empty] | 0% | bar: 1 to 15
| Depto.203 | [15 empty] | 0% | bar: 1 to 15
| Depto.204 | [15 empty] | 0% | bar: 1 to 15
| Depto.205 | [15 empty] | 0% | bar: 1 to 15
| Depto.206 | [15 empty] | 0% | bar: 1 to 15
| Depto.207 | [15 empty] | 0% | bar: 1 to 15
| Depto.208 | [15 empty] | 0% | bar: 1 to 15
| Depto.209 | [15 empty] | 0% | bar: 1 to 15
| Depto.210 | [15 empty] | 0% | bar: 1 to 15
| Depto.211 | [15 empty] | 0% | bar: 1 to 15
| Depto.212 | [15 empty] | 0% | bar: 1 to 15
| Depto.213 | [15 empty] | 0% | bar: 1 to 15
| Depto.214 | [15 empty] | 0% | bar: 1 to 15
| Depto.215 | [15 empty] | 0% | bar: 1 to 15
| Depto.216 | [15 empty] | 0% | bar: 1 to 15
| Depto.217 | [15 empty] | 0% | bar: 1 to 15
| Depto.218 | [15 empty] | 0% | bar: 1 to 15
| Depto.219 | [15 empty] | 0% | bar: 1 to 15
| Depto.220 | [15 empty] | 0% | bar: 1 to 15
| Depto.221 | [15 empty] | 0% | bar: 1 to 15
| Depto.222 | [15 empty] | 0% | bar: 1 to 15
| Depto.223 | [15 empty] | 0% | bar: 1 to 15
PISO N° 2 B | Depto.201 | [15 empty] | 0% | bar: 1 to 15
| Depto.202 | [15 empty] | 0% | bar: 1 to 15
| Depto.203 | [15 empty] | 0% | bar: 1 to 15
| Depto.204 | [15 empty] | 0% | bar: 1 to 15
| Depto.205 | [15 empty] | 0% | bar: 1 to 15
| Depto.206 | [15 empty] | 0% | bar: 1 to 15
| Depto.207 | [15 empty] | 0% | bar: 1 to 15
| Depto.208 | [15 empty] | 0% | bar: 1 to 15
| Depto.209 | [15 empty] | 0% | bar: 1 to 15
| Depto.210 | [15 empty] | 0% | bar: 1 to 15
| Depto.211 | [15 empty] | 0% | bar: 1 to 15
| Depto.212 | [15 empty] | 0% | bar: 1 to 15
| Depto.213 | [15 empty] | 0% | bar: 1 to 15
| Depto.214 | [15 empty] | 0% | bar: 1 to 15
| Depto.215 | [15 empty] | 0% | bar: 1 to 15
| Depto.216 | [15 empty] | 0% | bar: 1 to 15
| Depto.217 | [15 empty] | 0% | bar: 1 to 15
| Depto.218 | [15 empty] | 0% | bar: 1 to 15
| Depto.219 | [15 empty] | 0% | bar: 1 to 15
| Depto.220 | [15 empty] | 0% | bar: 1 to 15
| Depto.221 | [15 empty] | 0% | bar: 1 to 15
GRAFICO DE AVANCE POR PARTIDA
PORCENTAJE POR PARTIDA | bar: 1 to 15
AVANCE GENERAL PISO N° 2 | bar: 1
PISO N°3 A | Depto.301 | [15 empty] | 0% | bar: 1 to 15
| Depto.302 | [15 empty] | 0% | bar: 1 to 15
| Depto.303 | [15 empty] | 0% | bar: 1 to 15
| Depto.304 | [15 empty] | 0% | bar: 1 to 15
| Depto.305 | [15 empty] | 0% | bar: 1 to 15
| Depto.306 | [15 empty] | 0% | bar: 1 to 15
| Depto.307 | [15 empty] | 0% | bar: 1 to 15
| Depto.308 | [15 empty] | 0% | bar: 1 to 15
| Depto.309 | [15 empty] | 0% | bar: 1 to 15
| Depto.310 | [15 empty] | 0% | bar: 1 to 15
| Depto.311 | [15 empty] | 0% | bar: 1 to 15
| Depto.312 | [15 empty] | 0% | bar: 1 to 15
| Depto.313 | [15 empty] | 0% | bar: 1 to 15
| Depto.314 | [15 empty] | 0% | bar: 1 to 15
| Depto.315 | [15 empty] | 0% | bar: 1 to 15
| Depto.316 | [15 empty] | 0% | bar: 1 to 15
| Depto.317 | [15 empty] | 0% | bar: 1 to 15
| Depto.318 | [15 empty] | 0% | bar: 1 to 15
| Depto.319 | [15 empty] | 0% | bar: 1 to 15
| Depto.320 | [15 empty] | 0% | bar: 1 to 15
| Depto.321 | [15 empty] | 0% | bar: 1 to 15
| Depto.322 | [15 empty] | 0% | bar: 1 to 15
| Depto.323 | [15 empty] | 0% | bar: 1 to 15
PISO N°3 B | Depto.301 | [15 empty] | 0% | bar: 1 to 15
| Depto.302 | [15 empty] | 0% | bar: 1 to 15
| Depto.303 | [15 empty] | 0% | bar: 1 to 15
| Depto.304 | [15 empty] | 0% | bar: 1 to 15
| Depto.305 | [15 empty] | 0% | bar: 1 to 15
| Depto.306 | [15 empty] | 0% | bar: 1 to 15
| Depto.307 | [15 empty] | 0% | bar: 1 to 15
| Depto.308 | [15 empty] | 0% | bar: 1 to 15
| Depto.309 | [15 empty] | 0% | bar: 1 to 15
| Depto.310 | [15 empty] | 0% | bar: 1 to 15
| Depto.311 | [15 empty] | 0% | bar: 1 to 15
| Depto.312 | [15 empty] | 0% | bar: 1 to 15
| Depto.313 | [15 empty] | 0% | bar: 1 to 15
| Depto.314 | [15 empty] | 0% | bar: 1 to 15
| Depto.315 | [15 empty] | 0% | bar: 1 to 15
| Depto.316 | [15 empty] | 0% | bar: 1 to 15
| Depto.317 | [15 empty] | 0% | bar: 1 to 15
| Depto.318 | [15 empty] | 0% | bar: 1 to 15
| Depto.319 | [15 empty] | 0% | bar: 1 to 15
| Depto.320 | [15 empty] | 0% | bar: 1 to 15
| Depto.321 | [15 empty] | 0% | bar: 1 to 15
GRAFICO DE AVANCE POR PARTIDA
PORCENTAJE POR PARTIDA | bar: 1 to 15
AVANCE GENERAL PISO N° 3 | bar: 1
PISO N°4 A | Depto.401 | [15 empty] | 0% | bar: 1 to 15
Depto.402 | bar: 1 to 15
Depto.403 | bar: 1 to 15
Depto.404 | bar: 1 to 15
Depto.405 | bar: 1 to 15
Depto.406 | bar: 1 to 15
Depto.407 | bar: 1 to 15
Depto.408 | bar: 1 to 15
Depto.409 | bar: 1 to 15
Depto.410 | bar: 1 to 15
Depto.411 | bar: 1 to 15
Depto.412 | bar: 1 to 15
Depto.413 | bar: 1 to 15
Depto.414 | bar: 1 to 15
Depto.415 | bar: 1 to 15
Depto.416 | bar: 1 to 15
Depto.417 | bar: 1 to 15
Depto.418 | bar: 1 to 15
Depto.419 | bar: 1 to 15
Depto.420 | bar: 1 to 15
Depto.421 | bar: 1 to 15
Depto.422 | bar: 1 to 15
Depto.423 | bar: 1 to 15
PISO N°4 B | Depto.401 | bar: 1 to 15
Depto.402 | bar: 1 to 15
Depto.403 | bar: 1 to 15
Depto.404 | bar: 1 to 15
Depto.405 | bar: 1 to 15
Depto.406 | bar: 1 to 15
Depto.407 | bar: 1 to 15
Depto.408 | bar: 1 to 15
| Depto.409 | [15 empty] | 0% | bar: 1 to 15
| Depto.410 | [15 empty] | 0% | bar: 1 to 15
| Depto.411 | [15 empty] | 0% | bar: 1 to 15
| Depto.412 | [15 empty] | 0% | bar: 1 to 15
| Depto.413 | [15 empty] | 0% | bar: 1 to 15
| Depto.414 | [15 empty] | 0% | bar: 1 to 15
| Depto.415 | [15 empty] | 0% | bar: 1 to 15
| Depto.416 | [15 empty] | 0% | bar: 1 to 15
| Depto.417 | [15 empty] | 0% | bar: 1 to 15
| Depto.418 | [15 empty] | 0% | bar: 1 to 15
| Depto.419 | [15 empty] | 0% | bar: 1 to 15
| Depto.420 | [15 empty] | 0% | bar: 1 to 15
| Depto.421 | [15 empty] | 0% | bar: 1 to 15
GRAFICO DE AVANCE POR PARTIDA
PORCENTAJE POR PARTIDA | bar: 1 to 15
AVANCE GENERAL PISO N° 4 | bar: 1
PISO N°5 A | Depto.501 | [15 empty] | 0% | bar: 1 to 15
Depto.502 | bar: 1 to 15
| Depto.503 | [15 empty] | 0% | bar: 1 to 15
| Depto.504 | [15 empty] | 0% | bar: 1 to 15
| Depto.505 | [15 empty] | 0% | bar: 1 to 15
| Depto.506 | [15 empty] | 0% | bar: 1 to 15
| Depto.507 | [15 empty] | 0% | bar: 1 to 15
| Depto.508 | [15 empty] | 0% | bar: 1 to 15
| Depto.509 | [15 empty] | 0% | bar: 1 to 15
| Depto.510 | [15 empty] | 0% | bar: 1 to 15
| Depto.511 | [15 empty] | 0% | bar: 1 to 15
| Depto.512 | [15 empty] | 0% | bar: 1 to 15
| Depto.513 | [15 empty] | 0% | bar: 1 to 15
| Depto.514 | [15 empty] | 0% | bar: 1 to 15
| Depto.515 | [15 empty] | 0% | bar: 1 to 15
| Depto.516 | [15 empty] | 0% | bar: 1 to 15
| Depto.517 | [15 empty] | 0% | bar: 1 to 15
| Depto.518 | [15 empty] | 0% | bar: 1 to 15
| Depto.519 | [15 empty] | 0% | bar: 1 to 15
| Depto.520 | [15 empty] | 0% | bar: 1 to 15
| Depto.521 | [15 empty] | 0% | bar: 1 to 15
| Depto.522 | [15 empty] | 0% | bar: 1 to 15
| Depto.523 | [15 empty] | 0% | bar: 1 to 15
PISO N°5 B | Depto.501 | [15 empty] | 0% | bar: 1 to 15
| Depto.502 | [15 empty] | 0% | bar: 1 to 15
| Depto.503 | [15 empty] | 0% | bar: 1 to 15
| Depto.504 | [15 empty] | 0% | bar: 1 to 15
| Depto.505 | [15 empty] | 0% | bar: 1 to 15
| Depto.506 | [15 empty] | 0% | bar: 1 to 15
| Depto.507 | [15 empty] | 0% | bar: 1 to 15
| Depto.508 | [15 empty] | 0% | bar: 1 to 15
| Depto.509 | [15 empty] | 0% | bar: 1 to 15
| Depto.510 | [15 empty] | 0% | bar: 1 to 15
| Depto.511 | [15 empty] | 0% | bar: 1 to 15
| Depto.512 | [15 empty] | 0% | bar: 1 to 15
| Depto.513 | [15 empty] | 0% | bar: 1 to 15
| Depto.514 | [15 empty] | 0% | bar: 1 to 15
| Depto.515 | [15 empty] | 0% | bar: 1 to 15
| Depto.516 | [15 empty] | 0% | bar: 1 to 15
| Depto.517 | [15 empty] | 0% | bar: 1 to 15
| Depto.518 | [15 empty] | 0% | bar: 1 to 15
| Depto.519 | [15 empty] | 0% | bar: 1 to 15
| Depto.520 | [15 empty] | 0% | bar: 1 to 15
| Depto.521 | [15 empty] | 0% | bar: 1 to 15
GRAFICO DE AVANCE POR PARTIDA
PORCENTAJE POR PARTIDA | bar: 1 to 15
AVANCE GENERAL PISO N° 5 | bar: 1
PISO N°6 A | Depto.601 | [15 empty] | 0% | bar: 1 to 15
| Depto.602 | [15 empty] | 0% | bar: 1 to 15
| Depto.603 | [15 empty] | 0% | bar: 1 to 15
| Depto.604 | [15 empty] | 0% | bar: 1 to 15
| Depto.605 | [15 empty] | 0% | bar: 1 to 15
| Depto.606 | [15 empty] | 0% | bar: 1 to 15
| Depto.607 | [15 empty] | 0% | bar: 1 to 15
| Depto.608 | [15 empty] | 0% | bar: 1 to 15
| Depto.609 | [15 empty] | 0% | bar: 1 to 15
| Depto.610 | [15 empty] | 0% | bar: 1 to 15
| Depto.611 | [15 empty] | 0% | bar: 1 to 15
| Depto.612 | [15 empty] | 0% | bar: 1 to 15
| Depto.613 | [15 empty] | 0% | bar: 1 to 15
| Depto.614 | [15 empty] | 0% | bar: 1 to 15
| Depto.615 | [15 empty] | 0% | bar: 1 to 15
| Depto.616 | [15 empty] | 0% | bar: 1 to 15
| Depto.617 | [15 empty] | 0% | bar: 1 to 15
| Depto.618 | [15 empty] | 0% | bar: 1 to 15
| Depto.619 | [15 empty] | 0% | bar: 1 to 15
| Depto.620 | [15 empty] | 0% | bar: 1 to 15
| Depto.621 | [15 empty] | 0% | bar: 1 to 15
| Depto.622 | [15 empty] | 0% | bar: 1 to 15
| Depto.623 | [15 empty] | 0% | bar: 1 to 15
PISO N°6 B | Depto.601 | [15 empty] | 0% | bar: 1 to 15
| Depto.602 | [15 empty] | 0% | bar: 1 to 15
| Depto.603 | [15 empty] | 0% | bar: 1 to 15
| Depto.604 | [15 empty] | 0% | bar: 1 to 15
| Depto.605 | [15 empty] | 0% | bar: 1 to 15
| Depto.606 | [15 empty] | 0% | bar: 1 to 15
| Depto.607 | [15 empty] | 0% | bar: 1 to 15
| Depto.608 | [15 empty] | 0% | bar: 1 to 15
| Depto.609 | [15 empty] | 0% | bar: 1 to 15
| Depto.610 | [15 empty] | 0% | bar: 1 to 15
| Depto.611 | [15 empty] | 0% | bar: 1 to 15
| Depto.612 | [15 empty] | 0% | bar: 1 to 15
| Depto.613 | [15 empty] | 0% | bar: 1 to 15
| Depto.614 | [15 empty] | 0% | bar: 1 to 15
| Depto.615 | [15 empty] | 0% | bar: 1 to 15
| Depto.616 | [15 empty] | 0% | bar: 1 to 15
| Depto.617 | [15 empty] | 0% | bar: 1 to 15
| Depto.618 | [15 empty] | 0% | bar: 1 to 15
| Depto.619 | [15 empty] | 0% | bar: 1 to 15
| Depto.620 | [15 empty] | 0% | bar: 1 to 15
| Depto.621 | [15 empty] | 0% | bar: 1 to 15
GRAFICO DE AVANCE POR PARTIDA
PORCENTAJE POR PARTIDA | bar: 1 to 15
AVANCE GENERAL PISO N° 6 | bar: 1
PISO N°7 A | Depto.701 | [15 empty] | 0% | bar: 1 to 15
| Depto.702 | [15 empty] | 0% | bar: 1 to 15
| Depto703 | [15 empty] | 0% | bar: 1 to 15
| Depto.704 | [15 empty] | 0% | bar: 1 to 15
| Depto.705 | [15 empty] | 0% | bar: 1 to 15
| Depto.706 | [15 empty] | 0% | bar: 1 to 15
| Depto.707 | [15 empty] | 0% | bar: 1 to 15
| Depto.708 | [15 empty] | 0% | bar: 1 to 15
| Depto.709 | [15 empty] | 0% | bar: 1 to 15
| Depto.710 | [15 empty] | 0% | bar: 1 to 15
| Depto.711 | [15 empty] | 0% | bar: 1 to 15
| Depto.712 | [15 empty] | 0% | bar: 1 to 15
| Depto.713 | [15 empty] | 0% | bar: 1 to 15
| Depto.714 | [15 empty] | 0% | bar: 1 to 15
| Depto.715 | [15 empty] | 0% | bar: 1 to 15
| Depto.716 | [15 empty] | 0% | bar: 1 to 15
| Depto.717 | [15 empty] | 0% | bar: 1 to 15
| Depto.718 | [15 empty] | 0% | bar: 1 to 15
| Depto.719 | [15 empty] | 0% | bar: 1 to 15
| Depto.720 | [15 empty] | 0% | bar: 1 to 15
| Depto.721 | [15 empty] | 0% | bar: 1 to 15
| Depto.722 | [15 empty] | 0% | bar: 1 to 15
| Depto.723 | [15 empty] | 0% | bar: 1 to 15
PISO N°7 B | Depto.701 | [15 empty] | 0% | bar: 1 to 15
| Depto.702 | [15 empty] | 0% | bar: 1 to 15
| Depto.703 | [15 empty] | 0% | bar: 1 to 15
| Depto.704 | [15 empty] | 0% | bar: 1 to 15
| Depto.705 | [15 empty] | 0% | bar: 1 to 15
| Depto.706 | [15 empty] | 0% | bar: 1 to 15
| Depto.707 | [15 empty] | 0% | bar: 1 to 15
| Depto.708 | [15 empty] | 0% | bar: 1 to 15
| Depto.709 | [15 empty] | 0% | bar: 1 to 15
| Depto.710 | [15 empty] | 0% | bar: 1 to 15
| Depto.711 | [15 empty] | 0% | bar: 1 to 15
| Depto.712 | [15 empty] | 0% | bar: 1 to 15
| Depto.713 | [15 empty] | 0% | bar: 1 to 15
| Depto.714 | [15 empty] | 0% | bar: 1 to 15
| Depto.715 | [15 empty] | 0% | bar: 1 to 15
| Depto.716 | [15 empty] | 0% | bar: 1 to 15
| Depto.717 | [15 empty] | 0% | bar: 1 to 15
| Depto.718 | [15 empty] | 0% | bar: 1 to 15
| Depto.719 | [15 empty] | 0% | bar: 1 to 15
| Depto.720 | [15 empty] | 0% | bar: 1 to 15
| Depto.721 | [15 empty] | 0% | bar: 1 to 15
GRAFICO DE AVANCE POR PARTIDA
PORCENTAJE POR PARTIDA | bar: 1 to 15
AVANCE GENERAL PISO N° 7 | bar: 1
PISO N°8 A | Depto.801 | [15 empty] | 0% | bar: 1 to 15
| Depto.802 | [15 empty] | 0% | bar: 1 to 15
| Depto803 | [15 empty] | 0% | bar: 1 to 15
| Depto.804 | [15 empty] | 0% | bar: 1 to 15
| Depto.805 | [15 empty] | 0% | bar: 1 to 15
| Depto.806 | [15 empty] | 0% | bar: 1 to 15
| Depto.807 | [15 empty] | 0% | bar: 1 to 15
| Depto.808 | [15 empty] | 0% | bar: 1 to 15
| Depto.809 | [15 empty] | 0% | bar: 1 to 15
| Depto.810 | [15 empty] | 0% | bar: 1 to 15
| Depto.811 | [15 empty] | 0% | bar: 1 to 15
| Depto.812 | [15 empty] | 0% | bar: 1 to 15
| Depto.813 | [15 empty] | 0% | bar: 1 to 15
| Depto.814 | [15 empty] | 0% | bar: 1 to 15
| Depto.815 | [15 empty] | 0% | bar: 1 to 15
| Depto.816 | [15 empty] | 0% | bar: 1 to 15
| Depto.817 | [15 empty] | 0% | bar: 1 to 15
| Depto.818 | [15 empty] | 0% | bar: 1 to 15
| Depto.819 | [15 empty] | 0% | bar: 1 to 15
| Depto.820 | [15 empty] | 0% | bar: 1 to 15
| Depto.821 | [15 empty] | 0% | bar: 1 to 15
| Depto.822 | [15 empty] | 0% | bar: 1 to 15
| Depto.823 | [15 empty] | 0% | bar: 1 to 15
PISO N°8 B | Depto.801 | [15 empty] | 0% | bar: 1 to 15
| Depto.802 | [15 empty] | 0% | bar: 1 to 15
| Depto.803 | [15 empty] | 0% | bar: 1 to 15
| Depto.804 | [15 empty] | 0% | bar: 1 to 15
| Depto.805 | [15 empty] | 0% | bar: 1 to 15
| Depto.806 | [15 empty] | 0% | bar: 1 to 15
| Depto.807 | [15 empty] | 0% | bar: 1 to 15
| Depto.808 | [15 empty] | 0% | bar: 1 to 15
| Depto.809 | [15 empty] | 0% | bar: 1 to 15
| Depto.810 | [15 empty] | 0% | bar: 1 to 15
| Depto.811 | [15 empty] | 0% | bar: 1 to 15
| Depto.812 | [15 empty] | 0% | bar: 1 to 15
| Depto.813 | [15 empty] | 0% | bar: 1 to 15
| Depto.814 | [15 empty] | 0% | bar: 1 to 15
| Depto.815 | [15 empty] | 0% | bar: 1 to 15
| Depto.816 | [15 empty] | 0% | bar: 1 to 15
| Depto.817 | [15 empty] | 0% | bar: 1 to 15
| Depto.818 | [15 empty] | 0% | bar: 1 to 15
| Depto.819 | [15 empty] | 0% | bar: 1 to 15
| Depto.820 | [15 empty] | 0% | bar: 1 to 15
| Depto.821 | [15 empty] | 0% | bar: 1 to 15
GRAFICO DE AVANCE POR PARTIDA
PORCENTAJE POR PARTIDA | bar: 1 to 15
AVANCE GENERAL PISO N° 8 | bar: 1
PISO N°9 A | Depto.901 | [15 empty] | 0% | bar: 1 to 15
| Depto.902 | [15 empty] | 0% | bar: 1 to 15
| Depto.903 | [15 empty] | 0% | bar: 1 to 15
| Depto.904 | [15 empty] | 0% | bar: 1 to 15
| Depto.905 | [15 empty] | 0% | bar: 1 to 15
| Depto.906 | [15 empty] | 0% | bar: 1 to 15
| Depto.907 | [15 empty] | 0% | bar: 1 to 15
| Depto.908 | [15 empty] | 0% | bar: 1 to 15
| Depto.909 | [15 empty] | 0% | bar: 1 to 15
| Depto.910 | [15 empty] | 0% | bar: 1 to 15
| Depto.911 | [15 empty] | 0% | bar: 1 to 15
| Depto.912 | [15 empty] | 0% | bar: 1 to 15
| Depto.913 | [15 empty] | 0% | bar: 1 to 15
| Depto.914 | [15 empty] | 0% | bar: 1 to 15
| Depto.915 | [15 empty] | 0% | bar: 1 to 15
| Depto.916 | [15 empty] | 0% | bar: 1 to 15
| Depto.917 | [15 empty] | 0% | bar: 1 to 15
| Depto.918 | [15 empty] | 0% | bar: 1 to 15
| Depto.919 | [15 empty] | 0% | bar: 1 to 15
| Depto.923 | [15 empty] | 0% | bar: 1 to 15
PISO N°9 B | Depto.901 | [15 empty] | 0% | bar: 1 to 15
| Depto.902 | [15 empty] | 0% | bar: 1 to 15
| Depto.903 | [15 empty] | 0% | bar: 1 to 15
| Depto.904 | [15 empty] | 0% | bar: 1 to 15
| Depto.905 | [15 empty] | 0% | bar: 1 to 15
| Depto.906 | [15 empty] | 0% | bar: 1 to 15
| Depto.907 | [15 empty] | 0% | bar: 1 to 15
| Depto.908 | [15 empty] | 0% | bar: 1 to 15
| Depto.909 | [15 empty] | 0% | bar: 1 to 15
| Depto.910 | [15 empty] | 0% | bar: 1 to 15
| Depto.911 | [15 empty] | 0% | bar: 1 to 15
| Depto.912 | [15 empty] | 0% | bar: 1 to 15
| Depto.913 | [15 empty] | 0% | bar: 1 to 15
| Depto.914 | [15 empty] | 0% | bar: 1 to 15
| Depto.915 | [15 empty] | 0% | bar: 1 to 15
| Depto.916 | [15 empty] | 0% | bar: 1 to 15
| Depto.917 | [15 empty] | 0% | bar: 1 to 15
| Depto.918 | [15 empty] | 0% | bar: 1 to 15
| Depto.919 | [15 empty] | 0% | bar: 1 to 15
| Depto.920 | [15 empty] | 0% | bar: 1 to 15
| Depto.921 | [15 empty] | 0% | bar: 1 to 15
GRAFICO DE AVANCE POR PARTIDA
PORCENTAJE POR PARTIDA | bar: 1 to 15
AVANCE GENERAL PISO N° 9 | bar: 1
| PISO | Huinchas tabiques | Instalación Marco Puerta Acceso | Marcos Puertas Interiores | Impermeabilizacion Baños | Impermeabilizacion Terrazas | Preparación de Pisos | Instalacion de tina/Receptaculo | Protección Tina/receptaculo | Faldon de tina. | Instalación Ventana | Ceramica Pisos | Ceramica Muros | Instalación de Gargolas en Terraza | Frague | Cerámica de Terrazas | Avance Real x Piso
| Piso n°1 | 15% | 8.333% | 8.333% | 36.67% | 16.67% | 34.58% | 8.333% | 8.333% | 8.333% | 8.333% | 4.167% | 4.167% | 0% | 4.167% | 12.5% | 11.86%
| Piso n°2 | [15 empty] | 0% | bar: 1 to 15
| Piso n°3 | [15 empty] | 0% | bar: 1 to 15
| Piso n°4 | [15 empty] | 0% | bar: 1 to 15
| Piso n°5 | [15 empty] | 0% | bar: 1 to 15
| Piso n°6 | [15 empty] | 0% | bar: 1 to 15
| Piso n°7 | [15 empty] | 0% | bar: 1 to 15
| Piso n°8 | [15 empty] | 0% | bar: 1 to 15
| Piso n°9 | [15 empty] | 0% | bar: 1 to 15
| AVANCE PARTIDA | 1.667% | 0.9259% | 0.9259% | 4.074% | 1.852% | 3.843% | 0.9259% | 0.9259% | 0.9259% | 0.9259% | 0.463% | 0.463% | 0% | 0.463% | 1.389% | 1.318%
1.318%

## AVANCE SEMANAL 1 (hidden)
AVANCE SEMANAL POR PARTIDAS LYON
|  | MAYO | MAYO | JUNIO | JUNIO | JUNIO | JULIO | JULIO | JULIO | AGOSTO
| Partidas | PISO | PISO | PISO | PISO | PISO | PISO | PISO | PISO | PISO | PISO | PISO | PISO | % Avance Real | % Avance Programado | [5 empty] | Insidencia en Dias | METAS
|  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
[15 empty] | NOVIEMBRE | DICIEMBRE | ENERO | FEBRERO | MARZO
| 0% | 8.333% | 16.67% | 25% | 33.33% | 41.67% | 50% | 58.33% | 66.67% | 75% | 83.33% | 91.67% | 100% |  | 41.67% | 58.33% | 75% | 91.67% | 100%
FASE 1 | Recepción Obra Gruesa | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #REF! | #REF! | #REF! | #N/A | #N/A
| Cangueo y desbaste de pisos | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #REF! | #REF! | #REF! | #N/A | #N/A
| Retiro camisas / Tapado Pasadas | 58.33% | 97.67% | 47.73% | 0% | 0% | 0% | 0% | 0% | 0% | #REF! | #REF! | #REF! | #REF! | #REF!
| Pulido, descarachado y preparacion de muros | 58.33% | 95.35% | 18.18% | 0% | 0% | 0% | 0% | 0% | 0% | #REF! | #REF! | #REF! | #REF! | #REF!
| Trazado tabique/Yeso/auxiliares vent. Y puertas | 58.33% | 26.51% | 18.18% | 0% | 0% | 0% | 0% | 0% | 0% | #REF! | #REF! | #REF! | #REF! | #REF!
| Chequeo Rasgos Puerta Acceso | 38.33% | 29.77% | 18.18% | 0% | 0% | 0% | 0% | 0% | 0% | #REF! | #REF! | #REF! | #REF! | #REF!
| Grada Buque (9cm) | 58.33% | 46.51% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | #REF! | #REF! | #REF! | #REF! | #REF!
| Rasgo ventana - terrazas | 57.5% | 19.88% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | #REF! | #REF! | #REF! | #REF! | #REF!
| Despeje caja electricas | 52.08% | 48.84% | 12.27% | 0% | 0% | 0% | 0% | 0% | 0% | #REF! | #REF! | #REF! | #REF! | #REF!
| Yeso Muro | 58.33% | 45.35% | 18.18% | 0% | 0% | 0% | 0% | 0% | 0% | #REF! | #REF! | #REF! | #REF! | #REF!
| Yeso Cielo | 58.33% | 18.6% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | #REF! | #REF! | #REF! | #REF! | #REF!
| Sanitario vertical y ramal | 31.67% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | #REF! | #REF! | #REF! | #REF! | #REF!
| Instalación Lana Mineral | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #REF! | #REF! | #REF! | #N/A | #N/A
| Ductos de Extracción | 22.92% | 3.721% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | #REF! | #REF! | #REF! | #REF! | #REF!
| Maquillaje de Terraza | 44.17% | 14.65% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | #REF! | #REF! | #REF! | #REF! | #REF!
| Tabique 1° Cara | 52.71% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | #REF! | #REF! | #REF! | #REF! | #REF!
| Aislación Interior y Refuerzo Plasma | 45.83% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | #REF! | #REF! | #REF! | #REF! | #REF!
| Enlauchado | 8.333% | 8.333% | 8.333% | 8.333% | 8.333% | 8.333% | 8.333% | 8.333% | 8.333% | 8.333% | 8.333% | 8.333% | 8.333% | 8.333%
| Instalaciones Interior Tabique | 45% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | #REF! | #REF! | #REF! | #REF! | #REF!
| Tabique 2° cara | 36.04% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | #REF! | #REF! | #REF! | #REF! | #REF!
| Shaft /Tabique | 13.33% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | #REF! | #REF! | #REF! | #REF! | #REF!
| Mochetas y Dinteles Puerta Acceso | 11.67% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | #REF! | #REF! | #REF! | #REF! | #REF!
FASE 2 | [14 empty] | DICIEMBRE | ENERO | FEBRERO | MARZO | ABRIL | MAYO
[15 empty] | 25% | 41.67% | 58.33% | 75% | 91.67% | 100%
| Huinchas tabiques | 15% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | #REF! | #REF! | #REF! | #REF! | #REF!
| Instalación Marco Puerta Acceso | 8.333% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | #REF! | #REF! | #REF! | #REF! | #REF!
| Marcos Puertas Interiores | 8.333% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | #REF! | #REF! | #REF! | #REF! | #REF!
| Impermeabilizacion Baños | 36.67% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | #REF! | #REF! | #REF! | #REF! | #REF!
| Impermeabilizacion Terrazas | 16.67% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | #REF! | #REF! | #REF! | #REF! | #REF!
| Preparación de Pisos | 34.58% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | #REF! | #REF! | #REF! | #REF! | #REF!
| Instalacion de tina/Receptaculo | 8.333% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | #REF! | #REF! | #REF! | #REF! | #REF!
| Protección Tina/receptaculo | 8.333% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | #REF! | #REF! | #REF! | #REF! | #REF!
| Faldon de tina. | 8.333% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | #REF! | #REF! | #REF! | #REF! | #REF!
| Instalación Ventana | 8.333% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | #REF! | #REF! | #REF! | #REF! | #REF!
| Ceramica Pisos | 4.167% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | #REF! | #REF! | #REF! | #REF! | #REF!
| Ceramica Muros | 4.167% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | #REF! | #REF! | #REF! | #REF! | #REF!
| Instalación de Gargolas en Terraza | [12 empty] | 0% | 0% | bar: 1 to 12
| Frague | 4.167% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | #REF! | #REF! | #REF! | #REF! | #REF!
| Cerámica de Terrazas | 12.5% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | #REF! | #REF! | #REF! | #REF! | #REF!
FASE 3 | [14 empty] | ENERO | FEBRERO | MARZO | ABRIL | MAYO | JUNIO
[15 empty] | 25% | 41.67% | 58.33% | 75% | 91.67% | 100%
| Instalación piernas de closet | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | #REF! | #REF! | #REF! | #REF! | #REF!
| Instalación Cornisas | 8.333% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | #REF! | #REF! | #REF! | #REF! | #REF!
| Cuadratura de cajas. | 33.33% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | #REF! | #REF! | #REF! | #REF! | #REF!
| Remate yeso y cornisas | 8.333% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | #REF! | #REF! | #REF! | #REF! | #REF!
| Puertas interiores | 8.333% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | #REF! | #REF! | #REF! | #REF! | #REF!
| Puertas de acceso y pasillo | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | #REF! | #REF! | #REF! | #REF! | #REF!
| Cerradura Puertas | 8.333% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | #REF! | #REF! | #REF! | #REF! | #REF!
| Cableado Eléctrico y CCDD | 8.333% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | #REF! | #REF! | #REF! | #REF! | #REF!
| Canterias | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | #REF! | #REF! | #REF! | #REF! | #REF!
| Empaste Muro Cielo | 8.333% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | #REF! | #REF! | #REF! | #REF! | #REF!
| Instalacion Guardapolvo | 8.333% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | #REF! | #REF! | #REF! | #REF! | #REF!
| Instalación de Baranda de Crital | 8.333% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | #REF! | #REF! | #REF! | #REF! | #REF!
| Pintura Cielo Terrazas | 8.333% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | #REF! | #REF! | #REF! | #REF! | #REF!
| Grano Muros Terrazas | 8.333% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | #REF! | #REF! | #REF! | #REF! | #REF!
| Losalin Cielo Departamento | 8.333% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | #REF! | #REF! | #REF! | #REF! | #REF!
| Pintura Cielo Baños | 8.333% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | #REF! | #REF! | #REF! | #REF! | #REF!
| Instalacion de Muebles baño | 8.333% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | #REF! | #REF! | #REF! | #REF! | #REF!
| Instalacion Muebles de cocina (Base) | 8.333% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | #REF! | #REF! | #REF! | #REF! | #REF!
| Instalacion Muebles de cocina (Aereo) | 8.333% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | #REF! | #REF! | #REF! | #REF! | #REF!
| Instalación cubiertas cocina | 8.333% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | #REF! | #REF! | #REF! | #REF! | #REF!
| Muebles Interior closet | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | #REF! | #REF! | #REF! | #REF! | #REF!
FASE 4 | [14 empty] | FEBRERO | MARZO | ABRIL | MAYO | JUNIO | JULIO
[15 empty] | 25% | 41.67% | 58.33% | 75% | 91.67% | 100%
| Instalacion de Artefactos Sanitarios. | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | #REF! | #REF! | #REF! | #REF! | #REF!
| Extractor de baño. | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | #REF! | #REF! | #REF! | #REF! | #REF!
| 1° mano de Pintura (interior closet+ puertas) | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #REF! | #REF! | #REF! | #N/A | #N/A
| Instalacion de Espejos. | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #REF! | #REF! | #REF! | #N/A | #N/A
| Kit de cocina (Horno-Encimera -Campana - Lavaplato) | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | #REF! | #REF! | #REF! | #REF! | #REF!
| Griferia. | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | #REF! | #REF! | #REF! | #REF! | #REF!
| Pruebas de Instalaciones. | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | #REF! | #REF! | #REF! | #REF! | #REF!
| Piso Flotante + cubrejunta + junquillo | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | #REF! | #REF! | #REF! | #REF! | #REF!
| Protección Piso Flotante | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | #REF! | #REF! | #REF! | #REF! | #REF!
| (2°) Segunda Mano Pintura Interior | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #REF! | #REF! | #REF! | #N/A | #N/A
| 2° mano de pintura. (puertas, , cielo de baño, ) | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #REF! | #REF! | #REF! | #N/A | #N/A
| Topes en piso y Accesorios | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | #REF! | #REF! | #REF! | #REF! | #REF!
| Instalación de Shower Door y Barra Cortina | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #REF! | #REF! | #REF! | #N/A | #N/A
| PROGRAMA PARA R1 | [12 empty] | #N/A
PROGRAMA PARA RF
[7 empty] | 1330 | 48146000

## FASE 1
Avance General
CONTROL AVANCE FASE 1 SAN FRANCISCO 211
[20 empty] | Cantidad de Deptos. | 359 | 7.833%
|  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20
| Deptos. | Retiro camisas / Tapado Pasadas | Pulido, descarachado y preparacion de muros | Trazado tabique/Yeso/auxiliares vent. Y puertas | Chequeo Rasgos Puerta Acceso | Grada Buque (9cm) | Rasgo ventana - terrazas | Despeje caja electricas | Yeso Muro | Yeso Cielo | Sanitario vertical y ramal | Instalación Lana Mineral Verticales Samitarias | Ductos de Extracción | Maquillaje de Terraza | Tabique 1° Cara | Aislación Interior y Refuerzo Plasma | Enlauchado | Instalaciones Interior Tabique | Tabique 2° cara | Shaft /Tabique | Mochetas y Dinteles Puerta Acceso | Avance Real x Piso
PISO N° 1 | DEPTO 102 | 100% | 100% | 100% | 90% | 100% | 100% | 100% | 100% | 100% | 50% | 0% | 50% | 80% | 90% | 100% | 0% | 90% | 90% | 20% | 0% | 73%
| DEPTO 103 | 100% | 100% | 100% | 90% | 100% | 100% | 100% | 100% | 100% | 50% | 0% | 50% | 80% | 90% | 100% | 0% | 90% | 90% | 20% | 0% | 73%
| DEPTO 104 | 100% | 100% | 100% | 90% | 100% | 100% | 100% | 100% | 100% | 50% | 0% | 50% | 80% | 90% | 100% | 0% | 90% | 90% | 20% | 40% | 75%
| DEPTO 105 | 100% | 100% | 100% | 90% | 100% | 100% | 100% | 100% | 100% | 50% | 0% | 50% | 80% | 90% | 100% | 0% | 90% | 90% | 20% | 40% | 75%
| DEPTO 106 | 100% | 100% | 100% | 90% | 100% | 100% | 100% | 100% | 100% | 50% | 0% | 50% | 80% | 90% | 100% | 0% | 90% | 90% | 20% | 0% | 73%
| DEPTO 107 | 100% | 100% | 100% | 50% | 100% | 100% | 100% | 100% | 100% | 50% | 0% | 50% | 80% | 90% | 100% | 0% | 90% | 90% | 20% | 0% | 71%
| DEPTO 108 | 100% | 100% | 100% | 50% | 100% | 100% | 100% | 100% | 100% | 50% | 0% | 50% | 80% | 90% | 100% | 0% | 90% | 50% | 0% | 0% | 68%
| DEPTO 118 | 100% | 100% | 100% | 80% | 100% | 100% | 100% | 100% | 100% | 0% | 0% | 0% | 0% | 90% | 100% | 0% | 50% | 0% | 0% | 0% | 56%
| DEPTO 119 | 100% | 100% | 100% | 90% | 100% | 80% | 100% | 100% | 100% | 0% | 0% | 0% | 0% | 90% | 100% | 0% | 50% | 0% | 0% | 0% | 55.5%
| DEPTO 120 | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
| DEPTO 121 | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
| LOCAL 1 | [20 empty] | 0% | bar: 1 to 20
| LOCAL 2 | [20 empty] | 0% | bar: 1 to 20
| LOCAL 3 | [20 empty] | 0% | bar: 1 to 20
| LOCAL 4 | [20 empty] | 0% | bar: 1 to 20
| LOCAL 5 | [20 empty] | 0% | bar: 1 to 20
| LOCAL 6 | [20 empty] | 0% | bar: 1 to 20
| LOCAL 7 | 100% | 100% | 100% | 0% | 100% | 100% | 50% | 100% | 100% | 70% | 100% | 0% | 100% | 85% | 0% | 0% | 50% | 25% | 0% | 0% | 59%
| LOCAL 8 | 100% | 100% | 100% | 0% | 100% | 100% | 50% | 100% | 100% | 70% | 100% | 0% | 100% | 85% | 0% | 0% | 50% | 25% | 0% | 0% | 59%
| LOCAL 9 | 100% | 100% | 100% | 0% | 100% | 100% | 50% | 100% | 100% | 70% | 100% | 0% | 100% | 85% | 0% | 0% | 50% | 25% | 0% | 0% | 59%
| COWORK | [20 empty] | 0% | bar: 1 to 20
| GIMNASIO | [20 empty] | 0% | bar: 1 to 20
| SALON GOURMET 1 | [20 empty] | 0% | bar: 1 to 20
| SALON GOURMET 2 | [20 empty] | 0% | bar: 1 to 20
GRAFICO DE AVANCE POR PARTIDA
PORCENTAJE POR PARTIDA |  | 58.33% | 58.33% | 58.33% | 38.33% | 58.33% | 57.5% | 52.08% | 58.33% | 58.33% | 31.67% | 20.83% | 22.92% | 44.17% | 52.71% | 45.83% | 8.333% | 45% | 36.04% | 13.33% | 11.67%
AVANCE GENERAL PISO N° 1 |  | 1: 41.52%
PISO N° 2 A | Depto 202 | 100% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 10%
| Depto.203 | 100% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 10%
| Depto.204 | 100% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 10%
| Depto.205 | 100% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 10%
| Depto.206 | 100% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 10%
| Depto.207 | 100% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 10%
| Depto.208 | 100% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 10%
| Depto.209 | 100% | 100% | 0% | 0% | 0% | 0% | 0% | 50% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 12.5%
| Depto.210 | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 5%
| Depto.211 | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 5%
| Depto.212 | 100% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 10%
| Depto.213 | 100% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 10%
| Depto.214 | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 5%
| Depto.215 | 100% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 10%
| Depto.216 | 100% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 10%
| Depto.217 | 100% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 10%
| Depto.218 | 100% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 10%
| Depto.219 | 100% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 10%
| Depto.220 | 100% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 10%
| Depto.221 | 100% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 10%
| Depto.222 | 100% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 10%
| Depto.223 | 100% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 10%
PISO N° 2 B | Depto.201 | 100% | 100% | 100% | 90% | 100% | 95% | 100% | 100% | 100% | 0% | 0% | 20% | 90% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 49.75%
| Depto.202 | 100% | 100% | 100% | 90% | 100% | 95% | 100% | 90% | 100% | 0% | 0% | 20% | 90% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 49.25%
| Depto.203 | 100% | 100% | 100% | 90% | 100% | 95% | 100% | 90% | 100% | 0% | 0% | 20% | 90% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 49.25%
| Depto.204 | 100% | 100% | 100% | 50% | 100% | 95% | 100% | 90% | 100% | 0% | 0% | 20% | 90% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 47.25%
| Depto.205 | 100% | 100% | 100% | 50% | 100% | 95% | 100% | 90% | 100% | 0% | 0% | 20% | 90% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 47.25%
| Depto.206 | 100% | 100% | 100% | 80% | 100% | 95% | 100% | 90% | 100% | 0% | 0% | 20% | 90% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 48.75%
| Depto.207 | 100% | 100% | 100% | 90% | 100% | 95% | 100% | 90% | 100% | 0% | 0% | 20% | 90% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 49.25%
| Depto.208 | 100% | 100% | 100% | 90% | 100% | 95% | 100% | 90% | 100% | 0% | 0% | 20% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 44.75%
| Depto.209 | 100% | 100% | 100% | 50% | 100% | 95% | 100% | 90% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 36.75%
| Depto.210 | 100% | 100% | 20% | 50% | 100% | 0% | 100% | 90% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 28%
| Depto.211 | 100% | 100% | 20% | 50% | 100% | 0% | 100% | 90% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 28%
| Depto.212 | 100% | 100% | 20% | 50% | 100% | 0% | 100% | 90% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 28%
| Depto.213 | 100% | 100% | 20% | 50% | 100% | 0% | 100% | 90% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 28%
| Depto.214 | 100% | 100% | 20% | 50% | 0% | 0% | 100% | 90% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 23%
| Depto.215 | 100% | 100% | 20% | 50% | 100% | 0% | 100% | 90% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 28%
| Depto.216 | 100% | 100% | 20% | 50% | 100% | 0% | 100% | 90% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 28%
| Depto.217 | 100% | 100% | 20% | 50% | 100% | 0% | 100% | 90% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 28%
| Depto.218 | 100% | 100% | 20% | 50% | 100% | 0% | 100% | 90% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 28%
| Depto.219 | 100% | 100% | 20% | 50% | 100% | 0% | 100% | 90% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 28%
| Depto.220 | 100% | 100% | 20% | 50% | 100% | 0% | 100% | 90% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 28%
| Depto.221 | 100% | 100% | 20% | 50% | 100% | 0% | 100% | 90% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 28%
GRAFICO DE AVANCE POR PARTIDA
PORCENTAJE POR PARTIDA |  | 97.67% | 95.35% | 26.51% | 29.77% | 46.51% | 19.88% | 48.84% | 45.35% | 18.6% | 0% | 0% | 3.721% | 14.65% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
AVANCE GENERAL PISO N° 2 |  | 1: 22.34%
PISO N°3 A | Depto.301 | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 5%
| Depto.302 | [20 empty] | 0% | bar: 1 to 20
| Depto.303 | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 5%
| Depto.304 | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 5%
| Depto.305 | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 5%
| Depto.306 | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 5%
| Depto.307 | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 5%
| Depto.308 | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 5%
| Depto.309 | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 5%
| Depto.310 | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 5%
| Depto.311 | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 5%
| Depto.312 | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 5%
| Depto.313 | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 5%
| Depto.314 | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 5%
| Depto.315 | [20 empty] | 0% | bar: 1 to 20
| Depto.316 | [20 empty] | 0% | bar: 1 to 20
| Depto.317 | [20 empty] | 0% | bar: 1 to 20
| Depto.318 | [20 empty] | 0% | bar: 1 to 20
| Depto.319 | [20 empty] | 0% | bar: 1 to 20
| Depto.320 | [20 empty] | 0% | bar: 1 to 20
| Depto.321 | [20 empty] | 0% | bar: 1 to 20
| Depto.322 | [20 empty] | 0% | bar: 1 to 20
| Depto.323 | [20 empty] | 0% | bar: 1 to 20
PISO N°3 B | Depto.301 | 100% | 100% | 100% | 100% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 25%
| Depto.302 | 100% | 100% | 100% | 100% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 25%
| Depto.303 | 100% | 100% | 100% | 100% | 0% | 0% | 90% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 29.5%
| Depto.304 | 100% | 100% | 100% | 100% | 0% | 0% | 90% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 29.5%
| Depto.305 | 100% | 100% | 100% | 100% | 0% | 0% | 90% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 29.5%
| Depto.306 | 100% | 100% | 100% | 100% | 0% | 0% | 90% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 29.5%
| Depto.307 | 100% | 100% | 100% | 100% | 0% | 0% | 90% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 29.5%
| Depto.308 | 100% | 100% | 100% | 100% | 0% | 0% | 90% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 29.5%
| Depto.309 | [20 empty] | 0% | bar: 1 to 20
| Depto.310 | [20 empty] | 0% | bar: 1 to 20
| Depto.311 | [20 empty] | 0% | bar: 1 to 20
| Depto.312 | [20 empty] | 0% | bar: 1 to 20
| Depto.313 | [20 empty] | 0% | bar: 1 to 20
| Depto.314 | [20 empty] | 0% | bar: 1 to 20
| Depto.315 | [20 empty] | 0% | bar: 1 to 20
| Depto.316 | [20 empty] | 0% | bar: 1 to 20
| Depto.317 | [20 empty] | 0% | bar: 1 to 20
| Depto.318 | [20 empty] | 0% | bar: 1 to 20
| Depto.319 | [20 empty] | 0% | bar: 1 to 20
| Depto.320 | [20 empty] | 0% | bar: 1 to 20
| Depto.321 | [20 empty] | 0% | bar: 1 to 20
GRAFICO DE AVANCE POR PARTIDA
PORCENTAJE POR PARTIDA |  | 47.73% | 18.18% | 18.18% | 18.18% | 0% | 0% | 12.27% | 18.18% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
AVANCE GENERAL PISO N° 3 |  | 1: 6.636%
PISO N°4 A | Depto.401 | [20 empty] | 0% | bar: 1 to 20
| Depto.402 | [20 empty] | 0% | bar: 1 to 20
| Depto.403 | [20 empty] | 0% | bar: 1 to 20
| Depto.404 | [20 empty] | 0% | bar: 1 to 20
| Depto.405 | [20 empty] | 0% | bar: 1 to 20
| Depto.406 | [20 empty] | 0% | bar: 1 to 20
| Depto.407 | [20 empty] | 0% | bar: 1 to 20
| Depto.408 | [20 empty] | 0% | bar: 1 to 20
| Depto.409 | [20 empty] | 0% | bar: 1 to 20
| Depto.410 | [20 empty] | 0% | bar: 1 to 20
| Depto.411 | [20 empty] | 0% | bar: 1 to 20
| Depto.412 | [20 empty] | 0% | bar: 1 to 20
| Depto.413 | [20 empty] | 0% | bar: 1 to 20
| Depto.414 | [20 empty] | 0% | bar: 1 to 20
| Depto.415 | [20 empty] | 0% | bar: 1 to 20
| Depto.416 | [20 empty] | 0% | bar: 1 to 20
| Depto.417 | [20 empty] | 0% | bar: 1 to 20
| Depto.418 | [20 empty] | 0% | bar: 1 to 20
| Depto.419 | [20 empty] | 0% | bar: 1 to 20
| Depto.420 | [20 empty] | 0% | bar: 1 to 20
| Depto.421 | [20 empty] | 0% | bar: 1 to 20
| Depto.422 | [20 empty] | 0% | bar: 1 to 20
| Depto.423 | [20 empty] | 0% | bar: 1 to 20
PISO N°4 B | Depto.401 | [20 empty] | 0% | bar: 1 to 20
| Depto.402 | [20 empty] | 0% | bar: 1 to 20
| Depto.403 | [20 empty] | 0% | bar: 1 to 20
| Depto.404 | [20 empty] | 0% | bar: 1 to 20
| Depto.405 | [20 empty] | 0% | bar: 1 to 20
| Depto.406 | [20 empty] | 0% | bar: 1 to 20
| Depto.407 | [20 empty] | 0% | bar: 1 to 20
| Depto.408 | [20 empty] | 0% | bar: 1 to 20
| Depto.409 | [20 empty] | 0% | bar: 1 to 20
| Depto.410 | [20 empty] | 0% | bar: 1 to 20
| Depto.411 | [20 empty] | 0% | bar: 1 to 20
| Depto.412 | [20 empty] | 0% | bar: 1 to 20
| Depto.413 | [20 empty] | 0% | bar: 1 to 20
| Depto.414 | [20 empty] | 0% | bar: 1 to 20
| Depto.415 | [20 empty] | 0% | bar: 1 to 20
| Depto.416 | [20 empty] | 0% | bar: 1 to 20
| Depto.417 | [20 empty] | 0% | bar: 1 to 20
| Depto.418 | [20 empty] | 0% | bar: 1 to 20
| Depto.419 | [20 empty] | 0% | bar: 1 to 20
| Depto.420 | [20 empty] | 0% | bar: 1 to 20
| Depto.421 | [20 empty] | 0% | bar: 1 to 20
GRAFICO DE AVANCE POR PARTIDA
PORCENTAJE POR PARTIDA | bar: 1 to 20
AVANCE GENERAL PISO N° 4 | bar: 1
PISO N°5 A | Depto.501 | [20 empty] | 0% | bar: 1 to 20
| Depto.502 | [20 empty] | 0% | bar: 1 to 20
| Depto.503 | [20 empty] | 0% | bar: 1 to 20
| Depto.504 | [20 empty] | 0% | bar: 1 to 20
| Depto.505 | [20 empty] | 0% | bar: 1 to 20
| Depto.506 | [20 empty] | 0% | bar: 1 to 20
| Depto.507 | [20 empty] | 0% | bar: 1 to 20
| Depto.508 | [20 empty] | 0% | bar: 1 to 20
| Depto.509 | [20 empty] | 0% | bar: 1 to 20
| Depto.510 | [20 empty] | 0% | bar: 1 to 20
| Depto.511 | [20 empty] | 0% | bar: 1 to 20
| Depto.512 | [20 empty] | 0% | bar: 1 to 20
| Depto.513 | [20 empty] | 0% | bar: 1 to 20
| Depto.514 | [20 empty] | 0% | bar: 1 to 20
| Depto.515 | [20 empty] | 0% | bar: 1 to 20
| Depto.516 | [20 empty] | 0% | bar: 1 to 20
| Depto.517 | [20 empty] | 0% | bar: 1 to 20
| Depto.518 | [20 empty] | 0% | bar: 1 to 20
| Depto.519 | [20 empty] | 0% | bar: 1 to 20
| Depto.520 | [20 empty] | 0% | bar: 1 to 20
| Depto.521 | [20 empty] | 0% | bar: 1 to 20
| Depto.522 | [20 empty] | 0% | bar: 1 to 20
| Depto.523 | [20 empty] | 0% | bar: 1 to 20
PISO N°5 B | Depto.501 | [20 empty] | 0% | bar: 1 to 20
| Depto.502 | [20 empty] | 0% | bar: 1 to 20
| Depto.503 | [20 empty] | 0% | bar: 1 to 20
| Depto.504 | [20 empty] | 0% | bar: 1 to 20
| Depto.505 | [20 empty] | 0% | bar: 1 to 20
| Depto.506 | [20 empty] | 0% | bar: 1 to 20
| Depto.507 | [20 empty] | 0% | bar: 1 to 20
| Depto.508 | [20 empty] | 0% | bar: 1 to 20
| Depto.509 | [20 empty] | 0% | bar: 1 to 20
| Depto.510 | [20 empty] | 0% | bar: 1 to 20
| Depto.511 | [20 empty] | 0% | bar: 1 to 20
| Depto.512 | [20 empty] | 0% | bar: 1 to 20
| Depto.513 | [20 empty] | 0% | bar: 1 to 20
| Depto.514 | [20 empty] | 0% | bar: 1 to 20
| Depto.515 | [20 empty] | 0% | bar: 1 to 20
| Depto.516 | [20 empty] | 0% | bar: 1 to 20
| Depto.517 | [20 empty] | 0% | bar: 1 to 20
| Depto.518 | [20 empty] | 0% | bar: 1 to 20
| Depto.519 | [20 empty] | 0% | bar: 1 to 20
| Depto.520 | [20 empty] | 0% | bar: 1 to 20
| Depto.521 | [20 empty] | 0% | bar: 1 to 20
GRAFICO DE AVANCE POR PARTIDA
PORCENTAJE POR PARTIDA | bar: 1 to 20
AVANCE GENERAL PISO N° 5 | bar: 1
PISO N°6 A | Depto.601 | [20 empty] | 0% | bar: 1 to 20
| Depto.602 | [20 empty] | 0% | bar: 1 to 20
| Depto.603 | [20 empty] | 0% | bar: 1 to 20
| Depto.604 | [20 empty] | 0% | bar: 1 to 20
| Depto.605 | [20 empty] | 0% | bar: 1 to 20
| Depto.606 | [20 empty] | 0% | bar: 1 to 20
| Depto.607 | [20 empty] | 0% | bar: 1 to 20
| Depto.608 | [20 empty] | 0% | bar: 1 to 20
| Depto.609 | [20 empty] | 0% | bar: 1 to 20
| Depto.610 | [20 empty] | 0% | bar: 1 to 20
| Depto.611 | [20 empty] | 0% | bar: 1 to 20
| Depto.612 | [20 empty] | 0% | bar: 1 to 20
| Depto.613 | [20 empty] | 0% | bar: 1 to 20
| Depto.614 | [20 empty] | 0% | bar: 1 to 20
| Depto.615 | [20 empty] | 0% | bar: 1 to 20
| Depto.616 | [20 empty] | 0% | bar: 1 to 20
| Depto.617 | [20 empty] | 0% | bar: 1 to 20
| Depto.618 | [20 empty] | 0% | bar: 1 to 20
| Depto.619 | [20 empty] | 0% | bar: 1 to 20
| Depto.620 | [20 empty] | 0% | bar: 1 to 20
| Depto.621 | [20 empty] | 0% | bar: 1 to 20
| Depto.622 | [20 empty] | 0% | bar: 1 to 20
| Depto.623 | [20 empty] | 0% | bar: 1 to 20
PISO N°6 B | Depto.601 | [20 empty] | 0% | bar: 1 to 20
| Depto.602 | [20 empty] | 0% | bar: 1 to 20
| Depto.603 | [20 empty] | 0% | bar: 1 to 20
| Depto.604 | [20 empty] | 0% | bar: 1 to 20
| Depto.605 | [20 empty] | 0% | bar: 1 to 20
| Depto.606 | [20 empty] | 0% | bar: 1 to 20
| Depto.607 | [20 empty] | 0% | bar: 1 to 20
| Depto.608 | [20 empty] | 0% | bar: 1 to 20
| Depto.609 | [20 empty] | 0% | bar: 1 to 20
| Depto.610 | [20 empty] | 0% | bar: 1 to 20
| Depto.611 | [20 empty] | 0% | bar: 1 to 20
| Depto.612 | [20 empty] | 0% | bar: 1 to 20
| Depto.613 | [20 empty] | 0% | bar: 1 to 20
| Depto.614 | [20 empty] | 0% | bar: 1 to 20
| Depto.615 | [20 empty] | 0% | bar: 1 to 20
| Depto.616 | [20 empty] | 0% | bar: 1 to 20
| Depto.617 | [20 empty] | 0% | bar: 1 to 20
| Depto.618 | [20 empty] | 0% | bar: 1 to 20
| Depto.619 | [20 empty] | 0% | bar: 1 to 20
| Depto.620 | [20 empty] | 0% | bar: 1 to 20
| Depto.621 | [20 empty] | 0% | bar: 1 to 20
GRAFICO DE AVANCE POR PARTIDA
PORCENTAJE POR PARTIDA | bar: 1 to 20
AVANCE GENERAL PISO N° 6 | bar: 1
PISO N°7 A | Depto.701 | [20 empty] | 0% | bar: 1 to 20
| Depto.702 | [20 empty] | 0% | bar: 1 to 20
| Depto703 | [20 empty] | 0% | bar: 1 to 20
| Depto.704 | [20 empty] | 0% | bar: 1 to 20
| Depto.705 | [20 empty] | 0% | bar: 1 to 20
| Depto.706 | [20 empty] | 0% | bar: 1 to 20
| Depto.707 | [20 empty] | 0% | bar: 1 to 20
| Depto.708 | [20 empty] | 0% | bar: 1 to 20
| Depto.709 | [20 empty] | 0% | bar: 1 to 20
| Depto.710 | [20 empty] | 0% | bar: 1 to 20
| Depto.711 | [20 empty] | 0% | bar: 1 to 20
| Depto.712 | [20 empty] | 0% | bar: 1 to 20
| Depto.713 | [20 empty] | 0% | bar: 1 to 20
| Depto.714 | [20 empty] | 0% | bar: 1 to 20
| Depto.715 | [20 empty] | 0% | bar: 1 to 20
| Depto.716 | [20 empty] | 0% | bar: 1 to 20
| Depto.717 | [20 empty] | 0% | bar: 1 to 20
| Depto.718 | [20 empty] | 0% | bar: 1 to 20
| Depto.719 | [20 empty] | 0% | bar: 1 to 20
| Depto.720 | [20 empty] | 0% | bar: 1 to 20
| Depto.721 | [20 empty] | 0% | bar: 1 to 20
| Depto.722 | [20 empty] | 0% | bar: 1 to 20
| Depto.723 | [20 empty] | 0% | bar: 1 to 20
PISO N°7 B | Depto.701 | [20 empty] | 0% | bar: 1 to 20
| Depto.702 | [20 empty] | 0% | bar: 1 to 20
| Depto.703 | [20 empty] | 0% | bar: 1 to 20
| Depto.704 | [20 empty] | 0% | bar: 1 to 20
| Depto.705 | [20 empty] | 0% | bar: 1 to 20
| Depto.706 | [20 empty] | 0% | bar: 1 to 20
| Depto.707 | [20 empty] | 0% | bar: 1 to 20
| Depto.708 | [20 empty] | 0% | bar: 1 to 20
| Depto.709 | [20 empty] | 0% | bar: 1 to 20
| Depto.710 | [20 empty] | 0% | bar: 1 to 20
| Depto.711 | [20 empty] | 0% | bar: 1 to 20
| Depto.712 | [20 empty] | 0% | bar: 1 to 20
| Depto.713 | [20 empty] | 0% | bar: 1 to 20
| Depto.714 | [20 empty] | 0% | bar: 1 to 20
| Depto.715 | [20 empty] | 0% | bar: 1 to 20
| Depto.716 | [20 empty] | 0% | bar: 1 to 20
| Depto.717 | [20 empty] | 0% | bar: 1 to 20
| Depto.718 | [20 empty] | 0% | bar: 1 to 20
| Depto.719 | [20 empty] | 0% | bar: 1 to 20
| Depto.720 | [20 empty] | 0% | bar: 1 to 20
| Depto.721 | [20 empty] | 0% | bar: 1 to 20
GRAFICO DE AVANCE POR PARTIDA
PORCENTAJE POR PARTIDA | bar: 1 to 20
AVANCE GENERAL PISO N° 7 | bar: 1
PISO N°8 A | Depto.801 | [20 empty] | 0% | bar: 1 to 20
| Depto.802 | [20 empty] | 0% | bar: 1 to 20
| Depto803 | [20 empty] | 0% | bar: 1 to 20
| Depto.804 | [20 empty] | 0% | bar: 1 to 20
| Depto.805 | [20 empty] | 0% | bar: 1 to 20
| Depto.806 | [20 empty] | 0% | bar: 1 to 20
| Depto.807 | [20 empty] | 0% | bar: 1 to 20
| Depto.808 | [20 empty] | 0% | bar: 1 to 20
| Depto.809 | [20 empty] | 0% | bar: 1 to 20
| Depto.810 | [20 empty] | 0% | bar: 1 to 20
| Depto.811 | [20 empty] | 0% | bar: 1 to 20
| Depto.812 | [20 empty] | 0% | bar: 1 to 20
| Depto.813 | [20 empty] | 0% | bar: 1 to 20
| Depto.814 | [20 empty] | 0% | bar: 1 to 20
| Depto.815 | [20 empty] | 0% | bar: 1 to 20
| Depto.816 | [20 empty] | 0% | bar: 1 to 20
| Depto.817 | [20 empty] | 0% | bar: 1 to 20
| Depto.818 | [20 empty] | 0% | bar: 1 to 20
| Depto.819 | [20 empty] | 0% | bar: 1 to 20
| Depto.820 | [20 empty] | 0% | bar: 1 to 20
| Depto.821 | [20 empty] | 0% | bar: 1 to 20
| Depto.822 | [20 empty] | 0% | bar: 1 to 20
| Depto.823 | [20 empty] | 0% | bar: 1 to 20
PISO N°8 B | Depto.801 | [20 empty] | 0% | bar: 1 to 20
| Depto.802 | [20 empty] | 0% | bar: 1 to 20
| Depto.803 | [20 empty] | 0% | bar: 1 to 20
| Depto.804 | [20 empty] | 0% | bar: 1 to 20
| Depto.805 | [20 empty] | 0% | bar: 1 to 20
| Depto.806 | [20 empty] | 0% | bar: 1 to 20
| Depto.807 | [20 empty] | 0% | bar: 1 to 20
| Depto.808 | [20 empty] | 0% | bar: 1 to 20
| Depto.809 | [20 empty] | 0% | bar: 1 to 20
| Depto.810 | [20 empty] | 0% | bar: 1 to 20
| Depto.811 | [20 empty] | 0% | bar: 1 to 20
| Depto.812 | [20 empty] | 0% | bar: 1 to 20
| Depto.813 | [20 empty] | 0% | bar: 1 to 20
| Depto.814 | [20 empty] | 0% | bar: 1 to 20
| Depto.815 | [20 empty] | 0% | bar: 1 to 20
| Depto.816 | [20 empty] | 0% | bar: 1 to 20
| Depto.817 | [20 empty] | 0% | bar: 1 to 20
| Depto.818 | [20 empty] | 0% | bar: 1 to 20
| Depto.819 | [20 empty] | 0% | bar: 1 to 20
| Depto.820 | [20 empty] | 0% | bar: 1 to 20
| Depto.821 | [20 empty] | 0% | bar: 1 to 20
GRAFICO DE AVANCE POR PARTIDA
PORCENTAJE POR PARTIDA | bar: 1 to 20
AVANCE GENERAL PISO N° 8 | bar: 1
PISO N°9 A | Depto.901 | [20 empty] | 0% | bar: 1 to 20
| Depto.902 | [20 empty] | 0% | bar: 1 to 20
| Depto.903 | [20 empty] | 0% | bar: 1 to 20
| Depto.904 | [20 empty] | 0% | bar: 1 to 20
| Depto.905 | [20 empty] | 0% | bar: 1 to 20
| Depto.906 | [20 empty] | 0% | bar: 1 to 20
| Depto.907 | [20 empty] | 0% | bar: 1 to 20
| Depto.908 | [20 empty] | 0% | bar: 1 to 20
| Depto.909 | [20 empty] | 0% | bar: 1 to 20
| Depto.910 | [20 empty] | 0% | bar: 1 to 20
| Depto.911 | [20 empty] | 0% | bar: 1 to 20
| Depto.912 | [20 empty] | 0% | bar: 1 to 20
| Depto.913 | [20 empty] | 0% | bar: 1 to 20
| Depto.914 | [20 empty] | 0% | bar: 1 to 20
| Depto.915 | [20 empty] | 0% | bar: 1 to 20
| Depto.916 | [20 empty] | 0% | bar: 1 to 20
| Depto.917 | [20 empty] | 0% | bar: 1 to 20
| Depto.918 | [20 empty] | 0% | bar: 1 to 20
| Depto.919 | [20 empty] | 0% | bar: 1 to 20
| Depto.923 | [20 empty] | 0% | bar: 1 to 20
PISO N°9 B | Depto.901 | [20 empty] | 0% | bar: 1 to 20
| Depto.902 | [20 empty] | 0% | bar: 1 to 20
| Depto.903 | [20 empty] | 0% | bar: 1 to 20
| Depto.904 | [20 empty] | 0% | bar: 1 to 20
| Depto.905 | [20 empty] | 0% | bar: 1 to 20
| Depto.906 | [20 empty] | 0% | bar: 1 to 20
| Depto.907 | [20 empty] | 0% | bar: 1 to 20
| Depto.908 | [20 empty] | 0% | bar: 1 to 20
| Depto.909 | [20 empty] | 0% | bar: 1 to 20
| Depto.910 | [20 empty] | 0% | bar: 1 to 20
| Depto.911 | [20 empty] | 0% | bar: 1 to 20
| Depto.912 | [20 empty] | 0% | bar: 1 to 20
| Depto.913 | [20 empty] | 0% | bar: 1 to 20
| Depto.914 | [20 empty] | 0% | bar: 1 to 20
| Depto.915 | [20 empty] | 0% | bar: 1 to 20
| Depto.916 | [20 empty] | 0% | bar: 1 to 20
| Depto.917 | [20 empty] | 0% | bar: 1 to 20
| Depto.918 | [20 empty] | 0% | bar: 1 to 20
| Depto.919 | [20 empty] | 0% | bar: 1 to 20
| Depto.920 | [20 empty] | 0% | bar: 1 to 20
| Depto.921 | [20 empty] | 0% | bar: 1 to 20
GRAFICO DE AVANCE POR PARTIDA
PORCENTAJE POR PARTIDA | bar: 1 to 20
AVANCE GENERAL PISO N° 9 | bar: 1
|  | Retiro camisas / Tapado Pasadas | Pulido, descarachado y preparacion de muros | Trazado tabique/Yeso/auxiliares vent. Y puertas | Chequeo Rasgos Puerta Acceso | Grada Buque (9cm) | Rasgo ventana - terrazas | Despeje caja electricas y enlauchado | Yeso Muro | Yeso Cielo | Sanitario vertical y ramal | Instalación Lana Mineral | Ductos de Extracción | Maquillaje de Terraza | Tabique 1° Cara | Aislación Interior y Refuerzo Plasma |  | Instalaciones Interior Tabique | Tabique 2° cara | Shaft /Tabique | Mochetas y Dinteles Puerta Acceso |  | VALOR MAXIMO | COLOR
|  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF! | #REF! | #REF! |  | 67 | ROJO
|  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF! | #REF! | #REF! |  | 135 | AZUL
|  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF! | #REF! | #REF! |  | 202 | verde
|  | 67 | 67 | 67 | 67 | 67 | 67 | 67 | 67 | 67 | 67 | 67 | 67 | 67 | 67 | 67 |  | 67 | 67 | 67 | 67
|  | 134 | 134 | 134 | 134 | 134 | 134 | 134 | 134 | 134 | 134 | 134 | 134 | 134 | 134 | 134 |  | 134 | 134 | 134 | 134
|  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF! | #REF! | #REF! |  | VALOR MINIMO | VALOR MAXIMO | COLOR
|  | 202 | 202 | 202 | 202 | 202 | 202 | 202 | 202 | 202 | 202 | 202 | 202 | 202 | 202 | 202 |  | 202 | 202 | 202 | 202 |  | 0 | 30 | ROJO
[23 empty] | 31 | 70 | AZUL
|  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF! | #REF! | #REF! |  | 71 | 100
| PISO | Retiro camisas / Tapado Pasadas | Pulido, descarachado y preparacion de muros | Trazado tabique/Yeso/auxiliares vent. Y puertas | Chequeo Rasgos Puerta Acceso | Grada Buque (9cm) | Rasgo ventana - terrazas | Despeje caja electricas | Yeso Muro | Yeso Cielo | Sanitario vertical y ramal | Instalación Lana Mineral Verticales Samitarias | Ductos de Extracción | Maquillaje de Terraza | Tabique 1° Cara | Aislación Interior y Refuerzo Plasma | Enlauchado | Instalaciones Interior Tabique | Tabique 2° cara | Shaft /Tabique | Mochetas y Dinteles Puerta Acceso | Avance Real x Piso
| Piso n°1 | 58.33% | 58.33% | 58.33% | 38.33% | 58.33% | 57.5% | 52.08% | 58.33% | 58.33% | 31.67% | 20.83% | 22.92% | 44.17% | 52.71% | 45.83% | 8.333% | 45% | 36.04% | 13.33% | 11.67% | 41.52%
| Piso n°2 | 97.67% | 95.35% | 26.51% | 29.77% | 46.51% | 19.88% | 48.84% | 45.35% | 18.6% | 0% | 0% | 3.721% | 14.65% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 22.34%
| Piso n°3 | 47.73% | 18.18% | 18.18% | 18.18% | 0% | 0% | 12.27% | 18.18% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 6.636%
| Piso n°4 | [20 empty] | 0% | bar: 1 to 20
| Piso n°5 | [20 empty] | 0% | bar: 1 to 20
| Piso n°6 | [20 empty] | 0% | bar: 1 to 20
| Piso n°7 | [20 empty] | 0% | bar: 1 to 20
| Piso n°8 | [20 empty] | 0% | bar: 1 to 20
| Piso n°9 | [20 empty] | 0% | bar: 1 to 20
| AVANCE PARTIDA | 22.64% | 19.1% | 11.45% | 9.587% | 11.65% | 8.598% | 12.58% | 13.54% | 8.549% | 3.519% | 2.315% | 2.96% | 6.535% | 5.856% | 5.093% | 0.9259% | 5% | 4.005% | 1.481% | 1.296% | 7.833%
7.833%

## AVANCE SEMANAL
Metas
| Partidas | PISO 1 | PISO 2 | PISO 3 | PISO 4 | PISO 5 | PISO 6 | PISO 7 | PISO 8 | PISO 9 | % Avance Real | JUNIO 2026 | JULIO 2026 | AGOSTO 2026 | SEPT. 2026 | OCT. 2026 | NOV. 2026 | DIC. 2026 | ENERO 2027 | FEB. 2027 | MARZO 2027 | ABRIL 2027 | MAYO 2027 | JUNIO 2027 | JULIO 2027
FASE 1 | Retiro camisas / Tapado Pasadas | 58.33% | 97.67% | 47.73% | 0% | 0% | 0% | 0% | 0% | 0% | 22.64% | 58.33% | 97.67% | 47.73% | 0% | 0% | 0% | 0% | 0% | 0%
| Pulido, descarachado y preparacion de muros | 58.33% | 95.35% | 18.18% | 0% | 0% | 0% | 0% | 0% | 0% | 19.1% | 58.33% | 95.35% | 18.18% | 0% | 0% | 0% | 0% | 0% | 0%
| Trazado tabique/Yeso/auxiliares vent. Y puertas | 58.33% | 26.51% | 18.18% | 0% | 0% | 0% | 0% | 0% | 0% | 11.45% | 58.33% | 26.51% | 18.18% | 0% | 0% | 0% | 0% | 0% | 0%
| Chequeo Rasgos Puerta Acceso | 38.33% | 29.77% | 18.18% | 0% | 0% | 0% | 0% | 0% | 0% | 9.587% | 38.33% | 29.77% | 18.18% | 0% | 0% | 0% | 0% | 0% | 0%
| Grada Buque (9cm) | 58.33% | 46.51% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 11.65% | 58.33% | 46.51% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| Rasgo ventana - terrazas | 57.5% | 19.88% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 8.598% | 57.5% | 19.88% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| Despeje caja electricas | 52.08% | 48.84% | 12.27% | 0% | 0% | 0% | 0% | 0% | 0% | 12.58% | 52.08% | 48.84% | 12.27% | 0% | 0% | 0% | 0% | 0% | 0%
| Yeso Muro | 58.33% | 45.35% | 18.18% | 0% | 0% | 0% | 0% | 0% | 0% | 13.54% | 58.33% | 45.35% | 18.18% | 0% | 0% | 0% | 0% | 0% | 0%
| Yeso Cielo | 58.33% | 18.6% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 8.549% | 58.33% | 18.6% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| Sanitario vertical y ramal | 31.67% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 3.519% | 31.67% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| Instalación Lana Mineral Verticales Samitarias | 20.83% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 2.315% | 20.83% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| Ductos de Extracción | 22.92% | 3.721% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 2.96% | 22.92% | 3.721% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| Maquillaje de Terraza | 44.17% | 14.65% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 6.535% | 44.17% | 14.65% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| Tabique 1° Cara | 52.71% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 5.856% | 52.71% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| Aislación Interior y Refuerzo Plasma | 45.83% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 5.093% | 45.83% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| Enlauchado | 8.333% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.9259% | 8.333% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| Instalaciones Interior Tabique | 45% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 5% | 45% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| Tabique 2° cara | 36.04% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 4.005% | 36.04% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| Shaft /Tabique | 13.33% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 1.481% | 13.33% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| Mochetas y Dinteles Puerta Acceso | 11.67% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 1.296% | 11.67% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| PORCENTAJE DE AVANCE POR PISO | 41.52% | 22.34% | 6.636% | 0% | 0% | 0% | 0% | 0% | 0%
| PORCENTAJE DE AVANCE GENERAL DE FASE | 7.833%
FASE 2 | Partidas | PISO 1 | PISO 2 | PISO 3 | PISO 4 | PISO 5 | PISO 6 | PISO 7 | PISO 8 | PISO 9 | % Avance Real
| Huinchas tabiques | 15% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 1.667% |  | 15% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| Instalación Marco Puerta Acceso | 8.333% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.9259% |  | 8.333% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| Marcos Puertas Interiores | 8.333% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.9259% |  | 8.333% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| Impermeabilizacion Baños | 36.67% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 4.074% |  | 36.67% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| Impermeabilizacion Terrazas | 16.67% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 1.852% |  | 16.67% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| Preparación de Pisos | 34.58% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 3.843% |  | 34.58% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| Instalacion de tina/Receptaculo | 8.333% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.9259% |  | 8.333% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| Protección Tina/receptaculo | 8.333% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.9259% |  | 8.333% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| Faldon de tina. | 8.333% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.9259% |  | 8.333% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| Instalación Ventana | 8.333% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.9259% |  | 8.333% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| Ceramica Pisos | 4.167% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.463% |  | 4.167% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| Ceramica Muros | 4.167% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.463% |  | 4.167% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| Instalación de Gargolas en Terraza | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| Frague | 4.167% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.463% |  | 4.167% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| Cerámica de Terrazas | 12.5% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 1.389% |  | 12.5% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| PORCENTAJE DE AVANCE POR PISO | 11.86% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| PORCENTAJE DE AVANCE GENERAL DE FASE | 1.318%
FASE 3 | Partidas | PISO 1 | PISO 2 | PISO 3 | PISO 4 | PISO 5 | PISO 6 | PISO 7 | PISO 8 | PISO 9 | % Avance Real
| Instalación piernas de closet | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| Instalación Cornisas | 8.333% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.9259% |  |  | 8.333% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| Cuadratura de cajas. | 33.33% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 3.704% |  |  | 33.33% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| Remate yeso y cornisas | 8.333% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.9259% |  |  | 8.333% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| Puertas interiores | 8.333% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.9259% |  |  | 8.333% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| Puertas de acceso y pasillo | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| Cerradura Puertas | 8.333% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.9259% |  |  | 8.333% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| Cableado Eléctrico y CCDD | 8.333% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.9259% |  |  | 8.333% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| Canterias | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| Empaste Muro Cielo | 8.333% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.9259% |  |  | 8.333% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| Instalacion Guardapolvo | 8.333% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.9259% |  |  | 8.333% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| Instalación de Baranda de Crital | 8.333% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.9259% |  |  | 8.333% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| Pintura Cielo Terrazas | 8.333% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.9259% |  |  | 8.333% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| Grano Muros Terrazas | 8.333% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.9259% |  |  | 8.333% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| Losalin Cielo Departamento | 8.333% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.9259% |  |  | 8.333% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| Pintura Cielo Baños | 8.333% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.9259% |  |  | 8.333% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| Instalacion de Muebles baño | 8.333% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.9259% |  |  | 8.333% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| Instalacion Muebles de cocina (Base) | 8.333% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.9259% |  |  | 8.333% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| Instalacion Muebles de cocina (Aereo) | 8.333% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.9259% |  |  | 8.333% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| Instalación cubiertas cocina | 8.333% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.9259% |  |  | 8.333% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| Muebles Interior closet | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| PORCENTAJE DE AVANCE POR PISO | 8.333% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| PORCENTAJE DE AVANCE GENERAL DE FASE | 0.9259%
FASE 4 | Partidos | PISO 1 | PISO 2 | PISO 3 | PISO 4 | PISO 5 | PISO 6 | PISO 7 | PISO 8 | PISO 9 | % Avance Real
| Instalacion de Artefactos Sanitarios. | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% |  |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| Extractor de baño. | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% |  |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| Instalación de Shower Door | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% |  |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| Instalacion de Espejos y Retropintados | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% |  |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| Kit de cocina (Horno-Encimera -Campana - Lavaplato) | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% |  |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| Griferia. | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% |  |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| Pruebas de Instalaciones. | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% |  |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| Piso Flotante + cubrejunta + junquillo | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% |  |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| Protección Piso Flotante | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% |  |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| 2da Mano de Pintura | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% |  |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| Instalación de Papel Mural | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% |  |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| Topes en piso y Accesorios | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% |  |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| PORCENTAJE DE AVANCE POR PISO | 2.546% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| PORCENTAJE DE AVANCE GENERAL DE FASE | 0.2829%
| FASE | PISO 1 | PISO 2 | PISO 3 | PISO 4 | PISO 5 | PISO 6 | PISO 7 | PISO 8 | PISO 9 | % Avance Real
| FASE 1 | 41.52% | 22.34% | 6.636% | 0% | 0% | 0% | 0% | 0% | 0% | 7.833%
| FASE 2 | 11.86% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 1.318%
| FASE 3 | 8.333% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.9259%
| FASE 4 | 2.546% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.2829%
|  | PISO 1 | PISO 2 | PISO 3 | PISO 4 | PISO 5 | PISO 6 | PISO 7 | PISO 8 | PISO 9
| Avance Piso | 16.07% | 5.586% | 1.659% | 0% | 0% | 0% | 0% | 0% | 0%

## SEGUIMIENTO R.CRITICA (hidden)
MATRIZ SEGUIMIENTO RUTA CRITICA TERMINACIONES
| Departamento | Trazado | Yeso Cielo | Yeso Muro | Tabique 1° Cara | I. Sanitaria | I. Eléctrica | Extracción | Tabique 2° Cara | Puertas | Cerámicos | Piso Vinilico | Ventanas | Baranda Cristal | Pasta | Papel Mural | Muebles C/B | Muebles Closet | Cubiertas | Retropintado | Av. Depto/Piso
| 102 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| 103 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| 104 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| 105 | 20% | 0% | 90% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 5.789%
| 106 | 20% | 0% | 90% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 5.789%
| 107 | 20% | 0% | 90% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 5.789%
| 108 | 20% | 0% | 90% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 5.789%
| 208 | 20% | 0% | 90% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 5.789%
| 209 | 20% | 0% | 90% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 5.789%
| 210 | 20% | 0% | 90% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 5.789%
| 211 | 20% | 0% | 90% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 5.789%
| 212 | 20% | 0% | 90% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 5.789%
| 213 | 20% | 0% | 90% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 5.789%
| 214 | 20% | 0% | 90% | 0% | 0% | 0% | 0% | 0% | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
| 215 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
| 216 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
| 217 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
| PISO 2 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
| 301 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| 302 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| 303 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| 304 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| 305 | 100% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 10.53%
| 306 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| 307 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| 308 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| 309 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| 310 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| 311 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| 312 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| 313 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| 314 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| 315 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | #DIV/0! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #DIV/0!
| 316 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
| 317 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
| PISO 3 | 5.882% | 0% | 5.882% | 0% | 0% | 0% | 0% | 0% | #DIV/0! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #DIV/0!
| 401 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| 402 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| 403 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| 404 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| 405 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| 406 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| 407 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| 408 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| 409 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| 410 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| 411 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| 412 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| 413 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| 414 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| 415 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
| 416 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
| 417 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
| PISO 4 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
| 501 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| 502 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| 503 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| 504 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| 505 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| 506 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| 507 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| 508 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| 509 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| 510 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| 511 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| 512 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| 513 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| 514 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| 515 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
| 516 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
| 517 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
| PISO 5 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
| 601 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| 602 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| 603 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| 604 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| 605 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| 606 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| 607 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| 608 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| 609 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| 610 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| 611 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| 612 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| 613 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| 614 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| 615 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
| 616 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
| 617 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
| PISO 6 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
| 701 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| 702 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| 703 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| 704 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| 705 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| 706 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| 707 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| 708 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| 709 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| 710 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| 711 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| 712 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| 713 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| 714 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| 715 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
| 716 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
| 717 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
| PISO 7 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
| 801 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| 802 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| 803 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| 804 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| 805 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| 806 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| 807 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| 808 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| 809 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| 810 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| 811 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| 812 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| 813 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| 814 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| 815 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
| 816 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
| 817 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
| PISO 8 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
| 901 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| 902 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| 903 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| 904 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| 905 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| 906 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| 907 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| 908 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| 909 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| 910 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| 911 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| 912 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
| 913 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
| 914 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
| 915 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
| 916 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
| 917 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
| PISO 9 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
| 1001 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
| 1002 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
| 1003 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
| 1004 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
| 1005 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
| 1006 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
| 1007 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
| 1008 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
| 1009 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
| 1010 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
| 1011 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
| 1012 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
| 1013 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
| 1014 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
| 1015 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
| 1016 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
| 1017 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
| PISO 10 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
| 1101 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
| 1102 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
| 1103 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
| 1104 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
| 1105 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
| 1106 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
| 1107 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
| 1108 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
| 1109 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
| 1110 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
| 1111 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
| 1112 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
| 1113 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
| 1114 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
| 1115 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
| 1116 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
| 1117 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
| PISO 11 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
| 1201 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
| 1202 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
| 1203 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
| 1204 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
| 1205 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
| 1206 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
| 1207 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
| 1208 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
| 1209 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
| 1210 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
| 1211 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
| 1212 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
| 1213 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
| 1214 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
| 1215 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
| 1216 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
| PISO 12 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
P.SEMAN |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
|  |  | FEBRERO |  | MARZO |  |  | ABRIL |  | MAYO |  |  | JUNIO
| PROGRAMA R1 |  | PISO 1 | PISO 2 | PISO 3 | PISO 4 | PISO 5 | PISO 6 | PISO 7 | PISO 8 | PISO 9 | PISO 10 | PISO 11 | PISO 12
| % AVANCE |  |  | #REF! | #DIV/0! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
|  |  | MARZO |  | ABRIL |  |  | MAYO |  | JUNIO |  |  | JULIO
| PROGRAMA RF |  | PISO 1 | PISO 2 | PISO 3 | PISO 4 | PISO 5 | PISO 6 | PISO 7 | PISO 8 | PISO 9 | PISO 10 | PISO 11 | PISO 12
% AVANCE
|  |  |  | 99.6% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 97% | 95% | 90% | [6 empty] | 98.33%
GRAFICO AVANCE SEMANAL PARTIDAS

## GANTT_SFCO211
EDIFICIO SAN FRANCISCO
CONSTRUCTORA PAZ SPA |  |  |  |  | Leyenda: | Según lo previsto |  |  |  |  | Riesgo bajo |  |  |  |  | Riesgo medio |  |  |  |  | Riesgo alto |  |  |  | Sin asignar
Leonardo Castro G.
Fecha de inicio del proyecto: | 2026-06-01
Incremento de desplazamiento: | 0 |  |  |  |  | 2026 | [6 empty] | 2027
Descripción del hito | Categoría | Asignado a | Progreso | Inicio | Días | JUN | JUL | AGO | SEPT | OCT | NOV | DIC | ENE | FEB | MAR | ABR | MAY | JUN | JUL | AGO | SEPT | OCT | NOV | DIC
FASE 1 | Hito
Piso 1 | Según lo previsto |  | 41.52% | 2026-06-01 | 30 | bar: 2026 JUN
Piso 2 | Según lo previsto |  | 22.34% | 2026-07-01 | 30 | bar: 2026 JUL
Piso 3 | Según lo previsto |  | 6.636% | 2026-08-01 | 31 | bar: 2026 AGO
Piso 4 | Según lo previsto |  | 0% | 2026-09-01 | 31 | bar: 2026 SEPT
Piso 5 | Según lo previsto |  | 0% | 2026-10-01 | 30 | bar: 2026 OCT
Piso 6 | Según lo previsto |  | 0% | 2026-11-01 | 31 | bar: 2026 NOV
Piso 7 | Según lo previsto |  | 0% | 2026-12-01 | 30 | bar: 2026 DIC
Piso 8 | Según lo previsto |  | 0% | 2027-01-01 | 31 | bar: 2027 ENE
Piso 9 | Según lo previsto |  | 0% | 2027-02-01 | 31 | bar: 2027 FEB
FASE 2
Piso 1 | Según lo previsto |  | 0% | 2026-09-04 | 39 | bar: 2026 AGO
Piso 2 | Según lo previsto |  | 0% | 2026-10-05 | 31 | bar: 2026 SEPT
Piso 3 | Según lo previsto |  | 0% | 2026-11-04 | 30 | bar: 2026 OCT
Piso 4 | Según lo previsto |  | 0% | 2026-12-05 | 31 | bar: 2026 NOV
Piso 5 | Según lo previsto |  | 0% | 2027-01-04 | 30 | bar: 2026 DIC
Piso 6 | Según lo previsto |  | 0% | 2027-02-04 | 31 | bar: 2027 ENE
Piso 7 | Según lo previsto |  | 0% | 2027-03-07 | 31 | bar: 2027 FEB
Piso 8 | Según lo previsto |  | 0% | 2027-04-04 | 28 | bar: 2027 MAR
Piso 9 | Según lo previsto |  | 0% | 2027-05-05 | 31 | bar: 2027 ABR
FASE 3
Piso 1 | Según lo previsto |  | 0% | 2026-10-05 | 31 | bar: 2026 SEPT
Piso 2 | Según lo previsto |  | 0% | 2026-11-04 | 30 | bar: 2026 OCT
Piso 3 | Según lo previsto |  | 0% | 2026-12-05 | 31 | bar: 2026 NOV
Piso 4 | Según lo previsto |  | 0% | 2027-01-04 | 30 | bar: 2026 DIC
Piso 5 | Según lo previsto |  | 0% | 2027-02-04 | 31 | bar: 2027 ENE
Piso 6 | Según lo previsto |  | 0% | 2027-03-07 | 31 | bar: 2027 FEB
Piso 7 | Según lo previsto |  | 0% | 2027-04-04 | 28 | bar: 2027 MAR
Piso 8 | Según lo previsto |  | 0% | 2027-05-05 | 31 | bar: 2027 ABR
Piso 9 | Según lo previsto |  | 0% | 2027-06-04 | 30 | bar: 2027 MAY
FASE 4
Piso 1 | Según lo previsto |  | 0% | 2026-11-04 | 30 | bar: 2026 OCT
Piso 2 | Según lo previsto |  | 0% | 2026-12-05 | 31 | bar: 2026 NOV
Piso 3 | Según lo previsto |  | 0% | 2027-01-04 | 30 | bar: 2026 DIC
Piso 4 | Según lo previsto |  | 0% | 2027-02-04 | 31 | bar: 2027 ENE
Piso 5 | Según lo previsto |  | 0% | 2027-03-07 | 31 | bar: 2027 FEB
Piso 6 | Según lo previsto |  | 0% | 2027-04-04 | 28 | bar: 2027 MAR
Piso 7 | Según lo previsto |  | 0% | 2027-05-05 | 31 | bar: 2027 ABR
Piso 8 | Según lo previsto |  | 0% | 2027-06-04 | 30 | bar: 2027 MAY
Piso 9 | Según lo previsto |  | 0% | 2027-07-05 | 31 | bar: 2027 JUN
Formulas:
Inicio = [Inicio, row above]+30

## IMPRIMIR (hidden)
MATRIZ SEGUIMIENTO RUTA CRITICA TERMINACIONES
Departamento | Trazado | Yeso Cielo | Yeso Muro | Tabique 1° Cara | I. Sanitaria | I. Eléctrica | Extracción | Tabique 2° Cara | Puertas | Cerámicos | Piso Vinilico | Ventanas | Baranda Cristal | Pasta | Pintura | Muebles C/B | Muebles Closet | Cubiertas | Retropintado | Av. Depto/Piso
201
202
203
204
205
206
207
208
209
210
211
212
213
214
215
216
217
PISO 2
301
302
303
304
305
306
307
308
309
310
311
312
313
314
315
316
317
PISO 3
401
402
403
404
405
406
407
408
409
410
411
412
413
414
415
416
417
PISO 4
501
502
503
504
505
506
507
508
509
510
511
512
513
514
515
516
517
PISO 5
601
602
603
604
605
606
607
608
609
610
611
612
613
614
615
616
617
PISO 6
701
702
703
704
705
706
707
708
709
710
711
712
713
714
715
716
717
PISO 7
801
802
803
804
805
806
807
808
809
810
811
812
813
814
815
816
817
PISO 8
901
902
903
904
905
906
907
908
909
910
911
912
913
914
915
916
917
PISO 9
1001
1002
1003
1004
1005
1006
1007
1008
1009
1010
1011
1012
1013
1014
1015
1016
1017
PISO 10
1101
1102
1103
1104
1105
1106
1107
1108
1109
1110
1111
1112
1113
1114
1115
1116
1117
PISO 11
1201
1202
1203
1204
1205
1206
1207
1208
1209
1210
1211
1212
1213
1214
1215
1216
PISO 12

## Hoja2 (hidden)
Etiquetas de fila | Suma de Av. Depto/Piso
PISO 2 | 100%
PISO 3 | 0%
PISO 4 | 0%
PISO 5 | 0%
PISO 6 | 0%
PISO 7 | 0%
PISO 8 | 0%
PISO 9 | 0%
PISO 10 | 0%
PISO 11 | 0%
PISO 12 | 0%
Total general | 100%
Etiquetas de fila | Suma de Av. Depto/Piso
201 | 5.048%
202 | 5.048%
203 | 5.048%
204 | 5.048%
205 | 5.048%
206 | 5.048%
207 | 5.048%
208 | 5.048%
209 | 5.048%
210 | 5.048%
211 | 8.166%
212 | 8.241%
213 | 9.003%
214 | 8.989%
215 | 5.581%
216 | 4.768%
217 | 4.768%
Total general | 100%
Etiquetas de fila | Suma de Av. Depto/Piso
301 | 0
302 | 0
303 | 0
304 | 0
305 | 0
306 | 0
307 | 0
308 | 0
309 | 0
310 | 0
311 | 0
312 | 0
313 | 0
314 | 0
315 | 0
316 | 0
317 | 0
Total general | 0
Etiquetas de fila | Suma de Av. Depto/Piso
401 | 0
402 | 0
403 | 0
404 | 0
405 | 0
406 | 0
407 | 0
408 | 0
409 | 0
410 | 0
411 | 0
412 | 0
413 | 0
414 | 0
415 | 0
416 | 0
417 | 0
Total general | 0

## PROJECT TA Y TB KARINA (hidden)
AVANCE DIARIO POR PARTIDAS TORRE A
| Partidas | PISO | PISO | PISO | PISO | PISO | PISO | PISO | PISO | PISO | PISO | PISO | PISO | PISO | PISO | PISO | PISO | PISO | PISO | 144 | % Avance Real | % Avance Programado | Insidencia en Dias | METAS
|  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18
| 0% | 5.556% | 11.11% | 16.67% | 22.22% | 27.78% | 33.33% | 38.89% | 44.44% | 50% | 55.56% | 61.11% | 66.67% | 72.22% | 77.78% | 83.33% | 88.89% | 94.44% | 100% | 100%
1 | DESCARACHADO Y PULIDO | 0 | 0 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
2 | YESO y REMATES (CUADRATURA CAJAS,ETC…) | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
3 | TRAZADO Y NIVELES | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
4 | ALCANTARILLADO (VERTICALES Y RAMALES) | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
5 | EXTRACCION BAÑOS Y COCINA | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
6 | RASGOS VENTANAS, PUERTAS, ANTEPECHOS | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
7 | GRADA BAJO VENTANA | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
8 | TABIQUE VOLCOMETAL 1ra CARA | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
9 | IMPERMEABILIZACION RASGOS Y VENTANAS | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
10 | DISTRIBUCIÓN ELECT. Y CTE DEBILES EN TABIQUE | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
11 | DISTRIBUCION GASFITERIA EN TABIQUES | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
12 | TABIQUE VOLCOMETAL 2da CARA (incluye Shaff) | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
13 | IMPERMEABILIZACION BAÑO y COCINA | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
14 | HUINCHA TABIQUES, SHAFF Y VIGONES VOLC. | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
15 | VENTANAS | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
16 | INSTALACION PIERNAS Y CENEFAS DE CLOSETS | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
17 | COLOC.PUERTAS INTERIORES Y CENEFAS CORREDERAS | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
18 | NIVELACION PISO | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
19 | COLOCACION DE TINA | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
20 | FALDÓN DE TINA | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
21 | CORNISAS | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
22 | COLOCACION PUERTA DE ACCESO | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
23 | CERAMICA MUROS Y PISO BAÑO/COCINA/TERRAZA | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
24 | COLOCACION DE GUARDAPOLVO | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
25 | PASTA TABIQUES Y MUROS | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
26 | LOSALIN CIELO | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
27 | ALAMBRADO y ENLAUCHADO ELECT. Y CTES DEBILES | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
28 | CERRADURAS | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
29 | 1RA.MANO PINTURA | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
30 | INSTALACION MUEBLES Y PUERTAS DE CLOSETS | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
31 | INST.MUEBLES DE COCINA | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
32 | INST. MUEBLES DE VANITORIOS | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
33 | CUBIERTA DE M.COCINA | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
34 | MANO DE PINTURA FINAL | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
35 | INST.ARTEFACTOS SANITARIOS | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
36 | COLOC.CUBIERTAS BAÑOS | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
37 | PAPEL MURAL | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
38 | VIDRIO RETROPINTADO+ESPEJOS | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
39 | ARTEFACTOS DE COCINA | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
40 | GRIFERIA | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
41 | BARANDA TERRAZA | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
42 | PISO FOTOLAMINADO | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
43 | COLOC.TABLERO ELECTRICO | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
44 | SELLOS (PAPEL, VENTANAS, ETC…) | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
45 | CITOFONO y CORRIENTES DEBILES | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
46 | ASEO FINAL | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
47 | COLOC.ARTEFACTOS ELECTRICOS | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
48 | CONVECTORES | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
49 | ACCESORIOS DE BAÑOS | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
AVANCE DIARIO POR PARTIDAS TORRE B
| Partidas | PISO | PISO | PISO | PISO | PISO | PISO | PISO | PISO | PISO | PISO | PISO | PISO | PISO | PISO | PISO | PISO | PISO | PISO | 144 | % Avance Real | % Avance Programado | Insidencia en Dias | METAS
|  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18
| 0% | 5.5% |  | 11% | 16.5% | 22% | 27.5% | 33% | 38.5% | 44% | 49.5% | 55% | 60.5% | 66% | 71.5% | 77% | 82.5% | 88% | 93.5%
1 | DESCARACHADO Y PULIDO | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0%
2 | YESO y REMATES (CUADRATURA CAJAS,ETC…) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0%
3 | TRAZADO Y NIVELES | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0%
4 | ALCANTARILLADO (VERTICALES Y RAMALES) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0%
5 | EXTRACCION BAÑOS Y COCINA | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0%
6 | RASGOS VENTANAS, PUERTAS, ANTEPECHOS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0%
7 | GRADA BAJO VENTANA | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0%
8 | TABIQUE VOLCOMETAL 1ra CARA | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0%
9 | IMPERMEABILIZACION RASGOS Y VENTANAS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0%
10 | DISTRIBUCIÓN ELECT. Y CTE DEBILES EN TABIQUE | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0%
11 | DISTRIBUCION GASFITERIA EN TABIQUES | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0%
12 | TABIQUE VOLCOMETAL 2da CARA (incluye Shaff) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0%
13 | IMPERMEABILIZACION BAÑO y COCINA | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0%
14 | HUINCHA TABIQUES, SHAFF Y VIGONES VOLC. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0%
15 | VENTANAS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0%
16 | INSTALACION PIERNAS Y CENEFAS DE CLOSETS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0%
17 | COLOC.PUERTAS INTERIORES Y CENEFAS CORREDERAS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0%
18 | NIVELACION PISO | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0%
19 | COLOCACION DE TINA | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0%
20 | FALDÓN DE TINA | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0%
21 | CORNISAS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0%
22 | COLOCACION PUERTA DE ACCESO | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0%
23 | CERAMICA MUROS Y PISO BAÑO/COCINA/TERRAZA | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0%
24 | COLOCACION DE GUARDAPOLVO | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0%
25 | PASTA TABIQUES Y MUROS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0%
26 | LOSALIN CIELO | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0%
27 | ALAMBRADO y ENLAUCHADO ELECT. Y CTES DEBILES | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0%
28 | CERRADURAS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0%
29 | 1RA.MANO PINTURA | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0%
30 | INSTALACION MUEBLES Y PUERTAS DE CLOSETS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0%
31 | INST.MUEBLES DE COCINA | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0%
32 | INST. MUEBLES DE VANITORIOS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0%
33 | CUBIERTA DE M.COCINA | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0%
34 | MANO DE PINTURA FINAL | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0%
35 | INST.ARTEFACTOS SANITARIOS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0%
36 | COLOC.CUBIERTAS BAÑOS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0%
37 | PAPEL MURAL | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0%
38 | VIDRIO RETROPINTADO+ESPEJOS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0%
39 | ARTEFACTOS DE COCINA | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0%
40 | GRIFERIA | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0%
41 | BARANDA TERRAZA | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0%
42 | PISO FOTOLAMINADO | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0%
43 | COLOC.TABLERO ELECTRICO | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0%
44 | SELLOS (PAPEL, VENTANAS, ETC…) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0%
45 | CITOFONO y CORRIENTES DEBILES | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0%
46 | ASEO FINAL | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0%
47 | COLOC.ARTEFACTOS ELECTRICOS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0%
48 | CONVECTORES | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0%
49 | ACCESORIOS DE BAÑOS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0%
Note on W5: Autor: AVANCE DEACUERDO A LAST PLANER
Note on W63: Autor: AVANCE DEACUERDO A LAST PLANER

## EXEL KARINA (hidden)
PORCENTAJES DE AVANCES A LA FECHA
OBRA PEDRO ALARCON
| 201-A | 202-A | 203-A | 204-A | 205-A | 206-A | 207-A | 301-A | 302-A | 303-A | 304-A | 305-A | 306-A | 307-A | 308-A | 401-A | 402-A | 403-A | 404-A | 405-A | 406-A | 407-A | 408-A | 501-A | 502-A | 503-A | 504-A | 505-A | 506-A | 507-A | 508-A | 601-A | 602-A | 603-A | 604-A | 605-A | 606-A | 607-A | 608-A | 701-A | 702-A | 703-A | 704-A | 705-A | 706-A | 707-A | 708-A | 801-A | 802-A | 803-A | 804-A | 805-A | 806-A | 807-A | 808-A | 901-A | 902-A | 903-A | 904-A | 905-A | 906-A | 907-A | 908-A | 1001-A | 1002-A | 1003-A | 1004-A | 1005-A | 1006-A | 1007-A | 1008-A | 1101-A | 1102-A | 1103-A | 1104-A | 1105-A | 1106-A | 1107-A | 1108-A | 1201-A | 1202-A | 1203-A | 1204-A | 1205-A | 1206-A | 1207-A | 1208-A | 1301-A | 1302-A | 1303-A | 1304-A | 1305-A | 1306-A | 1307-A | 1308-A | 1401-A | 1402-A | 1403-A | 1404-A | 1405-A | 1406-A | 1407-A | 1408-A | 1501-A | 1502-A | 1503-A | 1504-A | 1505-A | 1506-A | 1507-A | 1508-A | 1601-A | 1602-A | 1603-A | 1604-A | 1605-A | 1606-A | 1607-A | 1608-A | 1701-A | 1702-A | 1703-A | 1704-A | 1705-A | 1706-A | 1707-A | 1708-A | 1801-A | 1802-A | 1803-A | 1804-A | 1805-A | 1806-A | 1807-A | 1808-A | 1901-A | 1902-A | 1903-A | 1904-A | 1905-A | 1906-A | 1907-A | 1908-A | 201-B | 202-B | 203-B | 204-B | 205-B | 206-B | 207-B | 301-B | 302-B | 303-B | 304-B | 305-B | 306-B | 307-B | 308-B | 401-B | 402-B | 403-B | 404-B | 405-B | 406-B | 407-B | 408-B | 501-B | 502-B | 503-B | 504-B | 505-B | 506-B | 507-B | 508-B | 601-B | 602-B | 603-B | 604-B | 605-B | 606-B | 607-B | 608-B | 701-B | 702-B | 703-B | 704-B | 705-B | 706-B | 707-B | 708-B | 801-B | 802-B | 803-B | 804-B | 805-B | 806-B | 807-B | 808-B | 901-B | 902-B | 903-B | 904-B | 905-B | 906-B | 907-B | 908-B | 1001-B | 1002-B | 1003-B | 1004-B | 1005-B | 1006-B | 1007-B | 1008-B | 1101-B | 1102-B | 1103-B | 1104-B | 1105-B | 1106-B | 1107-B | 1108-B | 1201-B | 1202-B | 1203-B | 1204-B | 1205-B | 1206-B | 1207-B | 1208-B | 1301-B | 1302-B | 1303-B | 1304-B | 1305-B | 1306-B | 1307-B | 1308-B | 1401-B | 1402-B | 1403-B | 1404-B | 1405-B | 1406-B | 1407-B | 1408-B | 1501-B | 1502-B | 1503-B | 1504-B | 1505-B | 1506-B | 1507-B | 1508-B | 1601-B | 1602-B | 1603-B | 1604-B | 1605-B | 1606-B | 1607-B | 1608-B | 1701-B | 1702-B | 1703-B | 1704-B | 1705-B | 1706-B | 1707-B | 1708-B | 1801-B | 1802-B | 1803-B | 1804-B | 1805-B | 1806-B | 1807-B | 1808-B | 1901-B | 1902-B | 1903-B | 1904-B | 1905-B | 1906-B | 1907-B | 1908-B
DESCARACHADO Y PULIDO | 0% | 0% | 0% | 0% | 0% | 0% | 0% | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
YESO y REMATES (CUADRATURA CAJAS,ETC…) | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
TRAZADO Y NIVELES | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
ALCANTARILLADO (VERTICALES Y RAMALES) | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
EXTRACCION BAÑOS Y COCINA | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
RASGOS VENTANAS, PUERTAS, ANTEPECHOS | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
GRADA BAJO VENTANA | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
TABIQUE VOLCOMETAL 1ra CARA | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
IMPERMEABILIZACION RASGOS Y VENTANAS | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
DISTRIBUCIÓN ELECT. Y CTE DEBILES EN TABIQUE | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
DISTRIBUCION GASFITERIA EN TABIQUES | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
TABIQUE VOLCOMETAL 2da CARA (incluye Shaff) | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
IMPERMEABILIZACION BAÑO y COCINA | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
HUINCHA TABIQUES, SHAFF Y VIGONES VOLC. | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
VENTANAS | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
INSTALACION PIERNAS Y CENEFAS DE CLOSETS | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
COLOC.PUERTAS INTERIORES Y CENEFAS CORREDERAS | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
NIVELACION PISO | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
COLOCACION DE TINA | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
FALDÓN DE TINA | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
CORNISAS | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
COLOCACION PUERTA DE ACCESO | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
CERAMICA MUROS Y PISO BAÑO/COCINA/TERRAZA | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
COLOCACION DE GUARDAPOLVO | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
PASTA TABIQUES Y MUROS | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
LOSALIN CIELO | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
ALAMBRADO y ENLAUCHADO ELECT. Y CTES DEBILES | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
CERRADURAS | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
1RA.MANO PINTURA | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
INSTALACION MUEBLES Y PUERTAS DE CLOSETS | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
INST.MUEBLES DE COCINA | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
INST. MUEBLES DE VANITORIOS | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
CUBIERTA DE M.COCINA | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
MANO DE PINTURA FINAL | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
INST.ARTEFACTOS SANITARIOS | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
COLOC.CUBIERTAS BAÑOS | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
PAPEL MURAL | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
VIDRIO RETROPINTADO+ESPEJOS | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
ARTEFACTOS DE COCINA | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
GRIFERIA | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
BARANDA TERRAZA | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
PISO FOTOLAMINADO | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
COLOC.TABLERO ELECTRICO | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
SELLOS (PAPEL, VENTANAS, ETC…) | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
CITOFONO y CORRIENTES DEBILES | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
ASEO FINAL | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
COLOC.ARTEFACTOS ELECTRICOS | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
CONVECTORES | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
ACCESORIOS DE BAÑOS | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
REVISION 1
ENTREGA FINAL DEPTO
| TORRE A | [18 empty] | TORRE B
PASILLOS | 201-A: PISO 1; 202-A: PISO 2; 203-A: PISO 3; 204-A: PISO 4; 205-A: PISO 5; 206-A: PISO 6; 207-A: PISO 7; 301-A: PISO 8; 302-A: PISO 9; 303-A: PISO 10; 304-A: PISO 11; 305-A: PISO 12; 306-A: PISO 13; 307-A: PISO 14; 308-A: PISO 15; 401-A: PISO 16; 402-A: PISO 17; 403-A: PISO 18; 404-A: PISO 19; 405-A: PISO 1; 406-A: PISO 2; 407-A: PISO 3; 408-A: PISO 4; 501-A: PISO 5; 502-A: PISO 6; 503-A: PISO 7; 504-A: PISO 8; 505-A: PISO 9; 506-A: PISO 10; 507-A: PISO 11; 508-A: PISO 12; 601-A: PISO 13; 602-A: PISO 14; 603-A: PISO 15; 604-A: PISO 16; 605-A: PISO 17; 606-A: PISO 18; 607-A: PISO 19; 201-B: P1; 202-B: P2; 203-B: P3; 204-B: p4
Tabiques | 201-A: 50; 202-A: 100; 201-B: 100%; 202-B: 100%; 203-B: 100%; 204-B: 100%
Puertas
Ceramicas | 202-B: 30%
Guardapolvo
Empaste y Pintura | 202-B: 70%; 203-B: 50%; 204-B: 30%
Agua Potable | 202-B: 50%; 203-B: 50%; 204-B: 50%
Electricidad
Lamparas

## PROJECT OBRA TA Y TB (hidden)
RESUMEN POR PARTIDAS TORRE A
| Partidas | PISO | PISO | PISO | PISO | PISO | PISO | PISO | PISO | PISO | PISO | PISO | PISO | PISO | PISO | PISO | PISO | PISO | PISO | PISO | 1900 | % Avance Real | % Avance Programado | Insidencia en Dias | METAS
|  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19
| 0% | 5.263% | 10.53% | 15.79% | 21.05% | 26.32% | 31.58% | 36.84% | 42.1% | 47.37% | 52.63% | 57.89% | 63.16% | 68.42% | 73.68% | 78.95% | 84.21% | 89.47% | 94.74% | 100%
1 | DESCARACHADO Y PULIDO |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 100%
2 | TABIQUE |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
3 | BARANDA TERRAZA |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 100%
4 | YESO y REMATES (CUADRATURA CAJAS,ETC…) |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 100%
5 | INST PUERTAS |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
6 | CERAMICA MUROS Y PISO BAÑO/COCINA/TERRAZA |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 100%
7 | VENTANAS |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 100%
8 | PINTURA CIELO |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 100%
9 | PINTURA PUERTAS |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
10 | ASEO GRUESO
11 | PAPEL MURAL |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 100%
12 | MUEBLES |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
13 | CUBIERTA DE M.COCINA |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 100%
14 | ASEO FINAL |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 100%
AVANCE DIARIO POR PARTIDAS TORRE A 01-Enero-2015
| Partidas | PISO | PISO | PISO | PISO | PISO | PISO | PISO | PISO | PISO | PISO | PISO | PISO | PISO | PISO | PISO | PISO | PISO | PISO | PISO | 1900 | % Avance Real | % Avance Programado | Insidencia en Dias | METAS
|  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19
| 0% | 5.263% | 10.53% | 15.79% | 21.05% | 26.32% | 31.58% | 36.84% | 42.1% | 47.37% | 52.63% | 57.89% | 63.16% | 68.42% | 73.68% | 78.95% | 84.21% | 89.47% | 94.74% | 100%
1 | DESCARACHADO Y PULIDO |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 5.263%
2 | YESO y REMATES (CUADRATURA CAJAS,ETC…) |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0%
3 | TRAZADO Y NIVELES |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0%
4 | ALCANTARILLADO (VERTICALES Y RAMALES) |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0%
5 | EXTRACCION BAÑOS Y COCINA |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0%
6 | RASGOS VENTANAS, PUERTAS, ANTEPECHOS |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0%
7 | GRADA BAJO VENTANA |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0%
8 | TABIQUE VOLCOMETAL 1ra CARA |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0%
9 | IMPERMEABILIZACION RASGOS Y VENTANAS |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0%
10 | DISTRIBUCIÓN ELECT. Y CTE DEBILES EN TABIQUE |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0%
11 | DISTRIBUCION GASFITERIA EN TABIQUES |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0%
12 | TABIQUE VOLCOMETAL 2da CARA (incluye Shaff) |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0%
13 | IMPERMEABILIZACION BAÑO y COCINA |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0%
14 | HUINCHA TABIQUES, SHAFF Y VIGONES VOLC. |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0%
15 | VENTANAS |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0%
16 | INSTALACION PIERNAS Y CENEFAS DE CLOSETS |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0%
17 | COLOC.PUERTAS INTERIORES Y CENEFAS CORREDERAS |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0%
18 | NIVELACION PISO |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0%
19 | COLOCACION DE TINA |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0%
20 | FALDÓN DE TINA |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0%
21 | CORNISAS |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0%
22 | COLOCACION PUERTA DE ACCESO |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0%
23 | CERAMICA MUROS Y PISO BAÑO/COCINA/TERRAZA |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0%
24 | COLOCACION DE GUARDAPOLVO |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0%
25 | PASTA TABIQUES Y MUROS |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0%
26 | LOSALIN CIELO |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0%
27 | ALAMBRADO y ENLAUCHADO ELECT. Y CTES DEBILES |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0%
28 | CERRADURAS |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0%
29 | 1RA.MANO PINTURA |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0%
30 | INSTALACION MUEBLES Y PUERTAS DE CLOSETS |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0%
31 | INST.MUEBLES DE COCINA |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0%
32 | INST. MUEBLES DE VANITORIOS |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0%
33 | CUBIERTA DE M.COCINA |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0%
34 | MANO DE PINTURA FINAL |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0%
35 | INST.ARTEFACTOS SANITARIOS |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0%
36 | COLOC.CUBIERTAS BAÑOS |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0%
37 | PAPEL MURAL |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0%
38 | VIDRIO RETROPINTADO+ESPEJOS |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0%
39 | ARTEFACTOS DE COCINA |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0%
40 | GRIFERIA |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0%
41 | BARANDA TERRAZA |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0%
42 | PISO FOTOLAMINADO |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0%
43 | COLOC.TABLERO ELECTRICO |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0%
44 | SELLOS (PAPEL, VENTANAS, ETC…) |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0%
45 | CITOFONO y CORRIENTES DEBILES |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0%
46 | ASEO FINAL |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0%
47 | COLOC.ARTEFACTOS ELECTRICOS |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0%
48 | CONVECTORES |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0%
49 | ACCESORIOS DE BAÑOS |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0%
AVANCE DIARIO POR PARTIDAS TORRE B 01-Enero-2015
| Partidas | PISO | PISO | PISO | PISO | PISO | PISO | PISO | PISO | PISO | PISO | PISO | PISO | PISO | PISO | PISO | PISO | PISO | PISO | PISO | 1900 | % Avance Real | % Avance Programado | Insidencia en Dias | METAS
|  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19
| 0% | 5.263% | 10.53% | 15.79% | 21.05% | 26.32% | 31.58% | 36.84% | 42.1% | 47.37% | 52.63% | 57.89% | 63.16% | 68.42% | 73.68% | 78.95% | 84.21% | 89.47% | 94.74% | 100%
1 | DESCARACHADO Y PULIDO |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 5.263%
2 | YESO y REMATES (CUADRATURA CAJAS,ETC…) |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0%
3 | TRAZADO Y NIVELES |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0%
4 | ALCANTARILLADO (VERTICALES Y RAMALES) |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0%
5 | EXTRACCION BAÑOS Y COCINA |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0%
6 | RASGOS VENTANAS, PUERTAS, ANTEPECHOS |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0%
7 | GRADA BAJO VENTANA |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0%
8 | TABIQUE VOLCOMETAL 1ra CARA |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0%
9 | IMPERMEABILIZACION RASGOS Y VENTANAS |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0%
10 | DISTRIBUCIÓN ELECT. Y CTE DEBILES EN TABIQUE |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0%
11 | DISTRIBUCION GASFITERIA EN TABIQUES |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0%
12 | TABIQUE VOLCOMETAL 2da CARA (incluye Shaff) |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0%
13 | IMPERMEABILIZACION BAÑO y COCINA | 2: #REF! | #REF! | #REF! | 0%
14 | HUINCHA TABIQUES, SHAFF Y VIGONES VOLC. |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0%
15 | VENTANAS |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0%
16 | INSTALACION PIERNAS Y CENEFAS DE CLOSETS |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0%
17 | COLOC.PUERTAS INTERIORES Y CENEFAS CORREDERAS |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0%
18 | NIVELACION PISO |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0%
19 | COLOCACION DE TINA |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0%
20 | FALDÓN DE TINA |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0%
21 | CORNISAS |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0%
22 | COLOCACION PUERTA DE ACCESO |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0%
23 | CERAMICA MUROS Y PISO BAÑO/COCINA/TERRAZA |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0%
24 | COLOCACION DE GUARDAPOLVO |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0%
25 | PASTA TABIQUES Y MUROS |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0%
26 | LOSALIN CIELO |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0%
27 | ALAMBRADO y ENLAUCHADO ELECT. Y CTES DEBILES |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0%
28 | CERRADURAS |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0%
29 | 1RA.MANO PINTURA |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0%
30 | INSTALACION MUEBLES Y PUERTAS DE CLOSETS |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0%
31 | INST.MUEBLES DE COCINA |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0%
32 | INST. MUEBLES DE VANITORIOS |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0%
33 | CUBIERTA DE M.COCINA |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0%
34 | MANO DE PINTURA FINAL |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0%
35 | INST.ARTEFACTOS SANITARIOS |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0%
36 | COLOC.CUBIERTAS BAÑOS |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0%
37 | PAPEL MURAL |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0%
38 | VIDRIO RETROPINTADO+ESPEJOS |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0%
39 | ARTEFACTOS DE COCINA |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0%
40 | GRIFERIA |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0%
41 | BARANDA TERRAZA |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0%
42 | PISO FOTOLAMINADO |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0%
43 | COLOC.TABLERO ELECTRICO |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0%
44 | SELLOS (PAPEL, VENTANAS, ETC…) |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0%
45 | CITOFONO y CORRIENTES DEBILES |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0%
46 | ASEO FINAL |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0%
47 | COLOC.ARTEFACTOS ELECTRICOS |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0%
48 | CONVECTORES |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0%
49 | ACCESORIOS DE BAÑOS |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0%
Note on X4: Autor: AVANCE DEACUERDO A LAST PLANER
Note on X26: Autor: AVANCE DEACUERDO A LAST PLANER
Note on X84: Autor: AVANCE DEACUERDO A LAST PLANER

## GRAFICOS TA Y TB (hidden)
RESUMEN PARA GRAFICOS X DPTOS
| DESCARACHADO | TRAZADO TAB. | BARANDAS | TAB. ESTRUCTURA | TAB. 1 CARA | TAB 2 CARA | HUINCHAS TAB. | YESO | IMPERMEABILIZACION | CORNIZAS | CERAMICA MURO BA | INST. TINAS | CERAMICA PISO COCINA | CERAMICA MURO COCINA | CERAMICA PISO BAÑO | MUEBLES (COC,CL,) | INST. PUERTAS
PISO | DPTOS | DPTOS | DPTOS | DPTOS | DPTOS | DPTOS | DPTOS | DPTOS | DPTOS | DPTOS | DPTOS | DPTOS | DPTOS | DPTOS | DPTOS | DPTOS | DPTOS
1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2 | 0 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
3 | 0 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
4 | 0 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
5 | 0 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
6 | 0 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
7 | 0 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
8 | 0 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
9 | 0 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
10 | 0 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
11 | 0 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
12 | 0 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
13 | 0 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
14 | 0 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
15 | 0 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
16 | 0 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
17 | 0 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
18 | 0 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
19 | 0 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
| AVANCE PARA GRAFICOS | [16 empty] | CANTIDAD DPTOS | 8
| DESCARACHADO | TRAZADO TAB. | BARANDAS | TAB. ESTRUCTURA | TAB. 1 CARA | TAB 2 CARA | HUINCHAS TAB. | YESO | IMPERMEABILIZACION | CORNIZAS | CERAMICA MURO BA | INST. TINAS | CERAMICA PISO COCINA | CERAMICA MURO COCINA | CERAMICA PISO BAÑO | MUEBLES (COC,CL,) | INST. PUERTAS
PISO | DPTOS | DPTOS | DPTOS | DPTOS | DPTOS | DPTOS | DPTOS | DPTOS | DPTOS | DPTOS | DPTOS | DPTOS | DPTOS | DPTOS | DPTOS | DPTOS | DPTOS
1
2 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
3 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
4 |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
5 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
6 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
7 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
8 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
9 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
10 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
11 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
12 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
13 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
14 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
15 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
16 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
17 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
18 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
19 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
| AVANCE PARA GRAFICOS | [16 empty] | CANTIDAD DPTOS | 8
| DESCARACHADO | TRAZADO TAB. | BARANDAS | TAB. ESTRUCTURA | TAB. 1 CARA | TAB 2 CARA | HUINCHAS TAB. | YESO | IMPERMEABILIZACION | CORNIZAS | CERAMICA MURO BA | INST. TINAS | CERAMICA PISO COCINA | CERAMICA MURO COCINA | CERAMICA PISO BAÑO | MUEBLES (COC,CL,) | INST. PUERTAS
PISO | DPTOS | DPTOS | DPTOS | DPTOS | DPTOS | DPTOS | DPTOS | DPTOS | DPTOS | DPTOS | DPTOS | DPTOS | DPTOS | DPTOS | DPTOS | DPTOS | DPTOS
1
2 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
3 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
4 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
5 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
6 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
7 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
8 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
9 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
10 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
11 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
12 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
13 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
14 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
15 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
16 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
17 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
18 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
19 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!

## PROG TERMINACIONES (hidden)
FASE 1
| Descarachado y Pulido | Trazado y niveles tabiques gradas dint, cielo | Retiro de camisas | Tapada de pasadas | Ductos alcantarillado | Pruebas de agua recep. | Ductos extracción | Tabique 1er cara | Colocación lana mineral | Inst. Elec.y Tabiques | Tabique 2da cara | Yesos Pasillo | Yesos Departamentos | Cielos falsos Volcanitas ( Vigones cocinas y baños ) | Huincha Cielos tabiques (vigones cocinas y baños) | Huincha Muros Deptos. | Baranda Balcones | Rasgos Ventanas | Instalación fierro grada buque | Grada Buque Albañilería + Alfeiser y bloq. | Impermeabilizacion rasgos de ventanas
PISO | LEGADO 1 | LEGADO 1 | LEGADO 1 | LEGADO 1 | LEGADO 1 | LEGADO 1 | LEGADO 1 | LEGADO 1 | LEGADO 1 | LEGADO 1 | LEGADO 1 | LEGADO 1 | LEGADO 1 | LEGADO 1 | LEGADO 1 | LEGADO 1 | LEGADO 1 | LEGADO 1 | LEGADO 1 | LEGADO 1 | LEGADO 1
1 | 0 | 0 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
2 | #REF! | 0 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
3 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
4 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
5 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
6 | #REF! | 0 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
7 | 0 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
8 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
9 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
10 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
11 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
12 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
13 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
14 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
15 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
16 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
17 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
18 | 0 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
FASE 2
| Kangueo y desbaste de pisos | Afinado de pisos y terrazas | Colocacion de gargolas | Impermeabilizacion de baños y cocina | Refuerzo de tinas | Instalacion de Tinas | Faldon de Tinas / Zocalo | Instalacion de Ventanas | Vigones baño y Cocina | Instalacion Marco y puerta de acceso | Instalacion cerradura puerta acceso | Colocacion de cornisa | Coloc. Ceramica Cocina | Coloc. Porcelanato piso baño | Coloc. Porcelanato Terraza | Ceramicos muro Cocina | Ceramicos muro baño | Ceramicos Pasillos
PISO | TORRE A | TORRE A | TORRE A | TORRE A | TORRE A | TORRE A | TORRE A | TORRE A | TORRE A | TORRE A | TORRE A | TORRE A | TORRE A | TORRE A | TORRE A | TORRE A | TORRE A | TORRE A
2 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
3 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
4 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
5 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
6 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
7 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
8 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
9 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
10 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
11 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
12 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
13 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
14 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
15 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
16 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
17 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
18 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
19 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
FASE 3
| Aplicación de Pasta muros y cielos deptos. | Aplicación de bases (latex), cielos deptos. LIJADO | Colocacion piernas de closet y cenefas | Colocacion marcos y puertas interiores | Colocacion cerradura interiores | Enlauchado | Cableado | Colocacion de artefactos Electricos | Colocacion Guardapolvo | Aplicación de Losalin (textura deptos.) | Colocacion de Artefactos Sanitarios | Colocacion de extractor | Lijado y Aplicación Esmalte | Pintura Puertas , Cornizas, guarda polvo | Instalacion Muebles Cocina | Instalacion Closet | Instalacion de Granito (Marmol)
PISO | TORRE A | TORRE A | TORRE A | TORRE A | TORRE A | TORRE A | TORRE A | TORRE A | TORRE A | TORRE A | TORRE A | TORRE A | TORRE A | TORRE A | TORRE A | TORRE A | TORRE A
2 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
3 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
4 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
5 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
6 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
7 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
8 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
9 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
10 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
11 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
12 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
13 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
14 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
15 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
16 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
17 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
18 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
19 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
FASE 4
| Colocacion de Vanitorio | Aplicación final esmalte cocina-baños-walking closet | instalacion piso flotante y 1/4 rodon | Aplicación 2da mano y final de pintura de corniza-puertas | colocacion lavaplatos y griferia | colocacion artefactos electricos (horno, encimera, campana) | colocacion accesorios de baño, topes puertas | 2da mano de pintura muros y guardapolvo | Aseo Final
PISO | TORRE A | TORRE A | TORRE A | TORRE A | TORRE A | TORRE A | TORRE A | TORRE A | TORRE A
2 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
3 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
4 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
5 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
6 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
7 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
8 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
9 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
10 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
11 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
12 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
13 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
14 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
15 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
16 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
17 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
18 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
19 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!